## project resource allocation
ISP team | 5
Video team | 5
SOC team | 13
Analog team | 5
CEVA team | 2
new guy | 5
total man | 35
every one need at least 50GB disk | 1750
physical implement need 100GB for every sub block syn/fm/sdc(6x sub block) | 600
PR team need 100GB for every sub block | 1000
Analog team need 150GB per one | 750
veloce team need at least 200GB | 500
FPGA team need 200GB | 200
total disk request | 4800
total disk request*2(margin) | 9600

## resource
role
SOC |  | Pan song | soc arch plan, project plan and management
| PHY Implement | chen peng* | physical implement, SYN/FM/sdc/memory gen/DCG/Lowpower/cdc
|  | zhang jiajie | physical implement, SYN/FM/sdc/memory gen
|  | ?? | Back end layout /contract with BE team/floor plan/MFU
|  | ?? | scan/ mbist insert on RTL
| Integration | zhonghuibo* | Chip TOP/CGU/RGU/IO WRAP/ball map/PCB/package
|  | sunhao | USB/ MIPI DSI verification/GMAC (perfor enchance)/SEC/OTP | need license study
|  | xiezheng | MIPI(MIPI DSI develop)/DVP/VIF | need license study
|  | zhanghao | CA7/ CCI/DMAC/BOOTROM/CS/NOC | need license study
|  | maji | DDR/ M7_peri /I2S/SDC/eMMC/OTP verification | need license study
|  | yanglei | CEVA integration/verification/SRAM
| System verification | huang jinfeng* | verification env, plan , CNN acc verfication
|  | zhangxiangping | FPGA /IP verification/MIPI DSI verification.
|  | zhangjianzhong | veloce/IP verification
|  | shenzhongjian | FPGA/IP verification
video |  | liu jialiang* | H264,HEVC,JEPG,DE opt. save more area
|  | yu lei | H265,HEVC,JEPG,DE opt. save more area
|  | yuan xing | H266,HEVC,JEPG,DE opt. save more area
|  | hu li | H267,HEVC,JEPG,DE opt. save more area
|  | shen weiwei | video task
ISP |  | Wanghua* | ISP opt, save more area
yuezhi
jiangmingquan
zengqiang
mabin
| CNN acc | liu cong | NPU accelarator RTL develop
yili
|  | ?? | NPU acc verfication
??
Analog |  | YuanYuan | MIPI PHY opt/MPW/PLL/SAR-ADC
Lizhe
Fukai
xiaoyuzhong
wangxiongxiong
IT |  | haitao
| total resource request | 35