## Sheet1
No. | date | flow name | action | comments
1 | 2017-10-30 | T.O. | Get GDS from VSI
2 | 2017-10-30 | transfer GDS to ICC ftp | copy GDS to ICC ftp
3 | 2017-10-31 | transfer GDS to TSMC ftp | ICC transfer GDS to TSMC ftp
4 | 2017-11-01 | IP merge | OTP IP merge into whole GDS confirm Kilopass upload file checksum | kilopass IP is not qualified by TSMC, 128Kb IP is only mass production by TSMC 28HPM tech, not HPC.
5 | 2017-11-03 | IP merge done | export log, waiting for e-Jobview update GDS inform table for ICC side.
6 | 2017-11-03 | Dry run | kick dry run on TSMC
7 | 2017-11-07 | Real TO | pass dry run check, TSMC start real TO
8 | 2017-11-08 | Jobview | VSI do it
9 | 2017/11/10-14 | sign off table | MT form from TSMC check list from ICC 6xWafer, how to run. DRC vio Waive report | 4x run to contract, 2x all run.
10 | 2017-11-17 | photo die map | need it for manufacture material order | sirius 800/wafer
11 | 2017-11-27 | Wafer start
12 | 2017-11-27 | socket spec check |  | For package design, impact.
13 | 2017-11-29 | marking sample | prepare all information | font/lot infor/style
14 | 2017-12-25 | Package production order | 1st only product 200 package chip
| 2018-01-03 | EK PCB gerbe out
15 | 2018-01-08 | Project out date | wafer bump out | Need get Lot ID / Wafer ID information, forward to VSI
16 | 2018-01-11 | Ship date from TSMC
17 | 2018-01-15 | wait from Customs | Magic valley release packing list Forward to VSI test team
| 2018-01-16 | Get from Customs | Delivery to JSCC by Fedex
2018-01-17
18 | ??? | EK PCB board bring up | test power sequence/voltage
19
20