## action items
Status and Action Items
Issues: Library | Action Items | owner | open date | close date | status
memory cell update from LVT to SVT | artosyn to provide library | artosyn |  |  | open
CDM buffer | provide clamp cell liberty/verilog model/lef/gds/lvs netlist | artosyn |  |  | open
| provide pin list to insert clamp cell | artosyn |  |  | open
| wrap clamp with buffer | VSI |  |  | open
ABB verilog behavior model | Double check the integrity of verilog models of ABB to exactly match the actual behavior | artosyn |  |  | open
ABB LEF | to update with latest bump location | artosyn |  |  | close
place BUMP cell upon DDR SSTL IO cells | to check with snps | artosyn | 2017-05-03 |  | open
update ROM after code freeze |  | artosyn |  |  | open
Issues: Tech File | Action Items | owner | open date | close date | status
ITF/ICT/QRC/NXTgrd with "_T" | arotsyn to check with TSMC | artosyn |  |  | open
Issues: Timing Signoff Creteria | Action Items | owner | open date | close date | status
setup uncertainty | Artosyn to decide | artosyn |  |  | open
MEM signoff library (ffbc or ff) | Artosyn to confirm use ffbc or ff to signoff | artosyn |  |  | open
Issues: netlist | Action Items | owner | open date | close date | status
ceva core | artosyn to release DCG netlist | artosyn |  |  | open
| reduce LVT pct , currently 23% | artosyn |  |  | open
| UPF is not available | artosyn |  |  | open
| add power switch control port | artosyn |  |  | open
| ceva core ICG enable change for test mode | artosyn |  |  | open
ceva harden | Artosyn to update ceva harden netlist to reduce 28K pin number | artosyn |  |  | close
| artosyn to update NL to replace clock divider from neg-trigger to pos-trigger | artosyn |  |  | close
| add buffer "UCLKPRE" after throttle_0 | artosyn | 2017-05-03 |  | open
| UPF is not available/add isolation cell | artosyn |  |  | open
ceva subsys | UPF is not available | artosyn |  |  | open
| add LVL cell/ISO cell | artosyn |  |  | open
ceva subsys flatten | flatten SDC | artosyn |  |  | open
| flatten UPF | artosyn |  |  | open
ca7 core | UPF is not available/add power switch control port |  |  |  | open
ca7 harden | VSI to provide DEF for DCG | VSI | 2017-05-03 |  | open
| UPF is not available | artosyn |  |  | open
| add LVL/ISO in netlist | artosyn |  |  | open
ca7 subsystem | UPF is not available |  |  |  | open
| add LVL cell/ISO cell |  |  |  | open
ca7 subsys flatten | flatten SDC |  |  |  | open
| flatten UPF |  |  |  | open
DDR | VSI release DEF(version 4) with shinked size to Artosyn;; Artosyn to check with this version | VSI/artosyn |  |  | open
| Artosyn to release NL/SDC/DEF (version 2) to VSI | artosyn |  |  | open
| Artosyn to add 300ps uncertainy global and 450ps uncertainty for clock gating ; to check OCV derating applied in synthesis | artosyn |  |  | open
| VSI to propotype the version2/version 4(shrinked size) | VSI | 2017-05-03 |  | open
| don’t touch net in DDR implementation check list | artosyn
sub1 | MIPI should use BIO for master mode | artosyn |  |  | open
| sub1 scan clock gating logic remove | artosyn |  |  | open
sub3 | add don’t touch for BUMP net | artosyn |  |  | open
| add ports which tie ground in substrate and mark it in pin assignment | artosyn |  |  | open
| at speed clock controlled by scan mode only , no mbist mode |  |  |  | open
| at speed clock frequency not match function | artosyn |  |  | open
top | to add 3.3v IO | artosyn |  |  | open
| add isolation for isp/hevc | artosyn |  |  | open
| UPF is not availabe | artosyn |  |  | open
flatten | UPF is not availabe | artosyn |  |  | open
| add SDC | artosyn |  |  | open
Issues: inter-connection | Action Items | owner | open date | close date | status
many inter-connections between P1/p2 | move display from P1 to P2 | artosyn | 2017-04-24 | 2017-04-24 | close
inter-connection between P1/P3 | Artosyn to add async FIFO in P1, add slice pipeline in top | artosyn | 2017-04-24 |  | open
clock supply from block to top | artosyn to update netlist to remove aclk* of BB | artosyn | 2017-04-24 |  | open
clock supply from block to top | P4: m7 to TOP | artosyn | 2017-04-24 |  | close
local reset synchronization | Artosyn to double check all block already have local reset synchronization | artosyn |  |  | close
Issues: Netlist(DFT) | Action Items | owner | open date | close date | status
PLL reference clock clock for at speed test |  PLL reference clock need to be switched to crystal oscillator in scan¦mbist mode, the frequency should be as high as in functional mode. At least Audio PLL ref_clk(from HDMI in function mode) should be switched . Artosyn to check any other ref clock have same issue. | VSI |  |  | to be verified
cgu control for at speed test |  Throttle logic need to be configured in scan_mode¦mbist_mode. | VSI |  |  | to be verified
reset control for at speed test |  Separated reset IOs are required for PLL reset and clock gen reset. | VSI |  |  | to be verified
test case to verify at speed clock | artosyn to provide | artosyn |  |  | open
chain exclude list | 4 clock divider instances name which complements the ABB for PLL function, VSI will exclude them from scan chain. | artosyn |  |  | close
chain exclude list | Provide the list of block level(ca7,ceva) clock dividers’ registers. VSI will exclude them from scan chain. | artosyn |  |  | open
scan reset mux | Provide instance name list of scan reset mux for function logic (non-clock-gen, both block and top level) added by Artosyn. VSI will disconnect from original net then connect to DFT pin mux. | artosyn |  |  | open
explore the way to screen MBIST fail by block | dedicated fail obs pin for each block | VSI | 2017-05-03 |  | close
| to provide the block list | artosyn | 2017-05-03 |  | close
Issues: SDC by block | Action Items | owner | open date | close date | status
flatten clock structure diagram | artosyn to update display clock , add buffer name | artosyn |  |  | to be verified
block clock structure diagram | provide block clock diagram | artosyn |  |  | open
flatten SDC | full chip flatten/ca7 flatten/ceva flatten SDC are not available | artosyn |  |  | open
top only SDC | Artosyn to modify remaining issues | VSI |  |  | open
block SDC: ceva core |  |  |  |  | to be verified
block SDC: ceva harnden | VSI to check timing with ETM | VSI |  |  | to be verified
block SDC: ceva subsys only | VSI to check timing with ETM | VSI |  |  | to be verified
block SDC: ceva subsys flatten | Artosyn to provide sdc | artosyn |  |  | open
block SDC: ca7 core |  |  |  |  | to be verified
block SDC: ca7 harnden | VSI to add clock definition for MBIST LV WTAP logic; VSI to check timing with ETM | VSI |  |  | to be verified
block SDC: ca7 subsys | VSI to check timing with ETM | VSI |  |  | to be verified
block SDC: ca7 subsys flatten | Artosyn to provide sdc | artosyn |  |  | open
block SDC: ISP | partial input delay | artosyn |  |  | to be verified
block SDC: DDR | ilegal endpoint to PHY macro; ddr reset timing ; max delay to qmode; | artosyn |  |  | to be verified
block SDC: HEVC |  | artosyn |  |  | to be verified
block SDC: BB | add clock for registers | artosyn |  |  | to be verified
block SDC: sub1 | VSI to link 3 tcl files to check | VSI |  |  | to be verified
block SDC: sub2 |  add input delay on AXI rid ports.  clock gating hold violation. | artosyn |  |  | to be verified
block SDC: sub3 |  avoid illegal startpoint/endpoints  avoid case analysis on hierarchical pins  big hold violation | artosyn |  |  | to be verified
block SDC: sub4 | illegal points change to "through"; trng reg and div reg define clock ; OTP constraint hold violation | artosyn |  |  | to be verified
Issues: SDC general | Action Items | owner | open date | close date | status
generated clock define stype | o For generated clock , need to define source on it's upstream generated clock. o For generated clock, need define on divider output . o For generated clock, need define on mux output . | artosyn/VSI |  |  | to be verified
don’t touch cell list | Artosyn to provide if have (delay chain, CDM buffer ,eg.) | artosyn |  |  | open
delay chain instance list | DVP/Trng list-sub4 | artosyn |  |  | to be verified
don’t use cell list | artosyn to double check TIE cell ; artosyn to provide list to VSI | artosyn |  |  | open
any special clock gating check (special clock divider logic ) | Artosyn confirm no. | artosyn |  |  | close
prelayout timing clean with reasonable setup margin uncertainty and OCV in WCL corner | VSI check | VSI |  |  | to be verified
check warnings/errors of read_sdc log in PT | Artosyn to check | artosyn |  |  | to be verified
check SDC santity by using "check_timing" in PT | Artosyn to check | artosyn |  |  | to be verified
unreasonable clock defined on internal pin/hierarchical pin | Artosyn to check | artosyn |  |  | to be verified
IO timing constraint are included in SDC | Artosyn to check(DVP, RGMI,EMMC, SD, QSPI,SPI) | artosyn |  |  | to be verified
input/output delay for partition input/output port | Artosyn to check | artosyn |  |  | to be verified
define async for async clock groups | Artosyn to check | artosyn/VSI |  |  | to be verified
Artosyn to check reset path are well constrained. | Artosyn to check | artosyn |  |  | open
define sdc mode for mipi phy | to check | artosyn |  |  | open
check false path between async clocks | to check | artosyn |  |  | open
Issues: low power | Action Items | owner | open date | close date | status
power state table | Artosyn to provide | artosyn |  |  | open
UPF | UPF should be provided for below blocks: ca7 core, ca7 harden, ca7 subsystem, ca7 subsystem flatten, ceva core, ceva harden, ceva subsystem, ceva subsystem flatten, HEVC , ISP, top-only, full_chip_flatten | artosyn |  |  | open
hard macro in OD block need level shifter or not | Artosyn to check | artosyn |  |  | open
hard macro need level shifter nor NOT | Artosyn to check | artosyn |  |  | open
add isolation/lvl/ret cells in synthesis netlist | Artosyn to check | artosyn |  |  | open
select suitable isolations/lvl/ret cells (source/destination) | Artosyn to check | artosyn |  |  | open
power switch control port available at partition | Artosyn to check | artosyn |  |  | open
select suitable power switch cells to define the PMU control signal | Artosyn to check | artosyn |  |  | open
define power switch rule in UPF | Artosyn to check | artosyn |  |  | open
Issues: Floorplan guideline | Action Items | owner | open date | close date | status
avoid partitions with too much pin | Artosyn to check ceva harden pins (~20K) | artosyn |  |  | close
IO controller instance list | emmc: sirius_sub_top_inst/emmc_ctrl_inst rgmii: sirius_sub_top_inst/gbeth_top_inst sd : sirius_sub_top_inst/m7_peripheral_inst/u_sd_card_ctrl spi_mst: sirius_sub_top_inst/m7_peripheral_inst/u_spi_mst_grp spi_slv: sirius_sub_top_inst/m7_peripheral_inst/u_spi_slv_grp | VSI |  |  | to be verified
Issues: Pin Assignments | Action Items | owner | open date | close date | status
pin assignment file | Artosyn to update | artosyn |  |  | open
PHY mirror check | Artosyn to check with PCB | artosyn |  |  | open
move TYPEC PHY from left to right for memory placement | VSI to update pin assignment | VSI |  |  | open
SiP requirements | Artosyn to decide | artosyn |  |  | open
add package ball name | Artosyn to provide | artosyn |  |  | open
mark tie ground bump in pin assignment | Artosyn to provide | artosyn |  |  | open
Issues: ESD | Action Items | owner | open date | close date | status
CDM buffer requirement for PHY | Artosyn to provide requirement | Artosyn |  |  | open
CDM buffer requiement for analog IP | Artosyn to provide requirement | Artosyn |  |  | open
merge CLAMP with BUFFER to a "CDM" buffer (provide LEF/LIB) |  | Artosyn |  |  | open
instantiate CDM buffer in netlist for PHY input and output with different instance names |  | VSI |  |  | open
add diode between hard macro vss and digital core vss | Artosyn to provide requirement | Artosyn |  |  | open
clamp cell requirement | Artosyn to provide requirement | Artosyn |  |  | open
speical ESD requirement |  | Artosyn |  |  | open
Issues: Power Estimation/IR drop/EM | Action Items | owner | open date | close date | status
estimated power consumption | Artosyn to check IP power consumption or toggle rate VCD | Artosyn |  |  | open
IR drop signoff creteria | Y | Artosyn |  |  | open
EM signoff creteria | Y | Artosyn |  |  | open
Issues: ROM code files | Action Items | owner | open date | close date | status
update ROM code files and gds/cdl before tapeout | Artosyn to provide after finalize | Artosyn |  |  | open
Issues: Special physical requirement | Action Items | owner | open date | close date | status
OTP/efuse bonding pad/CP test requirement | Artosyn to check | Artosyn |  |  | close
speical IO balance check requirement | Artosyn to check | Artosyn |  |  | open
place PLL in digital core region | Artosyn to decide | Artosyn |  |  | close
use beachfrount DDR IO | Artosyn to check with SNPS about decap cell rows number and ESD penalty | Artosyn |  |  | close
puts high speed PLL close to sink registers | Y | Artosyn |  |  | close
power/ground routing guideline of analog IP | to check | VSI |  |  | to be verified
signal routing guideline of analog IP | to check | VSI |  |  | to be verified
placement guideline of analog IP | OSC_PVT/TS placement requirement, VSI to place TS/PVT aroung HEVC/ISP | VSI |  |  | to be verified
any signal pin of hard macro pin need level shift |  | Artosyn |  |  | open
any don’t touch requirement of net connected to hard macro |  | Artosyn |  |  | open
check floating input/inout pin of analog IP |  | Artosyn |  |  | open
Issues: Misc. | Action Items | owner | open date | close date | status
spare cell requirements | 1. for ISP/BB inhouse design, place ECO cell , before pnr. 2. for CA7/CEVA harden core, not ECO cell. 3. for other blocks, after pnr place ECO cell at spare place. | Artosyn |  |  | open
library cell naming style | Arotsyn to get updated one to match current library | Artosyn |  |  | close
customer in-house Analog IP physical implementation guideline | PLL/ABB/OSC_PVT/TS guide | Artosyn |  |  | close
third-party Analog IP physical implementation guideline | OTP guide | Artosyn |  |  | close
Any virtual connect setting for merged IP LVS |  | Artosyn |  |  | open
dummy PO/OD/metal/via owner for merged IP |  | Artosyn |  |  | open
LVT pct requirements | C35 lvt open to us, as less as possible, VSI to check pre-layout pct | VSI |  |  | open