## user case
no | user demo case name | input source | output source | data path | Performance | request block | status
1 | Data transfer from HDMI RX to DVP out | 1080p@60fps 8bit | 1080p@60fps 8bit | HDMI Input-> HDMI RX -> Encoder(HEVC) -> BB TX ----> BB RX --> Decoder(HEVC) --> DE -->DVP 16bit output @148.5Mhz | total delay < 30ms | HDMI_RX/VIF/DDR/CA7/BB/HEVC/DE/DVP Out
2 | Data transfer from MIPI sensor to DVP out | 1080p@60fps 8bit | 1080p@60fps 8bit | Sensor Input-> MIPI RX -> ISP -> DE -->DVP 16bit output @148.5Mhz |  | MIPI_RX/VIF/DDR/ISP/CA7/DE/DVP Out

## PCB resource
1(socket)
1(soldered)
No | Board | Qty | Team | Support Engineer |  |  | Task | status
|  |  |  | SE | Chip | SW
| 1(socket) | 1 | Analog | Jujiangjun | Yuanyuan | Liujing | ABB block/DDR PLL/CA7 PLL/CEVA PLL/PVT/TS test, further BB usage test
| 1(socket) | 1 | BB | Jujiangjun | Lizheng | Liujing | Baseband block test
| 1(socket) | 1 | SOC | Jujiangjun | SongPan | Liujing | CA7 ROM boot directly from QSPI+SRAM+UART0/Driver test
| 1(socket) | 1 | Vision | Jujiangjun | Shashen | Liujing | CEVA function test
| 1(socket) | 1 | Vision | Jujiangjun | Wanghua/Liujialiang | Liujing | ISP/Codec/Display multi-media test
| 1(soldered) | 15 |  |  |  |  | pending usage
| Total | 20
Note on B7: 1(socket): the task need to use socket board; 1: the task need use soldered board; 1(socket) or 1: either socket or solder board is OK.

## DAY0
No. | board | Qty | Team | Support Engineer |  |  | Task | Deliverable | status
|  |  |  | SE | Chip | SW
1 | socket board | 5 | SE | Ju Jianjun |  |  | PCB check, power supply/power sequence, w/o chip | mother board/daughter board/sensor board/socket | ??
|  |  |  | Ju Jianjun |  |  | HDMI input source/HDMI output sink check |  | ??
|  |  |  | Ju Jianjun |  |  | High speed analyzer check | HDMI/DDR test fixture | ??
|  |  |  | Ju Jianjun |  |  | Bring up power supply/ working desk check | new lab space | ??
2 |  |  | SW |  | Songpan | Liujing | Tool check | QSPI flash Program tool | ??
[5 empty] | Songpan | Liujing |  | SPI debug tool | ??
[5 empty] | Songpan | Liujing |  | Jlink/DS5 | ??
[5 empty] | SongPan | Liujing |  | DDR tuning tool check | ??
[5 empty] | Shensha | Liujing |  | ISP tuning tool check | ??
3 |  |  | SW |  | SongPan | Liujing | boot Image check | QSPI Nor flash boot image | ??
4 |  |  | Analog |  | Yuanyuan |  | Clock check | PLL setting, validation plan document | ??
5 |  |  | BB |  | Lizheng | Liujing | baseband TX/RX function check | firmware ,validation plan document | ??
6 |  |  | Video |  | Jialiang | Liujing | HEVC codec/Display function check | firmware ,validation plan document | ??
7 |  |  | SOC |  | Huibo | Liujing | HDMI RX /DVP out/VIF function check | firmware ,validation plan document | ??

## DAY1
1(socket)
1(soldered)
Day x
| Board | Qty | Team | Support Engineer |  |  | Task | Deliverable
|  |  |  | SE | Chip | SW
| 1(socket) | 1 | Analog |  | Yuanyuan |  | ABB block/DDR PLL/CA7 PLL/CEVA PLL/PVT/TS test
| 1(socket) | 1 | BB |  | Lizheng |  | Baseband block test
| 1(socket) | 1 | SOC |  | SongPan |  | CA7 ROM boot directly from QSPI+SRAM+UART0
| 1(socket) | 1 | Vision |  | Shashen |  | CEVA function test
| 1(socket) | 1 | Vision |  | Wanghua/Liujialiang |  | ISP/Codec/Display
| Total | 5
Note on B9: 1(socket): the task need to use socket board; 1: the task need use soldered board; 1(socket) or 1: either socket or solder board is OK.