## validation block list
no | validation block name | status
1 | CGU/RGU/PLL output | done
2 | SPI debug interface | done
3 | DS5 JTAG interface/Coresight | done
4 | DDR | done
5 | QSPI flash | done
6 | DMA controller x3 | done
7 | NOC | done
8 | On Chip SRAM | done
9 | CA7 x4 CPU | done
10 | CEVA DSP | done
11 | M7 CPU | done
12 | TYPEC/DP/USB | done
13 | HDMI RX | done
14 | MIPI x8 | done
15 | DVP interface | done
16 | I2S | done
17 | DISPLAY | done
18 | H264 | done
19 | HEVC | done
20 | JPEG | done
21 | ISP | done
22 | USB30 | done
23 | PCIe | done
24 | GMAC | done
25 | eMMC | done
26 | SD controller | done
27 | slow speed perip (GPIO/PWM/I2C/UART/CAN/WDT/Timer/SPIM/SPIS) | done
28 | ADC/DAC/TS/PVT sensor | done
29 | Baseband | done
30 | Secure ROM/tRoot/TRNG/SPAcc | done
31 | OTP | done
32 | SMMU x2 | done
33 | MIPI TX | done
34 | TZC | done

## HDMI
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
HDMI | function validation | register default value check and read/write | PASS/ Fail
video interface timing test (for different vidoe resolution)
audio interface timing test (for different audio format)
EDID read
HPD toggle
HDMI Audio Sample Subpacket test
HDMI Audio Clock Regeneration (audio pll)
HDMI GCP packet test
HDMI interrupt test
HDCP DDC channel test
HDCP An test
HDCP Km test
HDCP R0、M0 test
HDCP V match test
HDCP interrupt test
HDCP OESS encrypt test
HDCP EESS encrypt test
CEC Tx function test
CEC Tx Reset test
CEC Rx function test
CEC Rx Reset test
Channel Invert test
Bist test
| performance validation | HDMI electrical test
| compliance validation | CEC test
HDCP test
HDMI input compliance test

## TypeC
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
TypeC | function validation | UDF register default value check and read/write
DP register default value check and read/write
USB register default value check and read/write
TCPC register default value check and read/write
Write FW to Xtensa by Host, test basic function of FW
Confirm the PD message trans path
Test the flip connection feature
Let TypeC work in USB mode
Let TypeC work in DP mode
Let TypeC work in Concurrent mode
In DP mode, do Link training in RBR/HBR/HBR2 mode with 1 lane/2 lanes/4 lanes
In DP Alt mode, video interface timing test(for different video resolution)
In DP Alt mode, I2S interface timing test(for different audio configuration)
In DP Alt mode, HDCPv1.3 authentication and send encrypted frames
In DP Alt mode, HDCPv2.2 authentication and send encrypted frames
In USB Host mode, do USB3 initialization sequence followed by Bulk transfer
In USB Device mode, do USB3 initialization sequence followed by Bulk transfer
| performance validation | In DP Alt mode, send 4k resolution frames in HBR2 4 lane
In USB mode, test the bandwidth

## CA7
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
CA7 CPU | function validation | ARM core mode switch test | pass/ fail
4x ARM CPU core runing test
cpu 1/2/3 reset test
CPU /L1 /L2 Cache bist test
4x CPU peformance monitor test
4x CPU peformance monitor interrupt test
L2 Cache tag/data RAM latency test
L2C/GIC register test
CP14/CP15 cop test
L1, L2 Cache and MMU test
private timer/global timer interrupt test
4 x SGI interrtup test
cpu0 wake up cpu1/2/3 test
GIC：allocate interrput ID to 4x cpu test
cpu boot up test
Verify boot remap with BOOT_SPI_EN and OTP_SPI_BOOT_DISABLE
Use sec_subsys_reg[0] to control the accessibility of a7 secure system control register
Use sec_subsys_reg[1] to control CFGSDISABLE to control the accessibility of secure registers of GIC
Use debug spi to access global register of A7
Use coresight to discover, trace and debug A7
Verify throttle function of A7
Verify tst clock of a7 pll.
Verify a7 pll clock frequency adjustment
Verify global register function of a7.
Verify FPU and NEON.
Verify using global register to control AxQOS
| performance validation | 4x CPU DVFS test, max frequency
| stable validation | over night CPU running test

## DDR
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
DDR | function validation | DDRC register access
PHY PUB register access
DDR TOP register access
PHY initialization
SDRAM initialization
DDR4-1600 W/R
LPDDR3-1333 W/R
DDR3-1333 W/R
Full memory space access
Self refresh
Deep Power-down mode
Maximum Power Saving mode
SDRAM mode register access
Frequency change
Half bus mode
Quarter bus mode
Inline ECC
2T Memory Command Timing
DLL off mode
Write Mask
Read DBI
Write DBI
HPR access
LPR access
VPR access
NPW access
VPW access
Qos
Axi Monitor
SSC
PHY WL
PHY Read DQS Gate
PHY WLADJ
PHY Write Deskew
PHY Read Deskew
PHY Write Eye Training
PHY Read Eye Training
LPDDR3 AC Training
| performance validation | DDR4 clock range
DDR3 clock range
LPDDR3 clock range
Six Maters Access
Random Access
Stability Test
| physical validation | Power
ODT Value
Eye Diagram

## BB
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
Baseband | function validation | Debug SPI R/W
BR/CSMA TX spectrum
|  | BR/CSMA RX correct |  | BR TX on fpga
slot TX spectrum
tlv built-in test correct
|  | slot RX correct |  | Slot TX on fpga
2.4G/5.8G test
|  | Known pattern test on slot |  | both end on chip
|  | bb mode A test |  | both end on chip
|  | bb mode B test |  | both end on chip
|  | bb mode C test |  | both end on chip
|  | bb mode D test |  | both end on chip
slot 1T1R/1T2R/2T2R/2T4R
| Performance | BR/CSMA RX on BW(1.25~20M)/repeat(1/2/4)/MCS |  | SNR, sensitivity
|  | slot RX on BW(2.5~40M)/repeat(1/2/4/8)/MCS/tlv(12/24/48) |  | SNR, sensitivity
|  | packet detection |  | false alarm/miss detection rate
|  | Bra-A~E test |  | SNR
frequency offset range test
doppler test
ldpc 300M
distance measurement
frequency hop
burst noise
harq
MRC

## MIPIx8
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
MIPI | function validation | register default value check and read/write | PASS/ Fail
Patten_gen mode test (raw8, 1280x720@30fps)
IDI interface test(raw8, 1280x720@30fps)
IPI interface test(raw8, 1280x720@30fps)
Two_lane mode test (raw8, 1280x720@30fps)
four_lane mode test (raw8, 1280x720@30fps)
Hsync generate test (raw8, 1280x720@30fps)
video Interface Timing test: raw8, 1280x720@30fps
video Interface Timing test: raw8, 1920x1080@30fps
video Interface Timing test: raw8, 3840x2160@30fps
video Interface timing test: raw10, 1920x1080@30fps
video Interface timing test: raw12, 1920x1080@30fps
video Interface timing test: raw14, 1920x1080@30fps
video Interface timing test: yuv422_8bit, 1920x1080@30fps
video Interface timing test: yuv422_10bit, 1920x1080@30fps
video Interface Timing test: raw8, 1920x1080@30fps, SBS mode
video Interface Timing test: yuv422_8, 1920x1080@30fps, SBS mode
Inter Bist test
| performance validation | MIPI electrical test

## Codec_Display
block name | validation check list and status |  |  |  |  | issue list | finish percentage
| validattion type | validate item | Dependency | status | comment
HEVC | function validation | HEVC IP version read 0x00000000 when power down, after power on , read 0x | CGU/RGU ready
|  | CPU write one 8bit image, HEVC encoding, CPU read bitstream @ Cclk 450MHz, bclk: 300, comparing golden | CGU/RGU ready
|  | CPU write one 8bit image, HEVC encoding, CPU read bitstream @ 500MHz, bclk: 400, comparing golden | CGU/RGU ready
|  | CPU write bitstream, HEVC decoding, CPU read rec frame @450MHz, comparing golden | CGU/RGU ready
|  | HEVC Encoding + ISP Low-delay, can be decoding | ISP ready
|  | HEVC Encoding + VIF low-delay, can be decoding | VIF ready
| performance validation | HEVC 4K@30fps @ 450fps
HEVC 4K@30fps + H264@30fps @ 500Mhz
compliance validation
H264 | function validation | Read H264 IP version, can read 0x434f4441 | CGU/RGU ready
|  | CPU write one 8bit image, H264 encoding, CPU read bitstream @ cclk400 MHz, comparing golden | CGU/RGU ready
|  | CPU write bitstream, H264 decoding, CPU read rec frame @400MHz, comparing golden | CGU/RGU ready
|  | H264 Encoding + ISP Low-delay, can be decoding | ISP ready
|  | H264 Encoding + VIF low-delay, can be decoding | VIF ready
| performance validation | 1080P@60fps @ 400MHz
2x 720P@60fps @ 400MHz
compliance validation
JPEG | function validation | CPU write one 8bit image, JPEG encoding, CPU read bitstream @ cclk450 MHz, comparing golden | CGU/RGU ready
|  | CPU write bitstream, Jpeg decoding, CPU read rec frame @450MHz, comparing golden | CGU/RGU ready
| performance validation | 32Kx32K Max resoltuion encoding
compliance validation
Display | function validation | Display single color @ 480p @60fps | CGU/RGU/ DVP ready
|  | Display DDR data @ 480p @ 60fps | CGU/RGU/ DVP ready
|  | Display Scaling data @ 480p@60fps | CGU/RGU/ DVP ready
|  | Display one videolayer + one video layer @ 480p @ 60fps | CGU/RGU/ DVP ready
| performance validation | Display 4K@30fps | CGU/RGU/DP ready
|  | Display 1080P@60fps | CGU/RGU/DVP ready
compliance validation
System | function validation | ISP(4K@30fps) -> HEVC encoding -> SD card | CGU/RGU/ ISP/SD card ready
|  | ISP(1080P@30fps) -> H264 encoding -> SD card | CGU/RGU/ ISP / SD ready
|  | ISP(1080P@30fps) -> H264 encoding -> BB->BB -> dec -> Display | CGU/RGU/ ISP/ H264/BB/display ready
CGU/RGU/ DVP ready
performance validation
compliance validation

## NOC_OTP
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
NOC | function validation | read and write NOC register
write ta20's rigister, enable the secure on-chip sram main can be accessed by unsecure mode
A7 access all device's register
CS access OTP's register
SPI Debug access OTP's register
M7 access DDR
Baseband access DDR
DMA main access DDR
eMMC access DDR
SPAcc access DDR
tRoot access DDR
USB3.0 access DDR
Type-c access DDR
PCI-e access DDR
GMAC access DDR
CEVA access DDR
DMA_ceva access DDR
HEVC access DDR
H264 access DDR
JPEG access DDR
Video Interface access DDR
Display Control access DDR
| performance validation | NOC's clock switch to 600MHz and 400MHz
OTP | function validation | read and write OTP register
program password's 32bits to XPM
read password's 32bits from XPM

## M7_SUB
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status (pass/fail) | comment
M7 CPU | function validation | ARM core mode switch test
ARM CPU core runing test
CPU software reset control test
CPU wait control test
CPU initial vector table switch test
CPU boot up test
CPU operation clock frequency switch test (PLL & clk throttle)
ITCM/DTCM access test
Interrupt ID test
FPU test (single & double)
| performance validation | CPU max operation frequency
| stable validation | Over night CPU running test
QSPI | function validation | Flash Erase/Write/Read test
Clock frequency switch test
Operation mode swith test (single / quad / qpi)
Address mode swith test (3BAM / 4BAM)
Different type of flash test (Winbond / Spasion / Micron)
| performance validation | QSPI controller max operation frequency
| stable validation | Multi-times erase/write/read test
CoreSight | function validation | Auto detect test
Debug A7 (single / quad core) test
Debug M7 test
A7 / M7 trace test
| performance validation | Max operation frequency (JTAG clk)
| stable validation | Multi-times trace/debug begin/stop, hot-plug
Low-Speed Peripheral
Uart | function validation | Uart 0~8 tx/rx function test
Uart 1~4 dma feature test
Uart pin share test
| performance validation | Uart max baud rate
Max transmission efficiency with dma
| stable validation | Over night transfer
SPI Master | function validation | SPI master 0~3 tx/rx function test
SPI master 0~3 dma feature test
SPI Master pin share test
| performance validation | SPI master max operation frequency
Max transmission efficiency with dma
| stable validation | Over night running
SPI Slave | function validation | SPI slave 0~1 tx/rx function test
SPI slave 0~1 dma feature test
SPI slave pin share test
| performance validation | SPI slave max operation frequency
Max transmission efficiency with dma
| stable validation | Over night running
CAN | function validation | CAN 0~3 tx/rx function test
CAN buad rate switch test
CAN pin share test
| performance validation | Max buad rate
| stable validation | Over night running
I2C | function validation | I2C as master tx/rx function test
I2C as slave tx/rx function test
I2C dma feature test
I2C pin share test
| performance validation | Max transmission efficiency with dma
| stable validation | Over night running
GPIO | function validation | GPIO software control as input / output
GPIO input counter test
GPIO interrupt function test
GPIO pin share test
| performance validation | Max toggle rate controlled by software
| stable validation | N/A
PWM | function validation | PWM signal generate test
Timer function test
PWM pin share test
| performance validation | Max toggle rate
| stable validation | N/A
WDT | function validation | Watch Dog function test
Watch Dog generate soc reset signal test
Watch Dog pin share test
| performance validation | N/A
| stable validation | N/A
DMA_AHB | function validation | DMA transfer function test
DMA handshake interface test with peripheral
| performance validation | Max transmission efficiency with dma
| stable validation | Over night transfering

## CEVA
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
CEVA DSP | function validation | APB register access test | pass/ fail
Core0/1/2/3 soft reset test
Core0/1/2/3 running test
Power on/off test
IOP port test
EDP port test
EPP port test
EDAP port test
Clock frequency switch test (PLL & clk throttle)
TCM and cache bist test
Program cache test
Timer interrupt test
CPU operation clock frequency switch test (PLL & clk throttle)
MCCI test
communication with ARM test
JTAG test (Jbox)
| performance validation | 4x DSP DVFS test, max frequency
| stable validation | over night DSP running test

## GMAC_I2S_DMAC_SRAM_SD_EMMC
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status (pass/fail) | comment
EMMC | function validation | Register write/read test
Clock divider test
Clock frequency switch test
Initialization process test
Delay chain test
PIO write/read test
SDMA write/read test
AMDA write/read test
ADMA2 write/read test
Voltage switch(3.0V/1.8V) test
Interrupt test
| performance validation | SDR 200MHz write/read
| stable validation | Multi-times erase/write/read test
SD | function validation | Register write/read test
Clock frequency switch test
Initialization process test
Delay chain test
Data write/read through cpu test
Data write/read through dma test
Voltage switch(3.0V/1.8V) test
Interrupt test
Different type of sd card test
| performance validation | SDR 200MHz write/read
| stable validation | Multi-times erase/write/read test
Ethernet | function validation | Register write/read test
Mdio interface test
Mac internal loop back test
Mac and phy loop back test
Simple tx and rx data transmit with single bd test
10M/100M/1000M tx and rx data transmit test
CSMA/CD protocol test
Interrupt test
| performance validation | 1000M MAC data write and read speed test
| stable validation | Long time ping test
I2S | function validation | Register write/read test
I2S TX with N(1/2/4) wire mode with cpu
I2S RX with N(1/2/4) wire mode with cpu
I2S TX with N(1/2/4) wire mode with ahb_dma
I2S RX with N(1/2/4) wire mode with ahb_dma
I2S master and slave mux with different mode
| performance validation | Max transmission efficiency with dma
| stable validation | Over night transfer
DMAC | function validation | Register write/read test
Single-Block transfer test
Linked-List-Based multi-block transfer test
| performance validation | Max transmission efficiency between ddr and sram
| stable validation | Over night running
SRAM_TOP | function validation | Dmac transfer with different sram_top address
| performance validation | Max transmission efficiency from ddr to sram
| stable validation | Over night transfering

## Secure
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status (pass/fail) | comment
TZC | function validation | Register access
Configure DDR space to secure/non-secure access
Secure/non-secure space overlap
Access DDR from filter 0~5
| performance validation | Max latency
| stable validation | N/A
tRoot | function validation | read/verify secure boot firmware
read/verify system boot image
interrupt test
| performance validation | secure boot flow
compliance validation
SPACC | function validation | AES-CBC 128bit/256bit encrypt&decrypt
AES-CBC 128bit/256bit encrypt&decrypt with root key
spacc axcache[1] controlled by a secure register, and dma access can be modified by NOC
SHA256 test
dma ddt read/write data
interrupt test
| performance validation | continue encrypt/decrypt
secure boot flow
| compliance validation | use PC software aes cbc encrypt and use spacc decrypt data
PKA | function validation | 2048bit CALC_R_INV
2048bit CALC_MP
2048bit CALC_R_SQR
RSA 2048bit MODEXP
RSA 2048bit encrypt and decrypt
256bit ECC point verification
256bit ECC point multiplication
256bit ECC encryption& decryption with key pair
interrupt test
| performance validation | secure boot flow
| compliance validation | use PC software RSA 2048bit encrypt and use spacc decrypt data
use PC software ECC 256bit encrypt and use spacc decrypt data
TRNG | function validation | ATE mode test ring oscillator
do random reseed and get random number
interrupt test
performance validation
compliance validation
secure uart | function validation | Uart tx/rx function test
Uart pin share test
interrupt test
| performance validation | Uart max baud rate
| stable validation | Over night transfer
secure timer | function validation | Timer function test
interrupt test
performance validation
compliance validation
secure watch dog | function validation | Watch Dog pin share test
Watch Dog function test
Watch Dog generate soc reset signal test
interrupt test
performance validation
compliance validation

## MIPI_TX
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
mipitx | function validation | register default value check and read/write | PASS/ Fail
two mipi txpll lock test
mipi tx 1 lane at different rate
mipi tx 2 lane at different rate
mipi tx 3 lane at different rate
mipi tx 4 lane at different rate
mipitx interrupt
| performance validation | 2 lane @ 1.5G bps
4 lane @ 1.5G bps

## DVP
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
DVP | function validation | register default value check and read/write | PASS/ Fail
dvp rx clock delay chain setting
1view dvp input 16bit sdr test (BT601)
1view dvp input 8bit sdr test (BT601)
1view dvp input 8bit ddr test (BT601)
1view dvp input 16bit sdr test (BT656)
1view dvp input 8bit sdr test (BT656)
1view dvp input 8bit ddr test (BT656)
dvp video data to ddr data path
dvp tx clock delay chain setting
1view dvp output 16bit sdr test (BT601)
1view dvp output 8bit ddr test (BT601)
1view dvp output 16bit sdr test (BT656/1120)
1view dvp output 8bit ddr test (BT656/1120)
| performance validation | 1080p @60fps dvp input test
1080p @60fps dvp output test

## USB
Block Name | Validation checklist and status |  |  |  | issue list | finish percentage
USB | validation type | validate item | status | comment
| Function Test | USB pinshare test
register read/write test
USB2.0 host enumeration(HS/FS/LS)
USB2.0 host bulk transfer(HS/FS/LS)
USB2.0 host iso transfer(HS/FS/LS)
USB2.0 host int transfer(HS/FS/LS)
USB2.0 host control transfer(HS/FS/LS)
USB2.0 host no op transfer(HS/FS/LS)
USB2.0 suspend and resume
USB2.0 device enumeration(HS/FS)
USB2.0 device bulk transfer(HS/FS)
USB2.0 device iso transfer(HS/FS)
USB2.0 device int transfer(HS/FS)
USB2.0 device control transfer(HS/FS)
USB2.0 device no op transfer(HS/FS)
USB3.0 link training
USB3.0 link command
USB3.0 host enumeration(SS)
USB3.0 host bulk transfer(SS)
USB3.0 host iso transfer(SS)
USB3.0 host int transfer(SS)
USB3.0 host control transfer(SS)
USB3.0 host no op transfer(SS)
USB3.0 suspend and resume
USB3.0 device enumeration(SS)
USB3.0 device bulk transfer(SS)
USB3.0 device iso transfer(SS)
USB3.0 device int transfer(SS)
USB3.0 device control transfer(SS)
USB3.0 device no op transfer(SS)
interrupt test
multi-endpoint concurrent transfer test
non-aligned address test
cross 4k address transfer test
| Performance Test | single endpoint performance test
multi-endpoint concurrent performance test
axi master bus burst performance test
tx FIFO burst performance test
| Stability Test | continue read/write test
hot plug test
| Compatibility Test | Phy/Controller reset test
DP/DM pullup/pulldown test
usb2.0 phy bist test
usb3.0 phy loopback test
super speed electrical test
high speed electrical test
| Power Test | high speed power test
super speed power test

## CGU RGU PLL output
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
CGU RGU PLL output | function validation | config pin_share to monitor out for abb/clk/rst
CGU register default value check and read/write
RGU register default value check and read/write
ABB register default value check and read/write
clock frequency select from ABB

## SPI debug
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
SPI debug interface | function validation | SPI DBG for memory space
| performance validation | max sclk frequency test
| stable validation | long time memory space access test

## PCIe
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
PCIe | function validation | (RC/EP) Monitor out to PAD
(RC/EP) CLK frequency/RSTN check
(RC/EP) register default value check and read/write
(RC/EP) Link up interrupt check
(RC/EP) device id and vendor id access
(RC/EP) msix transaction test
(RC/EP) atu feature test
(RC/EP) atu bypass feature test
(RC/EP) dma ll feature test
(RC/EP) dma non ll feature test
(RC/EP) physical layer reset test
(RC/EP) link speeds test
(RC/EP) hot reset test
(RC/EP) link disable state test
(RC/EP) DDR access through remote pcie
(RC/EP) DMAC access axi slv
(RC/EP) Hot-Plug behavior
| performance validation | (RC/EP) TOP DMAC and PCIE edma
| physical validation | Eye Diagram

## SMMU
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
SMMU_DSP | function validation | Access registers of SMMU_DSP. | pass/ fail
Verify bypass mode of SMMU_DSP.
Verify one stage of translation.
Verify two stage of translation.
Verify interrupt of SMMU_DSP.
Verify large address access.
| performance validation | Verify the max bandwidth of SMMU_DSP
| stable validation | over night SMMU_DSP running test
SMMU_VIDEO | function validation | Access registers of SMMU_VIDEO. | pass/ fail
Verify bypass mode of SMMU_VIDEO.
Verify one stage of translation.
Verify two stage of translation.
Verify interrupt of SMMU_VIDEO.
Verify large address access.
| performance validation | Verify the max bandwidth of SMMU_VIDEO
| stable validation | over night SMMU_VIDEO running test

## ISP
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
ISP | function validation | Register Access
ISP Interrupt
|  | VIF Line Buffer Input ( 4K/1080P/720P) |  | video
|  | VIF Line Buffer Input, 2 View(1080P@30*2) |  | video
|  | VIF Line Buffer Input ,4K + 3 resolution Output |  | video
|  | DDR Input (4K/1080P/720P) |  | video
|  | DDR Input ,multi view input : 4K + 720P*2 |  | video
|  | DDR Input Super Size Picutre Mode ( Half View Mode) |  | picture
Test Pattern Mode
ISP Clock Switch
ISP Low Power ON/OFF switch
| Performance | 1080P30fps*8

## ABB_PLL
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
ABB | DC test | bandgap voltage |  | VBG=1.25V
|  | bandgap current |  | PMU_IOUT=40uA
|  | AVDDL_LDO VOLTAGE |  | AVDDL_LDO=0.9V
|  | OSC_LDO VOLTAGE |  | OSC_LDO=1.3V
|  | DACA LOCAL BIAS CURRENT |  | DAC_LOCAL_BIAS_A=10uA
|  | DACB LOCAL BIAS CURRENT |  | DAC_LOCAL_BIAS_B=10uA
|  | ADCA REFP VOLTAGE |  | ADC_A_REFP=1.35V
|  | ADCA REF_CM VOLTAGE |  | ADC_A_REF_CM=1.1V
|  | ADCA REFN VOLTAGE |  | ADC_A_REFN=0.85V
|  | ADCB REFP VOLTAGE |  | ADC_B_REFP=1.35V
|  | ADCB REF_CM VOLTAGE |  | ADC_B_REF_CM=1.1V
|  | ADCB REFN VOLTAGE |  | ADC_B_REFN=0.85V
|  | ADCC REFP VOLTAGE |  | ADC_C_REFP=1.35V
|  | ADCC REF_CM VOLTAGE |  | ADC_C_REF_CM=1.1V
|  | ADCC REFN VOLTAGE |  | ADC_C_REFN=0.85V
|  | ADCD REFP VOLTAGE |  | ADC_D_REFP=1.35V
|  | ADCD REF_CM VOLTAGE |  | ADC_D_REF_CM=1.1V
|  | ADCD REFN VOLTAGE |  | ADC_D_REFN=0.85V
|  | DVDD_LDO VOLTAGE |  | DVDD_LDO=0.9V
|  | SAR1 VREF VOLTAGE |  | SAR_VREF_1=1.25V
|  | SAR2 VREF VOLTAGE |  | SAR_VREF_2=1.25V
|  | SAR3 VREF VOLTAGE |  | SAR_VREF_3=1.25V
| PLL frequency test | ADDAPLL |  | 20MHz
|  | DSPPLL0 |  | 15.625MHz
|  | DSPPLL1 |  | 11.71875MHz
|  | DSPPLL2 |  | 4.6875MHz
|  | SDCPLL |  | 12.5MHz
|  | AUPLL |  | 5MHz
|  | PIXPLL |  | 18.5625MHz
| DA-AD loop test | read SNR from register |  | >50dB
| SARADC | force dc voltage at saradc input and read output code
| temperature sensor | read TS sensor output code and compare to simulation result
| PVT sensor | read PVT sensor output code and compare to simulation result
A7PLL | PLL frequency test |  |  | 3.90625MHz
CEVAPLL | PLL frequency test |  |  | 3.90625MHz
DDRPLL | PLL frequency test |  |  | 16.65625MHz