## validation block list
no | validation block name | status
1 | CGU/RGU/PLL output
2 | SPI debug interface
3 | DS5 JTAG interface/Coresight
4 | DDR
5 | QSPI flash
6 | DMA controller x3
7 | NOC
8 | On Chip SRAM
9 | CA7 x4 CPU
10 | CEVA DSP
11 | M7 CPU
12 | TYPEC/DP/USB
13 | HDMI RX
14 | MIPI x8
15 | DVP interface
16 | I2S
17 | DISPLAY
18 | H264
19 | HEVC
20 | JPEG
21 | ISP
22 | USB30
23 | PCIe
24 | GMAC
25 | eMMC
26 | SD controller
27 | slow speed perip (GPIO/PWM/I2C/UART/CAN/WDT/Timer/SPIM/SPIS)
28 | ADC/DAC/TS/PVT sensor
29 | Baseband
30 | Secure ROM/tRoot/TRNG/SPAcc/TZC
31 | OTP
32 | SMMU x2
33 | DMA controller x3
34 | On Chip SRAM

## HDMI validation item
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
HDMI | function validation | register default value check and read/write | PASS/ Fail
不同分辨率Video Interface Timing测试
不同格式下Audio Interface timing测试
HDMI模块版本号读取测试
HPD中断检测
内部SRAM读写测试
HDMI Audio Sample Subpacket设置测试
HDMI Audio Clock Regeneration测试
HDMI GCP测试
Periodic RAM Packet测试
视频数据格式测试
视频数据来源测试
保护带到视频数据期之间等待延迟测试
HDCP An产生方式测试
HDCP Km生成测试
HDCP R0、M0生成方式测试
HDCP Vmatch测试
HDCP Ri、Pj Update中断模式测试
HDCP OESS加密方式测试
HDCP EESS加密方式测试
HDCP DDC通道测试
CEC Tx功能测试
CEC Tx Reset测试
CEC Rx功能测试
CEC Rx Reset测试
Channel Invert功能测试
Audio Channel防错乱测试
Bist模式测试
| performance validation | EDID test |  | protocol analyzer test
HDMI electrical test
| compliance validation | CEC test
HDCP test
HDMI input compliance test

## CA7
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
CA7 CPU | function validation | ARM core mode switch test | pass/ fail
4x ARM CPU core runing test
cpu 1/2/3 reset test
CPU /L1 /L2 Cache bist test
4x CPU peformance monitor test
4x CPU peformance monitor interrupt test
L2 Cache tag/data RAM latency test
L2C/GIC register test
CP14/CP15 cop test
L1, L2 Cache and MMU test
private timer/global timer interrupt test
4 x SGI interrtup test
cpu0 wake up cpu1/2/3 test
GIC：allocate interrput ID to 4x cpu test
cpu boot up test
Verify boot remap with BOOT_SPI_EN and OTP_SPI_BOOT_DISABLE
Use sec_subsys_reg[0] to control the accessibility of a7 secure system control register
Use sec_subsys_reg[1] to control CFGSDISABLE to control the accessibility of secure registers of GIC
Use debug spi to access global register of A7
Use coresight to discover, trace and debug A7
Verify throttle function of A7
Verify tst clock of a7 pll.
Verify a7 pll clock frequency adjustment
Verify global register function of a7.
Verify FPU and NEON.
Verify using global register to control AxQOS
| performance validation | 4x CPU DVFS test, max frequency
| stable validation | over night CPU running test

## DDR
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
DDR （90%） | function validation | Slave port优先级验证 | pass |  |  | 90%
|  | Akeep | pass
|  | Tag FIFO验证 | pass
|  | Command Pause | pass
|  | PM验证 | pass
|  | Reorder 验证 | pass
|  | Inorder 访问 | pass
|  | Monitor | pass
|  | High performance mode | pass
|  | Timeout | pass
|  | VDD OFF | pass
|  | In Cache | pass
|  | DTU验证 | pass
|  | LPDDR2 | pass
|  | DRAM初始化 | pass
|  | Switch state | pass
|  | Timing | pass
|  | UPCTL statue register | pass
|  | HW LOW power down | pass
|  | Software low power down | pass
|  | Partially popular memory | pass
|  | Memory 状态寄存器 | pass
|  | ODT | pass
|  | Mask refresh | pass
|  | DCU验证 | pass
|  | Auto command | pass
|  | Remove clock | pass
|  | 软件reset | pass
|  | DLL 验证 | pass
|  | Data gate training | pass
|  | BIST | pass
|  | DCU(PUBL) | pass
|  | ZQ clk div | pass
|  | PHY状态寄存器 | pass
|  | DQS gate widow大小 调整 | pass
|  | Data slew rate | pass
|  | ITM dQS trim | pass
|  | Slave dll phase select | pass
| performance validation | March C | PASS
|  | DDR3 clock范围 | PASS 性能板使用合适的dfi参数后可以到660MHz，使用DMA 随机数据老化暂无发现错误，EVB板稳定可以跑540M，眼图宽度600ps
|  | Delay chain window | pass
|  | 多master访问 | pass
|  | 随机访问 | pass
|  | 稳定性测试 | pass
| physical validation | 输出阻抗测试 | 待测
|  | ODT | 待测
|  | 功耗测试 | 待测
|  | 电气特殊性 | 粗略看了480MHz读写data和command信号的眼图，眼图质量ok；
|  | DLL测试 | 待测

## MIPIx8
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
MIPI | function validation | register default value check and read/write | PASS/ Fail
Patten_gen mode test (raw8, 1280x720@30fps)
IDI interface test(raw8, 1280x720@30fps)
IPI interface test(raw8, 1280x720@30fps)
Two_lane mode test (raw8, 1280x720@30fps)
four_lane mode test (raw8, 1280x720@30fps)
Hsync generate test (raw8, 1280x720@30fps)
video Interface Timing test: raw8, 1280x720@30fps
video Interface Timing test: raw8, 1920x1080@30fps
video Interface Timing test: raw8, 3840x2160@30fps
video Interface timing test: raw10, 1920x1080@30fps
video Interface timing test: raw12, 1920x1080@30fps
video Interface timing test: raw14, 1920x1080@30fps
video Interface timing test: yuv422_8bit, 1920x1080@30fps
video Interface timing test: yuv422_10bit, 1920x1080@30fps
video Interface Timing test: raw8, 1920x1080@30fps, SBS mode
video Interface Timing test: yuv422_8, 1920x1080@30fps, SBS mode
Inter Bist test
| performance validation | MIPI electrical test

## Codec_Display
block name | validation check list and status |  |  |  |  | issue list | finish percentage
| validattion type | validate item | Dependency | status | comment
HEVC | function validation | HEVC IP version read 0x00000000 when power down, after power on , read 0x | CGU/RGU ready
|  | CPU write one 8bit image, HEVC encoding, CPU read bitstream @ Cclk 450MHz, bclk: 300, comparing golden | CGU/RGU ready
|  | CPU write one 8bit image, HEVC encoding, CPU read bitstream @ 500MHz, bclk: 400, comparing golden | CGU/RGU ready
|  | CPU write bitstream, HEVC decoding, CPU read rec frame @450MHz, comparing golden | CGU/RGU ready
|  | HEVC Encoding + ISP Low-delay, can be decoding | ISP ready
|  | HEVC Encoding + VIF low-delay, can be decoding | VIF ready
| performance validation | HEVC 4K@30fps @ 450fps
HEVC 4K@30fps + H264@30fps @ 500Mhz
compliance validation
H264 | function validation | Read H264 IP version, can read 0x434f4441 | CGU/RGU ready
|  | CPU write one 8bit image, H264 encoding, CPU read bitstream @ cclk400 MHz, comparing golden | CGU/RGU ready
|  | CPU write bitstream, H264 decoding, CPU read rec frame @400MHz, comparing golden | CGU/RGU ready
|  | H264 Encoding + ISP Low-delay, can be decoding | ISP ready
|  | H264 Encoding + VIF low-delay, can be decoding | VIF ready
| performance validation | 1080P@60fps @ 400MHz
2x 720P@60fps @ 400MHz
compliance validation
JPEG | function validation | CPU write one 8bit image, JPEG encoding, CPU read bitstream @ cclk450 MHz, comparing golden | CGU/RGU ready
|  | CPU write bitstream, Jpeg decoding, CPU read rec frame @450MHz, comparing golden | CGU/RGU ready
| performance validation | 32Kx32K Max resoltuion encoding
compliance validation
Display | function validation | Display single color @ 480p @60fps | CGU/RGU/ DVP ready
|  | Display DDR data @ 480p @ 60fps | CGU/RGU/ DVP ready
|  | Display Scaling data @ 480p@60fps | CGU/RGU/ DVP ready
|  | Display one videolayer + one video layer @ 480p @ 60fps | CGU/RGU/ DVP ready
| performance validation | Display 4K@30fps | CGU/RGU/DP ready
|  | Display 1080P@60fps | CGU/RGU/DVP ready
compliance validation
System | function validation | ISP(4K@30fps) -> HEVC encoding -> SD card | CGU/RGU/ ISP/SD card ready
|  | ISP(1080P@30fps) -> H264 encoding -> SD card | CGU/RGU/ ISP / SD ready
|  | ISP(1080P@30fps) -> H264 encoding -> BB->BB -> dec -> Display | CGU/RGU/ ISP/ H264/BB/display ready
CGU/RGU/ DVP ready
performance validation
compliance validation

## NOC_OTP
block name | validation check list and status |  |  |  | issue list | finish percentage
| validattion type | validate item | status | comment
NOC | function validation | read and write NOC register
write ta20's rigister, enable the secure on-chip sram main can be accessed by unsecure mode
A7 access all device's register
CS access OTP's register
SPI Debug access OTP's register
M7 access DDR
Baseband access DDR
DMA main access DDR
eMMC access DDR
SPAcc access DDR
tRoot access DDR
USB3.0 access DDR
Type-c access DDR
PCI-e access DDR
GMAC access DDR
CEVA access DDR
DMA_ceva access DDR
HEVC access DDR
H264 access DDR
JPEG access DDR
Video Interface access DDR
Display Control access DDR
| performance validation | NOC's clock switch to 600MHz and 400MHz
OTP | function validation | read and write OTP register
program password's 32bits to XPM
read password's 32bits from XPM