## Overall
| Standard Cell | Memory Compiler | External IP | Internal IP | DFT | Backend
Phase 0 | OK | OK | OK | OK | N/A | N/A
Phase 1 | need update | OK | OK | OK |  |  | 5/15/2017
Phase 2

## Bottoms Up schedule
|  | 2016 |  |  | 2017
 | time axis 2015-12-05 to 2017-02-11
Week | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6
Milestones | 2015-12-05: IP Bronze RTL/Netlist Release; 2015-12-12: Project Kick Off; 2015-12-19: A7/CEVA Harden IP ready; 2016-01-09: Memory/Analog PHY/IO Silver RTL ready; 2016-01-16: On Monday IP Silver Netlist Release IP Silver Timing Constraints IP Floorplan Guides and Requirements; 2016-01-23: On Wed Whole Chip Silver Netlist Release Whole Chip Silver Timing Constraints release; 2016-02-06: SOC simulation env release; 2016-02-13: emulation build up on veloce release; 2016-03-12: RTL pre-gold ready, start user case verification; 2016-04-09: On Monday Final Gold .lef, .lib and .v; 2016-04-16: IP PreGold Netlist Release IP preGold Timing Constraints Release; 2016-04-23: VSI D1 Floorplan, sdc/nls quality check; 2016-04-30: Floorplan adjustment; 2016-05-07: Trial run start; 2016-05-14: clean Subblock SDC/tune Subblock floorplan; 2016-05-28: FPGA platform release; 2016-06-04: Golden SOC simulation env with UPF release; 2016-06-11: Veloce platfom #5 build release; 2016-06-18: Golden RTL release; 2016-06-25: Golden IP NLS/SDC/UPF release; 2016-07-02: Golden whole chip NLS/SDC/UPF release; 2016-07-09: Trial run end; 2016-07-16: Finial run start; 2016-07-23: Golden SOC netlist simulation env with UPF release; 2016-08-13: Post netlist simulation; 2016-09-03: Whole chip STA timing check; 2016-09-10: ECO windowns week; 2016-10-15: Validation Done - Risk Production (Metal Only); 2016-10-22: Validation Done - Risk Production (Metal Only); 2016-10-29: Rev A0 - Tapeout; 2016-11-05: IP merge and Dry run check; 2016-11-19: Rev A0 - All Layer Tape Out; 2016-12-10: release all function pattern; 2016-12-17: release EK board/Load board PCB schematic; 2017-01-14: Wafter delivery from TSMC; 2017-01-21: Package procuduce; 2017-02-04: Package chip return and Bring up
[21 empty] | 1 |  | 2 | [9 empty] | 3 | [14 empty] | 4 |  |  | 5 | [7 empty] | 6 | 7 |  | 8
Review Date
Status | 2016-02-13: CA7 harden release; 2016-02-27: CEVA Harden release; 2016-03-05: std lib/mem/silver nls release; 2016-03-12: Discuss group/floorplan with VSI; 2016-03-19: HEVC/ISP Harden release; 2016-05-07: trial run version release; 2016-05-14: HEVC/ISP/BB Floorplan; 2016-05-21: clean all sdc/ release to VSI; 2016-05-28: change sub block tuning new floorplan,clean nLite log; 2016-07-09: trial delay; 2016-07-16: trial delay; 2016-07-23: trial delay; 2016-07-30: trial delay; 2016-08-06: trial run done. release BB/ISP final version nls; 2016-08-13: final run start, delay 5 weeks; 2016-10-01: DDR Si check; 2016-10-08: build up STA timing check env; 2016-10-29: package/substrate freeze; 2016-11-19: Bring up plan reivew; 2016-12-03: Build up Function pattern; 2016-12-10: EK PCB review
Note | 2016-01-02: New year's day; 2016-01-09: annual dinner; 2016-01-30: Spring festival

## Detailed Plan
|  | MKT/ARCH | Analog IP | Digital IP | DFT | TOP/SoC | P&R | Milestone Requirement | Note
2016-12-12 | 50
2016-12-19 | 51
2016-12-26 | 52
2017-01-02 | 1 | [7 empty] | new year's day
2017-01-09 | 2 | [7 empty] | anaual dinner
2017-01-16 | 3
2017-01-23 | 4 | [7 empty] | Whole Chip Silver Netlist/SDC Release
2017-01-30 | 5 | [7 empty] | spring festival
2017-02-06 | 6
2017-02-13 | 7 |  |  | CA7 harden release
2017-02-20 | 8
2017-02-27 | 9 |  |  | CEVA Harden release
2017-03-06 | 10 |  |  |  |  | std lib/mem/silver nls release
2017-03-13 | 11 |  |  |  |  | Discuss group/floorplan with VSI
2017-03-20 | 12 |  | Need update CA7 PLL with V direction | HEVC/ISP Harden release need update USB30 to 3.20a(current is 3.10a) need update DDRMC to 3.10a-lp00(current is 3.10a) |  | Floorplan/Pin assignment/Group release
2017-03-27 | 13
2017-04-03 | 14
2017-04-10 | 15
2017-04-17 | 16 | [7 empty] | IP Gold Netlist/SDC Release
2017-04-24 | 17
2017-05-01 | 18
2017-05-08 | 19
2017-05-15 | 20
2017-05-22 | 21
2017-05-29 | 22
2017-06-05 | 23
2017-06-12 | 24
2017-06-19 | 25
2017-06-26 | 26
2017-07-03 | 27
2017-07-10 | 28
2017-07-17 | 29
2017-07-24 | 30
2017-07-31 | 31
2017-08-07 | 32
2017-08-14 | 33
2017-08-21 | 34
2017-08-28 | 35
2017-09-04 | 36

## Overall IP schedule
IPs | Owners | IP Silver rtl release (by date) | IP Silver nls/sdc release (by date) | Pre Gloden RTL release | Pre Golden NLS/SDC release | IP trial run release (5/15/2017) | IP Golden release
dft_module/MBIST/Package | VSI
CHIP_TOP | zhuoxu |  |  | by 4/14/2017 | n.a. | OK
IO SHARE | hzhang |  |  | OK | by 4/16/2017 | OK
CGU/RGU/TOP_REG | jjzhang | 12/27/2016 | 1/3/2017 | by 4/13/2017 | by 4/16/2017 | OK
ABB_TOP(analog/PLL) | yyuan |  |  | .v/.lib by 4/12/2017 .lef by 4/15/2017 | n.a. | OK
A7_SUB_SYS | pchen |  | 12/20/2016 | OK | by 4/15/2017 upf need delay | OK
CCI/Boot_ROM/DVM_repeater | pchen |  | 12/20/2016 | OK | OK(check) | OK
CEVA_SUB_SYS | cliu |  | 12/20/2016 | OK | by 4/15/2017 | OK
M7_Peri | hzhang | 12/27/2016 | 1/3/2017 | OK | by 4/16/2017 | need update(I2S)
M7_core | hzhang |  |  | OK | by 4/16/2017 | OK
CS | hzhang | 12/27/2016 | 1/3/2017 | OK | OK( check) | OK
TZC400 | hzhang | 12/27/2016 | 1/3/2017 | OK | OK( check) | OK
SMMU(VIDEO/DSP) | pchen | 12/27/2016 | 1/3/2017 | by 4/13/2017 | by 4/15/2017 | OK
NOC | wwshen | 12/27/2016 | 1/3/2017 | by 4/13/2017 | by 4/15/2017 | OK
DDR_TOP | jma | 1/6/2017 | 1/17/2017 | OK | by 4/15/2017 | OK
USB30_TOP | hsun | 12/27/2016 | 1/3/2017 | by 4/12/2017 | by 4/15/2017 | OK
TYPC_TOP | jfhuang |  |  |  |  | need update
PCIE_TOP | jjzhang | 12/27/2016 | 1/3/2017 | OK | by 4/15/2017 | OK
HDMI_RX_TOP | hbzhong |  |  | by 4/12/2017 | by 4/15/2017 | OK
MIPI_RX_TOP/TX | zxie |  |  | OK | by 4/15/2017 | need update
GMAC_TOP | lyang | 12/27/2016 | 1/3/2017 | OK | by 4/15/2017 | OK
eMMC_TOP | lyang |  |  | OK | by 4/15/2017 | OK
ISP_TOP | huawang |  |  | OK | by 4/16/2017 | OK
Video_IF(DVP) | zxie |  |  | OK | by 4/15/2017 | need update
BB_TOP | zhengli |  |  | mem need confirm. | by 4/16/2017 | OK
DMAC-TOP | lyang | 12/27/2016 | 1/3/2017 | OK | OK( check) | OK
DMAC-CEVA | lyang |  |  | OK | OK( check) | OK
SRAM_TOP | lyang | 12/27/2016 | 1/3/2017 | OK | by 4/15/2017 | OK
Sec_sub_system | hsun | 1/6/2017 | 1/17/2017 | by 4/13/2017 | by 4/15/2017 | OK
OTP_CTRL | wwshen | 1/3/2017 | 1/17/2017 | OK | by 4/15/2017 | need update
HEVC_TOP | zqchen | 1/3/2017 | 1/16/2017 | by 4/12/2017 | by 4/17/2017 | OK
H264_TOP | zqchen | 1/3/2017 | 1/16/2017 | by 4/12/2017 | by 4/15/2017 | OK
JPEG_TOP | zqchen | 1/3/2017 | 1/16/2017 | OK | by 4/15/2017 | OK
DISP_TOP | zqchen |  |  | by 4/12/2017 | by 4/15/2017 | OK

## External IP
| Source | Status | Silver | Gold | Note | license
DDR3 PHY | Synopsys | ready |  |  | 3.20a | renew already
DDR3 Link+ECC | Synopsys | ready |  |  | 3.10a
USB 3.0 PHY | Synopsys | ready |  |  | 4.04a
USB 3.0 MAC | Synopsys | ready |  |  | 3.20a
PCIe 2.0 PHY | Synopsys | ready |  |  | 2.07i
PCIe 2.0 MAC | Synopsys | ready |  |  | 4.90a
MIPI CSI PHY | Synopsys | ready |  |  | 6.02a
MIPI CSI RX controller | Synopsys | ready |  |  | 1.20a
eDP/TYPC MAC | Cadence | ready
eDP/TYPC PHY | Cadence | ready
HDMI 1.4b MAC | Synopsys | ready |  |  | 2.12a
HDMI 2.0 PHY | Synopsys | ready |  |  | 6.01a
GMAC | CAST | ready |  |  | 1.4
A7 CPU | ARM | ready
CCI-400 | ARM | ready
ADB-400 | ARM | ready
SMMU-500 | ARM | ready
Trust Zone Controller | ARM | ready
eMMC | Synopsys | ready |  |  | 1.60a | expired by 8/4
CEVA XM4 | CEVA | ready
DMAC-AXI | Synopsys | ready
tRoot | Synopsys | ready |  |  | 1.10a | wait for final version FM by 8/4
TRNG for ESM | Synopsys | ready |  |  | 2.00a
PKA | Synopsys | ready |  |  | 2.10a
SPAcc | Synopsys | ready |  |  | 2.00a
DISP | Verisillicon | ready
HEVC | chipmedia | ready
H264 | chipmedia | ready
JEPG | chipmedia | ready
CF50 | chipmedia | ready
Standard Cell | Synopsys | ready |  |  |  | HPC kit by2017/10/20
Memory Compilers | Synopsys | ready |  |  |  | expired by 8/10, replace boot rom as free TSMC ROM, no CCS model, only NLDM model
Memory Compilers | TSMC | ready |  |  |  | ROM only
OTP | Kilopass | ready
DMAC-AXI | Synopsys | ready |  |  | 1.01a

## inhouse Analog IP
ID | Analog Ips | Porting Source | Bronze | Silver | Gold | Note
1 | PLL
2 | eMMC PLL
3 | HDMI Audio PLL
4 | PVT sensor
5 | SAR-ADC w DMA
6 | cdm buffer
7 | ABB
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## backend_NTL_handoff
 | time axis 2017-02-13 to 2017-04-14
CEVA | cevaxm4_subsys_inst | 2017-02-27: core; 2017-03-28: CEVA
NOC_ceva
dmac_ceva_axi_wrapper_inst
mmu500_smmu_dsp_inst
CA7 | a7_subsystem_inst | 2017-02-13: core
cci400_inst
HEVC | hevc_top_inst | 2017-03-22: HEVC
ISP | luxury_isp_top_inst | 2017-03-24: ISP
DDR_TOP | DDR_TOP_inst | 2017-03-28: DDR
BaseBand | sirius_asic_top_baseband_inst | bar: 2017-03-28
P1 | mipi_top_inst
hdmi_top_inst
video_if_inst
display_engine_inst
P2 | h264_top_inst
jpeg_top_inst
NOC_vision
dmac_top_axi_wrapper_inst
mmu500_smmu_video_inst
P3 | cdn_typec_subsystem_top_inst
pcie_iip_device_inst
usb3_top_inst
P4 | m7core
sce_subsys_top_inst
boot_rom_inst
sram_top_inst
TOP | TZC400_6F_inst
sirius_non_secure_inst
gbeth_top_inst
sirius_test_func_inst
sirius_spi2apb_inst
NOC_main
emmc_ctrl_inst
M7_perip
CXSOC_inst

## BE_Status
No | Sub name | 2017-05-15 | 2017-05-16 | #REF! | 2017-07-06 | 2017-07-21
1 | DDR_TOP | DCG NLS/SDC release |  | no update | Finial NLS/SDC release | Final start
2 | HEVC_TOP | NLS/SDC/UPF release |  | resynthesis fix 0P5 DRC |  | Final start
3 | BASEBAND | NLS/SDC release |  |  |  | still not final
4 | ISP | NLS/SDC/UPF release, need resynthesis for M7 core to fix module long issue increase more area, need add spare logic for future. | ISP re-synthesis for naming long issue/add more spare logic | resynthesis fix 0P5 DRC,fix long name issue | ISP re-synthesis for congestion | still not final, congestion is resolved
5 | sirius_sub_ca7 | DCG NLS/SDC/UPF release |  | no update | CORE is final | Final start
6 | sirius_sub_ceva | DCG NLS/SDC/UPF is not ready |  | no update | CORE is final | CORE is final, harden/sub is not
7 | sirius_sub_1 | NLS/SDC release |  | add USB |  | change MIPI P/G interface
8 | sirius_sub_2 | NLS/SDC release |  | add bridge,remove DMAC TOP |  | add AXI repeater for VIF
9 | sirius_sub_3 | NLS/SDC release |  | remove USB |  | change TYPC/PCIe RTL to aviod in2out path
10 | sirius_sub_4 | NLS/SDC release, need resynthesis for M7 core to fix module long issue | release new NLS to fix naming long issue | add bridge, fix long name issue |  | replace Boot_rom/merge Sec_rom
11 | sirius_sub_top | NLS/SDC release | Pin assignment sync up SDC review on VSI | add DMAC TOP, reduce NOC main interface |  | not final

## Groups
No | IP |  | power stratege | tech
1 | CHIP_TOP | SUB_TOP | N.A | 7T
2 | IO SHARE | SUB_TOP | N.A | 7T
3 | CGU/RGU/TOP_REG | SUB_TOP | N.A | 7T
4 | ABB_TOP(analog/PLL) | SUB_TOP | N.A | 7T
5 | A7_SUB_SYS | SUB_CA7 | OD+PSO | 12T+7T
6 | CCI | SUB_CA7 | N.A | 7T
7 | Boot_ROM | SUB4 | N.A | 7T
8 | DVM_repeater | SUB_TOP | N.A | 7T
9 | CEVA_SUB_SYS | SUB_CEVA | N.A | 12T+7T
10 | M7_Peri | SUB_TOP | N.A | 7T
11 | M7_core | SUB4 | N.A | 7T
12 | CS | SUB_TOP | N.A | 7T
13 | TZC400 | SUB_TOP | N.A | 7T
14 | SMMU_DSP | SUB_CEVA | N.A | 7T
| SMMU_VIDEO | SUB2
15 | NOC_MAIN | SUB_TOP | N.A | 7T
| NOC_VISION | SUB2 | N.A | 7T
| NOC_CEVA | SUB_CEVA | N.A | 7T
16 | DDR_TOP | DDR_TOP | N.A | 9T
17 | USB30_TOP | SUB1 | N.A | 7T
18 | TYPC_TOP | SUB3 | N.A | 7T
19 | PCIE_TOP | SUB3 | N.A | 7T
20 | HDMI_RX_TOP | SUB1 | N.A | 7T
21 | MIPI_RX_TOP | SUB1 | N.A | 7T
22 | MIPI_TX_TOP | SUB1 | N.A | 7T
23 | GMAC_TOP | SUB_TOP | N.A | 7T
24 | eMMC_TOP | SUB_TOP | N.A | 7T
25 | ISP_TOP | ISP_TOP | N.A | 7T
26 | Video_IF | SUB1 | N.A | 7T
27 | BB_TOP | BB_TOP | N.A | 7T
28 | DMAC-TOP | SUB_TOP | N.A | 7T
29 | DMAC-CEVA | SUB_CEVA | N.A | 7T
30 | SRAM_TOP | SUB4 | N.A | 7T
31 | Sec_sub_system | SUB4 | N.A | 7T
32 | OTP_CTRL | SUB4 | N.A | 7T
33 | HEVC_TOP | HEVC | N.A | 7T
34 | H264_TOP | SUB2 | N.A | 7T
35 | JPEG_TOP | SUB2 | N.A | 7T
36 | DISP_TOP | SUB2 | N.A | 7T
37 | BB ROM value | BB_TOP
38 | Sec ROM value | SUB4
39 | Boot ROM value | SUB4
40 | cdm_buffer