## Overall
| Standard Cell | Memory Compiler | External IP | Internal IP | DFT | Backend
Phase 0 | OK | OK | OK | OK | N/A | N/A
Phase 1
Phase 2

## Bottoms Up schedule
| 2015 | [20 empty] | 2016
 | time axis 2015-12-12 to 2016-12-31
Week | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
Milestones | 2015-12-12: Project Kick Off; 2015-12-19: A7/CEVA Harden IP ready; 2016-01-09: Memory/Analog PHY/IO Silver RTL ready; 2016-01-16: On Monday IP Silver Netlist Release IP Silver Timing Constraints IP Floorplan Guides and Requirements; 2016-01-23: On Wed Whole Chip Silver Netlist Release Whole Chip Silver Timing Constraints release; 2016-02-13: eMMC/Ethernet/PCIe emulation model build up on veloce; 2016-03-12: RTL pregold ready, start user case verification; 2016-04-09: On Monday Final Gold .lef, .lib and .v; 2016-04-16: IP Gold Netlist Release IP Gold Timing Constraints Release; 2016-04-23: Whole Chip Golden Netlist Release Whole chip golden Timing Constraints release; 2016-07-09: On Monday Final IP GDSII Release; 2016-07-30: Rev A0 - Tapeout; 2016-10-15: Validation Done - Risk Production (Metal Only); 2016-10-22: Validation Done - Risk Production (Metal Only); 2016-11-19: Rev B0 - All Layer Tape Out
Review Date
Status | 2016-02-13: CA7 harden release; 2016-02-27: CEVA Harden release; 2016-03-05: std lib/mem/silver nls release; 2016-03-12: Discuss group/floorplan with VSI; 2016-03-19: HEVC/ISP Harden release
Note | 2016-01-02: New year's day; 2016-01-09: annual dinner; 2016-01-30: Spring festival

## Detailed Plan
|  | MKT/ARCH | Analog IP | Digital IP | DFT | TOP/SoC | P&R | Milestone Requirement | Note
2016-12-12 | 50
2016-12-19 | 51
2016-12-26 | 52
2017-01-02 | 1 | [7 empty] | new year's day
2017-01-09 | 2 | [7 empty] | anaual dinner
2017-01-16 | 3
2017-01-23 | 4 | [7 empty] | Whole Chip Silver Netlist/SDC Release
2017-01-30 | 5 | [7 empty] | spring festival
2017-02-06 | 6
2017-02-13 | 7 |  |  | CA7 harden release
2017-02-20 | 8
2017-02-27 | 9 |  |  | CEVA Harden release
2017-03-06 | 10 |  |  |  |  | std lib/mem/silver nls release
2017-03-13 | 11 |  |  |  |  | Discuss group/floorplan with VSI
2017-03-20 | 12 |  | Need update CA7 PLL with V direction | HEVC/ISP Harden release need update USB30 to 3.20a(current is 3.10a) need update DDRMC to 3.10a-lp00(current is 3.10a) |  | Floorplan/Pin assignment/Group release
2017-03-27 | 13
2017-04-03 | 14
2017-04-10 | 15
2017-04-17 | 16 | [7 empty] | IP Gold Netlist/SDC Release
2017-04-24 | 17
2017-05-01 | 18
2017-05-08 | 19
2017-05-15 | 20
2017-05-22 | 21
2017-05-29 | 22
2017-06-05 | 23
2017-06-12 | 24
2017-06-19 | 25
2017-06-26 | 26
2017-07-03 | 27
2017-07-10 | 28
2017-07-17 | 29
2017-07-24 | 30
2017-07-31 | 31
2017-08-07 | 32
2017-08-14 | 33
2017-08-21 | 34
2017-08-28 | 35
2017-09-04 | 36

## Overall IP schedule
IPs | Owners | IP Silver rtl release (by date) | IP Silver nls/sdc release (by date) | IP Golden release
dft_module/MBIST/Package
CHIP_TOP
IO SHARE
CGU/RGU/TOP_REG | jjzhang | 12/27/2016 | 1/3/2017
ABB_TOP(analog/PLL) | yyuan
A7_SUB_SYS | pchen |  | 12/20/2016
CEVA_SUB_SYS | cliu |  | 12/20/2016
M7_SUB_SYS(SD/I2S) | hzhang/lyang | 12/27/2016 | 1/3/2017
CS | hzhang | 12/27/2016 | 1/3/2017
TZC400 | hzhang | 12/27/2016 | 1/3/2017
SMMU | pchen | 12/27/2016 | 1/3/2017
NOC | wwshen | 12/27/2016 | 1/3/2017
DDR_TOP | jma | 1/6/2017 | 1/17/2017
USB30_TOP | hsun | 12/27/2016 | 1/3/2017
TYPC_TOP
PCIE_TOP | jjzhang | 12/27/2016 | 1/3/2017
HDMI_RX_TOP
MIPI_RX_TOP
MIPI_TX_TOP
GMAC_TOP | lyang | 12/27/2016 | 1/3/2017
eMMC_TOP
DVP_RX/DVP_TX
ISP_TOP
ISP_BYPASS_TOP
BB_TOP
DMAC-AXI | lyang | 12/27/2016 | 1/3/2017
SRAM_TOP | lyang | 12/27/2016 | 1/3/2017
TROOT_TOP | hsun | 1/6/2017 | 1/17/2017
OTP_CTRL | wwshen | 1/3/2017 | 1/17/2017
HECV_TOP | jlliu | 1/3/2017 | 1/16/2017
H264_TOP | jlliu | 1/3/2017 | 1/16/2017
JPEG_TOP | jlliu | 1/3/2017 | 1/16/2017
DISP_TOP | jlliu

## External IP
| Source | Status | Silver | Gold | Note
DDR3 PHY | Synopsys | ready
DDR3 Link+ECC | Synopsys | ready |  |  | 3.10a
USB 3.0 PHY | Synopsys | ready |  |  | 4.04a
USB 3.0 MAC | Synopsys | ready |  |  | 3.10a
PCIe 2.0 PHY | Synopsys | ready |  |  | 2.07i
PCIe 2.0 MAC | Synopsys | ready |  |  | 4.90a
MIPI CSI PHY | Synopsys | ready |  |  | 6.02a
MIPI CSI RX controller | Synopsys | ready |  |  | 1.20a
eDP/TYPC MAC | Cadence | ready
eDP/TYPC PHY | Cadence | ready
HDMI 1.4b MAC | Synopsys | ready |  |  | 2.12a
HDMI 2.0 PHY | Synopsys | ready |  |  | 6.01a
GMAC | CAST | ready
A7 CPU | ARM | ready
CCI-400 | ARM | ready
ADB-400 | ARM | ready
SMMU-500 | ARM | ready
Trust Zone Controller | ARM | ready
eMMC | Synopsys | ready |  |  | 1.50a
CEVA XM4 | CEVA | ready
DMAC-AXI | Synopsys | ready
tRoot | Synopsys | ready
TRNG for ESM | Synopsys | ready
PKA | Synopsys | ready
SPAcc | Synopsys | ready
DISP | Verisillicon | n.a |  |  | till Apr
HEVC | chipmedia | ready
H264 | chipmedia | ready
JEPG | chipmedia | ready
CF50 | chipmedia | ready
Standard Cell | Synopsys | ready
Memory Compilers | Synopsys | ready
OTP | Kilopass | ready

## inhouse Analog IP
ID | Analog Ips | Porting Source | Bronze | Silver | Gold | Note
1 | PLL
2 | eMMC PLL
3 | HDMI Audio PLL
4 | PVT sensor
5 | SAR-ADC w DMA
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29

## backend_NTL_handoff
 | time axis 2017-02-13 to 2017-04-14
CEVA | cevaxm4_subsys_inst | 2017-02-27: core; 2017-03-28: CEVA
NOC_ceva
dmac_ceva_axi_wrapper_inst
mmu500_smmu_dsp_inst
CA7 | a7_subsystem_inst | 2017-02-13: core
cci400_inst
HEVC | hevc_top_inst | 2017-03-22: HEVC
ISP | luxury_isp_top_inst | 2017-03-24: ISP
DDR_TOP | DDR_TOP_inst | 2017-03-28: DDR
BaseBand | sirius_asic_top_baseband_inst | bar: 2017-03-28
P1 | mipi_top_inst
hdmi_top_inst
video_if_inst
display_engine_inst
P2 | h264_top_inst
jpeg_top_inst
NOC_vision
dmac_top_axi_wrapper_inst
mmu500_smmu_video_inst
P3 | cdn_typec_subsystem_top_inst
pcie_iip_device_inst
usb3_top_inst
P4 | m7core
sce_subsys_top_inst
boot_rom_inst
sram_top_inst
TOP | TZC400_6F_inst
sirius_non_secure_inst
gbeth_top_inst
sirius_test_func_inst
sirius_spi2apb_inst
NOC_main
emmc_ctrl_inst
M7_perip
CXSOC_inst

## Sheet1
|  | FE |  |  | BE |  |  |  |  | TOP
| Weekly No. | BIST | SCAN | Timing | CA7 | CEVA | DDR | H265 | 6 x partition (BB+ISP+P1+P2+P3+P4) | PR | RDL+PV
trial run | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 3 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 4 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 6 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 7 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 9 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
| 10 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 12
finial run | 11 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 12 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 13 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 14 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 15 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 16 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 17 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 18 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 19 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 20 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 21 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 22 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 23 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 24 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 25 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 4 | 2 | 1 | 17
| 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 14
| 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 14
| 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 14
| 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 1 | 14
total man
[11 empty] | total effort | 431 | 14.8621