## 2017-05-16
Thanks you all to attend yesterday's review from morning to deep night. Please check action items below. | status
- ESD CDM clamp
o confirm OTP CDM buffer requirement with vendor (Artosyn)
o Artosyn to provide PCIE CDM buffer requirement (Artosyn)
o Artosyn to provide CDM clamp library (Artosyn, done)
o integrate CDM CLAMP with buffer(VSI)
- Pin Assignment
o add pin name for DDR VDD/VSS IO(Artosyn)
o confirm that no bump/ball requirement on VREF_DAC (Artosyn, done)
- Library
o deliver SNPS STD library and check the difference (Artosyn)
- Tech file
o provide NXTgrd file(Artosyn)
- Netlist
o update SUB3 netlist to fix DFT clock mux, PG port conflict, buffer on bump net issues (Artosyn)
- SDC
o Provide full chip flatten sdc(Artosyn)
o check SUB3 clock gating hold violation , and forcing pin as illegal timing points (Artosyn)
o sub1 hdmi clock edge issues in INNOVUS (VSI)
o check big hold violation (1.5ns) on ABB interface (Artosyn)
o update SDC of ddr/ceva_harden/ca7_sub/ca7_harden/top/sub1/sub3/sub4 SDC (VSI)
o check top timing based on latest SDC (VSI)
o set_max_delay use variable (Artosyn)
- UPF
o Provide full chip flatten upf(Artosyn)
o Provide CEVA pre-syn UPF (Artosyn)
o Provide CEVA subsys flatten UPF, CA7 subsys flatten UPF. (Artosyn)
- ECO decap cell
o confirm ECO for ISP/BB is 1% of total STD cell number , RVT ECO will be used (Artosyn, done)
- provide don't use cell list (Artosyn)
- provide floating leaf pins and floating ports (VSI)