## Action Items
Status and Action Items
Issues: Library | Action Items | owner | open date | close date | status | Artosyn
STD library update from snps |  | artosyn |  |  | open | studying
ABB LEF | t28_abb_top named B[*] placed at the bottom-right corner | artosyn |  |  | close
HPK library | no gds/cdl files | artosyn |  |  | open | doing
OTP | how to gurantee 20pF capacitance | artosyn |  |  | open | close
STD library EO_0P5 cell have DRC |  | artosyn/VSI |  |  | open | feedback to VSI
Memory | memory lib is ecsm , not ccs | artosyn |  |  | open | talking with SYNP for CCS
Memory | no spice netlist | artosyn |  |  | open | done
Issues: Tech File | Action Items | owner | open date | close date | status
ITF/ICT/QRC/NXTgrd with "_T" | arotsyn to check with TSMC | artosyn |  |  | open | pending for TSMC feedback
nxtgrd file |  | artosyn |  |  | open | pending for TSMC feedback
spice model for IR drop |  | artosyn |  |  | open | done
Issues: Timing Signoff Creteria | Action Items | owner | open date | close date | status
setup uncertainty | Artosyn to decide 50ps / 75ps ?; USB 200ps setup uncertainty; hold 100ps hold uncertainty | artosyn |  |  | open | done
MEM signoff library (ffbc or ff) | Artosyn to confirm use ffbc or ff to signoff | artosyn |  |  | open | done
Issues: NL/SDC/UPF by block | Action Items | owner | open date | close date | status
Ceva core | reduce LVT pct , currently 23% | artosyn |  |  | open | done
Ceva harden | adjust clock frequency from 800M to the achievable one | artosyn |  |  | open | done
ceva subsys flatten | update flatten SDC | artosyn |  |  | open | done
| flatten UPF | artosyn |  |  | open | done
CA7 CORE | provide pre-syn UPF |  |  |  | open | done
| LVT pct > 10% | artosyn |  |  | open | done
ca7 harden | provide pre-syn UPF |  |  |  | open | done
| share bus MBIST debug | artosyn |  |  | open | done
ca7 subsys | provide pre-syn UPF | artosyn |  |  | open | done
ca7 subsys flatten | update flatten SDC | artosyn |  |  | open | done
| flatten UPF | artosyn |  |  | open | done
DDR | check DDR place timing | artosyn |  |  | open | done
| don’t touch net in DDR implementation check list | artosyn |  |  | open | done
sub1 | big hold violation to be checked | VSI |  |  | open | done
sub3 | path between clock "usb3_top_inst_global_clk_150m" and " usb3_top_inst_FREECLK" is false or not | artosyn |  |  | open | done
ISP | shorten module name | artosyn |  |  | close
TOP | add port for OTP IO vdd18 | artosyn |  |  | close
| remove RGMI PVDD1ANARGM/PVSS1ANARGM IO | artosyn |  |  | close
| ABB/BB/TOP talk issues | artosyn |  |  | close
| pull Analog Power ports to top | artosyn |  |  | close
| connection between ABB to PVT sensorconnection | artosyn |  |  | open | done
| sub 1 clock mux not transparent | artosyn |  |  | close
| floating ports HDMI_CEC_PAD | artosyn |  |  | close
| full chip input transition/load | artosyn |  |  | close
| set IO driving strength in SDC | artosyn |  |  | open | done
| remove async groups for set_max delay | artosyn |  |  | open | done
| IO timing violation | artosyn |  |  | open | done
| timing path from regs through IO to regs | artosyn |  |  | close
flatten | UPF is not available | artosyn |  |  | open | doing
| SDC is not available | artosyn |  |  | open | doing
Issues: SDC general | Action Items | owner | open date | close date | status
set_max_delay use variable |  | artosyn |  |  | open | doing
Issues: clock diagram | Action Items | owner | open date | close date | status
update full chip clock diagram | Artosyn adjust cgu to imprve at-speed clock frequency | artosyn |  |  | open | done
provide sub1/sub2/sub3/sub4 clock diagram |  | artosyn |  |  | open | sub3, missing sub1/2/4
Issues: low power | Action Items | owner | open date | close date | status
low power switch enable and isolation enable sequence configurable |  | artosyn |  |  | close
power switch control active 0 or 1 | artosyn to check | artosyn |  |  | open | done
Issues: ESD | Action Items | owner | open date | close date | status
OTP CDM | Artosyn confirm OTP do not have CDM buffer requirement for both input/output | artosyn |  |  | open | done
PCIE CDM | Artosyn to confirm with SNPS about PCIE CDM requirement | artosyn |  |  | open | done
Issues: IP PG connection | Action Items | owner | open date | close date | status
IP name: dwc_usb3_pads_sspx1_hspx1_ns VSS1/VSS2 connection | connected to SOC ground | artosyn |  |  | close
can DVDD/GND of typeC connect to SOC VDD/VSS in SOC die ? |  | artosyn |  |  | open | done
can IP ground connect to SOC ground in package substrate and share same ball ? |  | artosyn |  |  | open | done
Issues: Package | Action Items | owner | open date | close date | status
signal name mismatch between pin_assignemnt and netlist | 如：AVDD1V8_MIPI和AGND_MIPI在网表里是叫MIPI_AVDD1V8和MIPI_AGND VREFI[*](pkg name “DDR_VREF*”)在网表里是VREFI_*_ GPIO_B0_4(pkg name “EMMC_PWR”)在网表里叫EMMC_PWR_PAD | artosyn |  |  | open | done
SD/EMMC have two power domain, have seperated VDD18 IO , need seperatated pin name | Artosyn to check with TSMC | artosyn |  |  | open | done
Issues: physical guideline | Action Items | owner | open date | close date | status
analog IP routing/placement keepout margin |  | artosyn |  |  | open | done
don’t touch net list | Artosyn to provide don’t touch net list to VSI | artosyn |  |  | open | done
update PLL behave model | [5 empty] | done
update BB nls to break in2out timing path | [5 empty] | done
request change floorplan size to 9.45x10 | [5 empty] | request