## Action Items
Status and Action Items
Issues: Library | Action Items | owner | comment | open date | close date | status
STD library update from snps |  | artosyn |  |  |  | open
OD library |  | artosyn |  |  |  | open
ECO DCAP | check DECAP_ECOCT difference with DECAP_ECO | artosyn |  |  |  | open
ABB LEF | t28_abb_top named B[*] placed at the bottom-right corner | artosyn |  |  |  | close
HPK library | no gds/cdl files | artosyn |  |  |  | open
OTP | how to gurantee 20pF capacitance | artosyn |  |  |  | close
STD library EO_0P5 cell have DRC |  | artosyn/VSI |  |  |  | open
Memory | memory lib is ecsm , not ccs | artosyn |  |  |  | open
Memory | no spice netlist | artosyn |  |  |  | close
Issues: Tech File | Action Items | owner | comment | open date | close date | status
ITF/ICT/QRC/NXTgrd with "_T" | arotsyn to check with TSMC | artosyn |  |  |  | open
nxtgrd file |  | artosyn |  |  |  | open
spice model for IR drop |  | artosyn |  |  |  | close
Issues: Timing Signoff Creteria | Action Items | owner | comment | open date | close date | status
setup uncertainty | Artosyn to decide 50ps / 75ps(<800M) ?; | artosyn |  |  |  | close
USB 200ps setup uncertainty; hold 100ps hold uncertainty | provide clock name |  |  |  |  | open
MEM signoff library (ffbc or ff) | Artosyn to confirm use ff to signoff | artosyn |  |  |  | close
signoff std@ffbc and mem@ff ? | [5 empty] | open
Issues: NL/SDC/UPF by block | Action Items | owner | comment | open date | close date | status
Ceva core | reduce LVT pct , currently 23% | artosyn |  |  |  | VSI check ING
Ceva harden | PLL reset need pulse in scan mode, update model | artosyn | DFT |  |  | close
| PLL output 500M instead of 650M in scan mode | artosyn | DFT |  |  | open
| adjust clock frequency from 800M to the achievable one | artosyn |  |  |  | open
ceva subsys | clock freq overconstraint | artosyn |  |  |  | open
| include constraint in harden | artosyn |  |  |  | open
ceva subsys flatten | update flatten SDC | artosyn |  |  |  | VSI check ING
| flatten UPF | artosyn |  |  |  | VSI check ING
CA7 CORE | provide pre-syn UPF |  |  |  |  | VSI check ING
| LVT pct > 10% | artosyn |  |  |  | VSI check ING
ca7 harden | provide pre-syn UPF | artosyn |  |  |  | VSI check ING
| share bus MBIST debug | artosyn |  |  |  | open
| scan reset tie 0 and be optimized , DFF become constant in scan mode | artosyn | DFT |  |  | open
| DFT DRC: sirius_top/sirius_sub_ca7_inst/a7_subsystem_inst/u_a7_harden_subsystem/u_a7_cgu/u_cortexa7_clk/X (it exists in ‘occ_location.list’ you released, but we cannot get this pin in netlist) | artosyn | DFT |  |  | open
ca7 subsys | provide pre-syn UPF | artosyn |  |  |  | VSI check ING
| axi clock freq 650M not consistent with clock diagram |  |  |  |  | open
ca7 subsys flatten | update flatten SDC | artosyn |  |  |  | VSI check ING
| flatten UPF | artosyn |  |  |  | VSI check ING
DDR | check DDR place timing | artosyn |  |  |  | VSI check ING
| add false path from ac_cfg_dtomode_reg | artosyn |  |  |  | VSI check ING
| don’t touch net in DDR implementation check list | artosyn |  |  |  | VSI check ING
SUB2 | DMAC move to top | artosyn |  |  |  | open
SUB4 | sub4 module long name | artosyn |  |  |  | open
sub1 | hold violation between clock groups mipi_top_inst/mipi_01/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and mipi_top_inst/mipi_01/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs | artosyn |  |  |  | VSI check ING
| hold violation between clock groups mipi_top_inst/mipi_23/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and 'mipi_top_inst/mipi_23/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs | artosyn |  |  |  | VSI check ING
sub3 | scan mode timing through pcie/tx0_state | VSI |  |  |  | VSI check ING
| DFT: Sub3 spdif_* regs clocks cannot be traced back to occ points. Please confirm whether they should be excluded from scan chains. Add fix buffer to add dedicated OCC , update clock diagram | artosyn | DFT |  |  | open
| DFT: sub3 ‘mux synthesized to NOR gate’ recurred. cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_mclk_rstn/U1 cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_cdr_rstn/U1 | artosyn | DFT |  |  | open
| TYPEC_DVDD_0P9 of TYPEC floating | artosyn |  |  |  | VSI check ING
| path between clock "usb3_top_inst_global_clk_150m" and " usb3_top_inst_FREECLK" is false or not | artosyn |  |  |  | open
HEVC | power switch control signal off state require the AON invter | artosyn |  |  |  | open
ISP | power switch control signal off state require the AON invter | artosyn |  |  |  | open
| shorten module name | artosyn |  |  |  | open
TOP | add port for OTP IO vdd18 | artosyn |  |  |  | close
| remove RGMI PVDD1ANARGM/PVSS1ANARGM IO | artosyn |  |  |  | close
| ABB/BB/TOP talk issues | artosyn |  |  |  | close
| pull Analog Power ports to top | artosyn |  |  |  | close
| connection between ABB to TS sensorconnection | artosyn |  |  |  | open
| sub 1 clock mux not transparent | artosyn |  |  |  | close
| floating ports HDMI_CEC_PAD | artosyn |  |  |  | close
| full chip input transition/load | artosyn |  |  |  | close
| set IO driving strength /slew rate in SDC (check pin assignment) | artosyn |  |  |  | open
| remove async groups for set_max delay | artosyn |  |  |  | VSI check ING
| trust zone pipeline (from sub2 through trust zone to sub2) | artosyn |  |  |  | open
| trust zone pipeline (from sub2 through trust zone to DDR) | artosyn |  |  |  | open
| IO timing violation | artosyn |  |  |  | open
| use set_output_delay to constraint clock/data IO skew | artosyn |  |  |  | VSI check ING
| DVP IO through pin share module to DVP, need mux name to avoid detour | artosyn |  |  |  | close
| DVP IO through pin share module to SUB3, add multicycle | artosyn |  |  |  | VSI check ING
| clock divider reset share with test mode latch enable | artosyn | DFT |  |  | close
| DFT DRC: five unfixed muxex on the clock path for clock sirius_sub_1_inst/dvp0_clk_p and sirius_sub_1_inst/dvp1_clk_p | artosyn | DFT |  |  | open
| DFT DRC: cannot be traced back to occ point for sirius_sub_3_inst/m7_i2s_sclk_out_dp | artosyn | DFT |  |  | open
|  DFT DRC: sirius_sub_top_inst/gbeth_top_inst/i_gbeth_clk_div/mtx_125_MHz_i_reg/Q (please confirm whether it is a clock divider of CLK_CORE_GMAC, it drives thousands of regs. If so, please make sure its reset signal is controlled by an individual IO which is dedicated to reset divider regs). no OCC insertiion points in clock diagram | artosyn | DFT |  |  | open
| clock divider reset do not have two pipeline register to de-X | artosyn | DFT |  |  | open
| timing path from regs through IO to regs | artosyn |  |  |  | close
flatten | UPF is not available | artosyn |  |  |  | open
| clock freqency consistency between block sdc and flatten sdc | artosyn |  |  |  | open
| SDC is not available | artosyn |  |  |  | open
Issues: SDC general | Action Items | owner | comment | open date | close date | status
set_max_delay use variable (NOC) |  | artosyn |  |  |  | open
clock period 6/6.66/6.67 in some block |  | artosyn |  |  |  | open
remove clock frequency over-constraint |  | artosyn |  |  |  | open
wrong clock frequency |  | artosyn |  |  |  | open
Issues: clock diagram | Action Items | owner | comment | open date | close date | status
update full chip clock diagram | Artosyn adjust cgu to imprve at-speed clock frequency | artosyn |  |  |  | open
provide sub1/sub2/sub3/sub4 clock diagram |  | artosyn | DFT/Timing |  |  | open
Issues: low power | Action Items | owner | comment | open date | close date | status
low power switch enable and isolation enable sequence configurable |  | artosyn |  |  |  | close
power switch control active 0 or 1 | artosyn to check | artosyn |  |  |  | open
Issues: ESD | Action Items | owner | comment | open date | close date | status
OTP CDM | Artosyn confirm OTP do not have CDM buffer requirement for both input/output | artosyn |  |  |  | close
PCIE CDM | Artosyn to confirm with SNPS about PCIE CDM requirement | artosyn |  |  |  | open
Issues: IP PG connection | Action Items | owner | comment | open date | close date | status
IP name: dwc_usb3_pads_sspx1_hspx1_ns VSS1/VSS2 connection | connected to SOC ground | artosyn |  |  |  | close
can DVDD/GND of typeC connect to SOC VDD/VSS in SOC die ? |  | artosyn |  |  |  | open
can IP ground connect to SOC ground in package substrate and share same ball ? |  | artosyn |  |  |  | open
Issues: Package | Action Items | owner | comment | open date | close date | status
signal name mismatch between pin_assignemnt and netlist | 如：AVDD1V8_MIPI和AGND_MIPI在网表里是叫MIPI_AVDD1V8和MIPI_AGND VREFI[*](pkg name “DDR_VREF*”)在网表里是VREFI_*_ GPIO_B0_4(pkg name “EMMC_PWR”)在网表里叫EMMC_PWR_PAD | artosyn |  |  |  | open
SD/EMMC have two power domain, have seperated VDD18 IO , need seperatated pin name ; | Artosyn to check with TSMC | artosyn |  |  |  | open
SD/EMMC require to have dedicated VDD18 ball for decap | Artosyn to check with TSMC | artosyn |  |  |  | open
RGMII IO require to share same ball for different power pin | Artosyn to check with TSMC | artosyn |  |  |  | open
OTP | no instance name of OTP IO in pin assignment | artosyn |  |  |  | open
TYPEC ref clock tie which ground |  | artosyn |  |  |  | open
define SSOG group |  | artosyn |  |  |  | open
define slew rate and driving strength |  | artosyn |  |  |  | open
Issues: physical guideline | Action Items | owner | comment | open date | close date | status
analog IP routing/placement keepout margin |  | artosyn |  |  |  | VSI check ING
don’t touch net list | Artosyn to provide don’t touch net list to VSI | artosyn |  |  |  | VSI check ING
Mask filed utilization |  | artosyn |  |  |  | open
Issues: dft | Action Items | owner | comment | open date | close date | status
Prepare testbench to check functionality of clock gen logic and confirm the clock frequency in scan_mode/mbist_mode. |  | artosyn | DFT |  |  | open
clock diagram / block sdc/ flatten SDC frequency consistency |  | artosyn | DFT |  |  | open
at speed dft clock frequncy higher than function | check excel sheet | artosyn | DFT |  |  | open
at speed dft clock frequncy lower than function |  | artosyn | DFT |  |  | open
reset signal need double-sync before reach to CGU in scan¦mbist mode. |  | artosyn | DFT |  |  | open
2. Don’t share OCC for clock groups which is async in function mode even they have same frequency , add fix buffer to split and mark in clock diagram . |  | artosyn | DFT |  |  | open