## Action Items
Status and Action Items
Issues: Library | Action Items | owner | comment | open date | close date | status
STD library update from snps |  | artosyn |  |  |  | open
OD library |  | artosyn |  |  |  | open
ECO DCAP | check DECAP_ECOCT difference with DECAP_ECO | artosyn |  |  |  | close
ABB LEF | t28_abb_top named B[*] placed at the bottom-right corner | artosyn |  |  |  | close
HPK library | no gds/cdl files | artosyn |  |  |  | close
OTP | how to gurantee 20pF capacitance | artosyn |  |  |  | close
STD library EO_0P5 cell have DRC |  | artosyn/VSI |  |  |  | close
Memory | memory lib is ecsm , not ccs | artosyn |  |  |  | close
Memory | no spice netlist | artosyn |  |  |  | close
Memory | update memory to use HVT , VSI check timing | artosyn/VSI |  |  |  | open
Issues: Tech File | Action Items | owner | comment | open date | close date | status
ITF/ICT/QRC/NXTgrd with "_T" | arotsyn to check with TSMC | artosyn |  |  |  | close
nxtgrd file |  | artosyn |  |  |  | close
spice model for IR drop |  | artosyn |  |  |  | close
Issues: Timing Signoff Creteria | Action Items | owner | comment | open date | close date | status
setup uncertainty | Artosyn to decide 50ps / 75ps(<800M) ?; | artosyn |  |  |  | close
USB 200ps setup uncertainty; hold 100ps hold uncertainty | provide clock name in flatten/top/sub1 SDC; 50ps for hold ? |  |  |  |  | open
MEM signoff library (ffbc or ff) | Artosyn to confirm use ff to signoff | artosyn |  |  |  | close
signoff std@ffbc and mem@ff ? | [5 empty] | close
Issues: NL/SDC/UPF by block | Action Items | owner | comment | open date | close date | status
Ceva core | reduce LVT pct , currently 23% | artosyn |  |  |  | VSI check ING
Ceva harden | PLL reset need pulse in scan mode, update model | artosyn | DFT |  |  | close
| PLL output 500M instead of 650M in scan mode | artosyn | DFT |  |  | VSI check ING
| adjust clock frequency from 800M to the achievable one | artosyn |  |  |  | VSI check ING
ceva subsys | clock freq overconstraint | artosyn |  |  |  | VSI check ING
| include constraint in harden | artosyn |  |  |  | VSI check ING
ceva subsys flatten | update flatten SDC | artosyn |  |  |  | VSI check ING
| flatten UPF | artosyn |  |  |  | VSI check ING
CA7 CORE | provide pre-syn UPF | artosyn |  |  |  | VSI check ING
| CA7_VDD_SW no port issue in UPF | VSI |  |  |  | open
| provide post-cts LVT pct | VSI |  |  |  | open
| LVT pct > 10% | artosyn |  |  |  | VSI check ING
ca7 harden | provide pre-syn UPF | artosyn |  |  |  | VSI check ING
| level shifter insert in analog/PG signal path : CEVA_AVSS_UPF_LS CEVA_AVDD_UPF_LS TS_SENSOR_IBEI_UPF_LS TS_SENSOR_RGND_UPF_LS | artosyn |  |  |  | open
| share bus MBIST debug | artosyn |  |  |  | open
| scan reset tie 0 and be optimized , DFF become constant in scan mode | artosyn | DFT |  |  | VSI check ING
| update netlist to add share-bus mbist reset control path | artosyn | DFT |  |  | open
| update netlist to meet share-bus mbist control requirement | artosyn | DFT |  |  | open
| DFT DRC: sirius_top/sirius_sub_ca7_inst/a7_subsystem_inst/u_a7_harden_subsystem/u_a7_cgu/u_cortexa7_clk/X (it exists in ‘occ_location.list’ you released, but we cannot get this pin in netlist) | artosyn | DFT |  |  | VSI check ING
ca7 subsys | provide pre-syn UPF | artosyn |  |  |  | VSI check ING
| update netlist to add share-bus mbist reset control path | artosyn |  |  |  | open
| axi clock freq 650M not consistent with clock diagram | artosyn |  |  |  | VSI check ING
ca7 subsys flatten | update flatten SDC | artosyn |  |  |  | VSI check ING
| flatten UPF | artosyn |  |  |  | VSI check ING
DDR | check DDR place timing | artosyn |  |  |  | VSI check ING
| add false path from ac_cfg_dtomode_reg | artosyn |  |  |  | VSI check ING
| don’t touch net in DDR implementation check list | artosyn |  |  |  | VSI check ING
SUB2 | DMAC move to top | artosyn |  |  |  | VSI check ING
SUB4 | sub4 module long name | artosyn |  |  |  | VSI check ING
sub1 | hold violation between clock groups mipi_top_inst/mipi_01/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and mipi_top_inst/mipi_01/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs | artosyn |  |  |  | VSI check ING
| hold violation between clock groups mipi_top_inst/mipi_23/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and 'mipi_top_inst/mipi_23/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs | artosyn |  |  |  | VSI check ING
sub3 | scan mode timing through pcie/tx0_state | VSI |  |  |  | VSI check ING
| DFT: Sub3 spdif_* regs clocks cannot be traced back to occ points. Please confirm whether they should be excluded from scan chains. Add fix buffer to add dedicated OCC , update clock diagram | artosyn | DFT |  |  | VSI check ING
| DFT: sub3 ‘mux synthesized to NOR gate’ recurred. cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_mclk_rstn/U1 cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_cdr_rstn/U1 | artosyn | DFT |  |  | VSI check ING
| TYPEC_DVDD_0P9 of TYPEC floating | artosyn |  |  |  | VSI check ING
| path between clock "usb3_top_inst_global_clk_150m" and " usb3_top_inst_FREECLK" is false or not | artosyn |  |  |  | VSI check ING
HEVC | power switch control signal off state require the AON invter | artosyn |  |  |  | VSI check ING
ISP | power switch control signal off state require the AON invter | artosyn |  |  |  | VSI check ING
| timing violation path if LVT don’t use | artosyn |  |  |  | open
| shorten module name | artosyn |  |  |  | VSI check ING
TOP | add port for OTP IO vdd18 | artosyn |  |  |  | close
| remove RGMI PVDD1ANARGM/PVSS1ANARGM IO | artosyn |  |  |  | close
| ABB/BB/TOP talk issues | artosyn |  |  |  | close
| pull Analog Power ports to top | artosyn |  |  |  | close
| connection between ABB to TS sensorconnection | artosyn |  |  |  | VSI check ING
| sub 1 clock mux not transparent | artosyn |  |  |  | close
| floating ports HDMI_CEC_PAD | artosyn |  |  |  | close
| full chip input transition/load | artosyn |  |  |  | close
| set IO driving strength /slew rate in SDC (check pin assignment) | artosyn |  |  |  | VSI check ING
| remove async groups for set_max delay | artosyn |  |  |  | VSI check ING
| trust zone pipeline (from sub2 through trust zone to sub2) | artosyn |  |  |  | VSI check ING
| trust zone pipeline (from sub2 through trust zone to DDR) | artosyn |  |  |  | VSI check ING
| IO timing violation | artosyn |  |  |  | VSI check ING
| use set_output_delay to constraint clock/data IO skew | artosyn |  |  |  | VSI check ING
| DVP IO through pin share module to DVP, need mux name to avoid detour | artosyn |  |  |  | close
| DVP IO through pin share module to SUB3, add multicycle | artosyn |  |  |  | VSI check ING
| clock divider reset share with test mode latch enable | artosyn | DFT |  |  | close
| DFT DRC: five unfixed muxex on the clock path for clock sirius_sub_1_inst/dvp0_clk_p and sirius_sub_1_inst/dvp1_clk_p | artosyn | DFT |  |  | VSI check ING
| DFT DRC: cannot be traced back to occ point for sirius_sub_3_inst/m7_i2s_sclk_out_dp | artosyn | DFT |  |  | VSI check ING
|  DFT DRC: sirius_sub_top_inst/gbeth_top_inst/i_gbeth_clk_div/mtx_125_MHz_i_reg/Q (please confirm whether it is a clock divider of CLK_CORE_GMAC, it drives thousands of regs. If so, please make sure its reset signal is controlled by an individual IO which is dedicated to reset divider regs). no OCC insertiion points in clock diagram | artosyn | DFT |  |  | VSI check ING
| clock divider reset do not have two pipeline register to de-X | artosyn | DFT |  |  | VSI check ING
| ca7 mbist sharebus reset controlled from IO | artosyn | DFT |  |  | open
| ISP to SUB2 timing violation | artosyn |  |  |  | open
| add generated clock on divider reg output pin even though they are not intended to propagate for CTS design rule purpose | artosyn |  |  |  | open
| check balance requirement of multi-input clock mux | artosyn |  |  |  | open
| timing path from regs through IO to regs | artosyn |  |  |  | close
flatten | UPF is not available | artosyn |  |  |  | open
| clock freqency consistency between block sdc and flatten sdc | artosyn |  |  |  | open
| SDC is not available | artosyn |  |  |  | open
Issues: SDC general | Action Items | owner | comment | open date | close date | status
set_max_delay use variable (NOC) |  | artosyn |  |  |  | open
clock period 6/6.66/6.67 in some block |  | artosyn |  |  |  | VSI check ING
remove clock frequency over-constraint |  | artosyn |  |  |  | VSI check ING
wrong clock frequency |  | artosyn |  |  |  | VSI check ING
Issues: clock diagram | Action Items | owner | comment | open date | close date | status
update full chip clock diagram | Artosyn adjust cgu to imprve at-speed clock frequency | artosyn |  |  |  | open
update full chip clock diagram | provide instance name list for clock divider | artosyn |  |  |  | open
provide sub1/sub2/sub3/sub4 clock diagram |  | artosyn | DFT/Timing |  |  | close
Issues: low power | Action Items | owner | comment | open date | close date | status
low power switch enable and isolation enable sequence configurable |  | artosyn |  |  |  | close
power switch control active 0 or 1 | artosyn to check | artosyn |  |  |  | open
Issues: ESD | Action Items | owner | comment | open date | close date | status
OTP CDM | Artosyn confirm OTP do not have CDM buffer requirement for both input/output | artosyn |  |  |  | close
PCIE CDM | Artosyn to confirm with SNPS about PCIE CDM requirement | artosyn |  |  |  | open
Issues: IP PG connection | Action Items | owner | comment | open date | close date | status
IP name: dwc_usb3_pads_sspx1_hspx1_ns VSS1/VSS2 connection | connected to SOC ground | artosyn |  |  |  | close
can dvdd/gnd of typeC connect to SOC VDD/VSS in SOC die ? |  | artosyn |  |  |  | open
can IP ground connect to SOC ground in package substrate and share same ball ? | lack of OTP/PLL_DDR/PLL_ARM/ABB/DDR | artosyn |  |  |  | open
Issues: Package | Action Items | owner | comment | open date | close date | status
signal name mismatch between pin_assignemnt and netlist | 如：AVDD1V8_MIPI和AGND_MIPI在网表里是叫MIPI_AVDD1V8和MIPI_AGND VREFI[*](pkg name “DDR_VREF*”)在网表里是VREFI_*_ GPIO_B0_4(pkg name “EMMC_PWR”)在网表里叫EMMC_PWR_PAD | artosyn |  |  |  | VSI check ING
SD/EMMC have two power domain, have seperated VDD18 IO , need seperatated pin name ; | Artosyn to check with TSMC | artosyn |  |  |  | VSI check ING
SD/EMMC require to have dedicated VDD18 ball for decap | Artosyn to check with TSMC | artosyn |  |  |  | VSI check ING
RGMII IO require to share same ball for different power pin | Artosyn to check with TSMC | artosyn |  |  |  | VSI check ING
OTP | no instance name of OTP IO in pin assignment | artosyn |  |  |  | VSI check ING
TYPEC ref clock tie which ground |  | artosyn |  |  |  | VSI check ING
define SSOG group |  | artosyn |  |  |  | VSI check ING
define slew rate and driving strength |  | artosyn |  |  |  | VSI check ING
swap USB and HDMI location in pin assignment due to bump rule |  | artosyn |  |  |  | open
Issues: physical guideline | Action Items | owner | comment | open date | close date | status
analog IP routing/placement keepout margin |  | artosyn |  |  |  | VSI check ING
don’t touch net list | Artosyn to provide don’t touch net list to VSI | artosyn |  |  |  | VSI check ING
Mask filed utilization |  | artosyn |  |  |  | close
Issues: dft | Action Items | owner | comment | open date | close date | status
Prepare testbench to check functionality of clock gen logic and confirm the clock frequency in scan_mode/mbist_mode. |  | artosyn | DFT |  |  | open
clock diagram / block sdc/ flatten SDC frequency consistency |  | artosyn | DFT |  |  | open
at speed dft clock frequncy higher than function | check excel sheet | artosyn | DFT |  |  | VSI check ING
at speed dft clock frequncy lower than function |  | artosyn | DFT |  |  | VSI check ING
reset signal need double-sync before reach to CGU in scan¦mbist mode. |  | artosyn | DFT |  |  | VSI check ING
2. Don’t share OCC for clock groups which is async in function mode even they have same frequency , add fix buffer to split and mark in clock diagram . |  | artosyn | DFT |  |  | VSI check ING