## Action Items
Status and Action Items
Issues: Library | Action Items | owner | comment | open date | close date | status
STD library update from snps |  | artosyn |  |  |  | open
OD library |  | artosyn |  |  |  | open
ECO DCAP | check DECAP_ECOCT difference with DECAP_ECO | artosyn |  |  |  | close
ABB LEF | t28_abb_top named B[*] placed at the bottom-right corner | artosyn |  |  |  | close
HPK library | no gds/cdl files | artosyn |  |  |  | close
OTP | how to gurantee 20pF capacitance | artosyn |  |  |  | close
STD library EO_0P5 cell have DRC |  | artosyn/VSI |  |  |  | close
Memory | memory lib is ecsm , not ccs | artosyn |  |  |  | close
Memory | no spice netlist | artosyn |  |  |  | close
Memory | update memory to use HVT , VSI check timing | artosyn/VSI |  |  |  | close
Memory | update ecsm to ccs, timing delay change, many setup violation | artosyn |  |  |  | close
clock gating cell | V5 and V7 difference | artosyn |  |  |  | close
ABB | LEF/lib pin mismatch | artosyn |  |  |  | close
7T library | no ICG library cell designed for falling edge triggered flop | artosyn |  |  |  | close
OTP | no cdl | artosyn |  |  |  | open
Memory VT swap | ISP , use RVT 0608 version HEVC (VSI change to RVT at this moment, Artosyn to justify which one can be replaced to HVT) , use RVT 0610 version H264_SR_1P_6656X128B1PG in sub2, use RVT 0610 version VIF in sub1 released in 0608 version for sub1 floorplan add new SMMU memory in 0616 release; update HEVC library 0627 | artosyn |  |  |  | open
Issues: Tech File | Action Items | owner | comment | open date | close date | status
ITF/ICT/QRC/NXTgrd with "_T" | arotsyn to check with TSMC | artosyn |  |  |  | close
nxtgrd file |  | artosyn |  |  |  | close
spice model for IR drop |  | artosyn |  |  |  | close
Issues: Timing Signoff Creteria | Action Items | owner | comment | open date | close date | status
setup uncertainty | Artosyn to decide 50ps / 75ps(<800M) ?; | artosyn |  |  |  | close
USB 200ps setup uncertainty; hold 100ps hold uncertainty | provide clock name in flatten/top/sub1 SDC; 100ps for hold |  |  |  |  | close
inter-clock uncertainty between post-PLL clocks and ddr clocks |  | artosyn |  |  |  | close
MEM signoff library (ffbc or ff) | Artosyn to confirm use ff to signoff | artosyn |  |  |  | close
signoff std@ffbc and mem@ff ? | [5 empty] | close
Issues: NL/SDC/UPF by block | Action Items | owner | comment | open date | close date | status
Ceva core | reduce LVT pct , currently 23% | artosyn |  |  |  | close
| Formal pass ? |  |  |  |  | close
| two POK ICG cells in netlist | artosyn |  |  |  | close
Ceva harden | PLL reset need pulse in scan mode, update model | artosyn | DFT |  |  | close
| PLL output 500M instead of 650M in scan mode | artosyn | DFT |  |  | close
| MMU timing violation analyze | artosyn |  |  |  | close
| adjust clock frequency from 800M to the achievable one | artosyn |  |  |  | close
ceva subsys | clock freq overconstraint | artosyn |  |  |  | close
| include constraint in harden | artosyn |  |  |  | close
ceva subsys flatten | update flatten SDC | artosyn |  |  |  | close
| flatten UPF | artosyn |  |  |  | close
CA7 CORE | provide pre-syn UPF | artosyn |  |  |  | close
| CA7_VDD_SW no port issue in UPF | VSI |  |  |  | close
| provide post-cts LVT pct | VSI |  |  |  | close
| LVT pct > 10% | artosyn |  |  |  | close
ca7 harden | provide pre-syn UPF | artosyn |  |  |  | close
| level shifter insert in analog/PG signal path : CEVA_AVSS_UPF_LS CEVA_AVDD_UPF_LS TS_SENSOR_IBEI_UPF_LS TS_SENSOR_RGND_UPF_LS | artosyn |  |  |  | close
| share bus MBIST debug | artosyn |  |  |  | open
| interface pin > 6000, congestion issues | artosyn |  |  |  | close
| scan reset tie 0 and be optimized , DFF become constant in scan mode | artosyn | DFT |  |  | close
| update netlist to add share-bus mbist reset control path | artosyn | DFT |  |  | close
| update netlist to meet share-bus mbist control requirement | artosyn | DFT |  |  | close
| provide analog pin/power pin list of TS/PVT/ARM_PLL/DDR_PLL for lvl/iso check | artosyn |  |  |  | close
| DFT DRC: sirius_top/sirius_sub_ca7_inst/a7_subsystem_inst/u_a7_harden_subsystem/u_a7_cgu/u_cortexa7_clk/X (it exists in ‘occ_location.list’ you released, but we cannot get this pin in netlist) | artosyn | DFT |  |  | close
ca7 subsys | provide pre-syn UPF | artosyn |  |  |  | close
| update netlist to add share-bus mbist reset control path | artosyn |  |  |  | close
| axi clock freq 650M not consistent with clock diagram | artosyn |  |  |  | close
ca7 subsys flatten | update flatten SDC | artosyn |  |  |  | close
| flatten UPF | artosyn |  |  |  | close
DDR | check DDR place timing | artosyn |  |  |  | close
| DATA X8 PHY q/q_e pin access issue due to PLL abut | artosyn |  |  |  | close
| add false path from ac_cfg_dtomode_reg | artosyn |  |  |  | close
| version 2 netlist | artosyn |  |  |  | close
| skew balance requirement | artosyn |  |  |  | close
| 900m maximum, add buffer? | artosyn |  |  |  | open
| skew report example |  |  |  |  | close
| skew based on non-SI report? |  |  |  |  | open
| Only skew group: ck_dqs is doing cross-lane skew check, comparing the skew between CK/CK# and all DQS/DQS#. The other skew check is only compared within the lane. The original requirement for ck_dqs is to compare from the system PLL output to the pad DOUT pins, 8% tCK. If this is too hard to meet, the start-point can also be relaxed at the AC/DX output |  |  |  |  | open
| check max delay to zctrl* is 4 cfg or 5 clock cycle and covererd in SDC | artosyn |  |  |  | open
The I/O order should align with the PHY macro pins to avoid crossing routes (especially in the CA lane). The define file provides a description of command and address lane signal assignments which, at the RTL stage, can be adjusted to match the I/O ring order. Please avoid cross-routing in your floorplan, or check DWC_AC_xxx_PNUM parameters from DWC_DDRPHY_define.v with the IO ring spreadsheet: report_PHY.csv
| io ring review to check PVREF to decide may delay or skew check apply for zctrl check | artosyn |  |  |  | open
| formal pass ? | artosyn |  |  |  | close
| set false path for clock gating hold violation | artosyn |  | 2017-06-20 |  | close
| don’t touch net in DDR implementation check list | artosyn |  |  |  | close
| use LVT to do CTS (to reduce SI effect ) | VSI |  |  |  | open
| UPF isolation rule define for top domain , should define for core domain | artosyn |  |  |  | open
HEVC | set_disable_timing [get_cells -h uHEVC_RF_2P_* -f "is_hierarchical==false"] -from CLKA -to CLKB set_disable_timing [get_cells -h uHEVC_RF_2P_* -f "is_hierarchical==false"] -from CLKB -to CLKA | artosyn |  |  |  | close
SUB2 | release SDC to waive memory(HVT) LS timing violation | artosyn |  |  |  | close
| MMU timing violation analyze | artosyn |  |  |  | close
| sub2 memory LS pin violation | artosyn |  |  |  | close
| set_disable_timing [get_cells -h* -f "is_hierarchical==false"] -from CLKA -to CLKB | artosyn |  |  |  | close
| DMAC move to top | artosyn |  |  |  | close
SUB4 | release SDC to waive memory(HVT) LS timing violation | artosyn |  |  |  | close
| check OTP interface timing is constrained based on ETM | VSI |  |  |  | open
| sub4 timing violation (not found in block but found in flatten, async in block but sync check in flatten?) | VSI |  |  |  | open
| sub4 module long name | artosyn |  |  |  | close
sub1 | hold violation between clock groups mipi_top_inst/mipi_01/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and mipi_top_inst/mipi_01/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs | artosyn |  |  |  | close
| need memory shape adjustment for floorplan | artosyn |  |  |  | close
| sub1 memory LS pin violation | artosyn |  |  |  | close
| set_clock_groups -name xxx -asynchronous -group [get_clocks CGU_CLK_CFG_TYPEC] -group [get_clocks cdn_typec_subsystem_top_inst_utmi_clk_60mhz] | artosyn |  |  |  | open
| hold violation between clock groups mipi_top_inst/mipi_23/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs and 'mipi_top_inst/mipi_23/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs |  |  |  |  | close
sub3 | scan mode timing through pcie/tx0_state | VSI |  |  |  | close
| evaluate memory size change TYPC_SR_1P_12288X32PG: 262.0000 x 327.0000 TYPC_SR_1P_6144X32B1PG: 155.6000 x 327.0000 TYPC_SR_1P_16384X32PG : 331.2000 x 327.0000 TYPC_SR_1P_16384X32B1PG : 331.2000 x 327.0000 |  |  |  |  | open
| add “set_clock_groups -name xxx -asynchronous -group {mipi_video_clk} -group \ [list [get_clocks mipi_top_inst/mipi_01/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_01/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_23/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_23/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_45/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_45/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_67/u_phy_0/I01DPHY/I01DPHYCORE/rxbyteclkhs] \ [get_clocks mipi_top_inst/mipi_67/u_phy_1/I01DPHY/I01DPHYCORE/rxbyteclkhs]]” |  |  |  |  | open
| DFT: Sub3 spdif_* regs clocks cannot be traced back to occ points. Please confirm whether they should be excluded from scan chains. Add fix buffer to add dedicated OCC , update clock diagram | artosyn | DFT |  |  | close
| DFT: sub3 ‘mux synthesized to NOR gate’ recurred. cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_mclk_rstn/U1 cdn_typec_subsystem_top_inst/u_ats_source_mhdp_core_mem/source_mhdp_core_top_i/source_car_i/rst_mux_spdif_cdr_rstn/U1 | artosyn | DFT |  |  | close
| There may be a typo in pin name for TYPEC shielding pin. In the document ,the pin name is sirius_sub_3_inst/cdn_typec_subsystem_top_inst/u_cdnsusbss_drd_ips/u_cdnsusbss_drd_phy/u_sdtc01cay_t28hpc_4t2r_vf180_6020/u_pma/cmn_ref_clk_i there is no such pin, but have the sirius_sub_3_inst/cdn_typec_subsystem_top_inst/u_cdnsusbss_drd_ips/u_cdnsusbss_drd_phy/u_sdtc01cay_t28hpc_4t2r_vf180_6020/u_pma/cmn_ref_clk_int |  |  |  |  | open
| TYPEC_DVDD_0P9 of TYPEC floating | artosyn |  |  |  | close
| path between clock "usb3_top_inst_global_clk_150m" and " usb3_top_inst_FREECLK" is false or not | artosyn |  |  |  | close
HEVC | justify which memory can be changed to HVT (VSI use RVT now) |  |  |  |  | open
| power switch control signal off state require the AON invter | artosyn |  |  |  | close
ISP | power switch control signal off state require the AON invter | artosyn |  |  |  | close
| false path set for timing path between sram_top_inst_noc_clk and sram_top_inst_bb_clk | artosyn |  |  |  | close
| release SDC to waive memory(HVT) LS timing violation | artosyn |  |  |  | close
| provide ISP data flow | artosyn |  |  |  | close
| check ISP LVT percentage in synthesis netlist (5%) | artosyn |  |  |  | open
| timing violation path if LVT don’t use | artosyn |  |  |  | close
| buf reg congestion issue | VSI |  |  |  | open
| IO timing violation from isolation control port should be set false path | artosyn |  |  |  | close
| UPF isolation rule define for top domain , should define for core domain | artosyn |  |  |  | open
| shorten module name | artosyn |  |  |  | close
TOP | add port for OTP IO vdd18 | artosyn |  |  |  | close
| remove RGMI PVDD1ANARGM/PVSS1ANARGM IO | artosyn |  |  |  | close
| ABB/BB/TOP talk issues | artosyn |  |  |  | close
| pull Analog Power ports to top | artosyn |  |  |  | close
| connection between ABB to TS sensorconnection | artosyn |  |  |  | close
| sub 1 clock mux not transparent | artosyn |  |  |  | close
| floating ports HDMI_CEC_PAD | artosyn |  |  |  | close
| full chip input transition/load | artosyn |  |  |  | close
| set IO driving strength /slew rate in SDC (check pin assignment) | artosyn |  |  |  | close
| remove async groups for set_max delay | artosyn |  |  |  | close
| trust zone pipeline (from sub2 through trust zone to sub2) | artosyn |  |  |  | close
| trust zone pipeline (from sub2 through trust zone to DDR) | artosyn |  |  |  | close
| IO timing violation | artosyn |  |  |  | close
| use set_output_delay to constraint clock/data IO skew | artosyn |  |  |  | close
| DVP IO through pin share module to DVP, need mux name to avoid detour | artosyn |  |  |  | close
| DVP IO through pin share module to SUB3, add multicycle | artosyn |  |  |  | close
| clock divider reset share with test mode latch enable | artosyn | DFT |  |  | close
| DFT DRC: five unfixed muxex on the clock path for clock sirius_sub_1_inst/dvp0_clk_p and sirius_sub_1_inst/dvp1_clk_p | artosyn | DFT |  |  | close
| DFT DRC: cannot be traced back to occ point for sirius_sub_3_inst/m7_i2s_sclk_out_dp | artosyn | DFT |  |  | close
|  DFT DRC: sirius_sub_top_inst/gbeth_top_inst/i_gbeth_clk_div/mtx_125_MHz_i_reg/Q (please confirm whether it is a clock divider of CLK_CORE_GMAC, it drives thousands of regs. If so, please make sure its reset signal is controlled by an individual IO which is dedicated to reset divider regs). no OCC insertiion points in clock diagram | artosyn | DFT |  |  | close
| clock divider reset do not have two pipeline register to de-X | artosyn | DFT |  |  | close
| ca7 mbist sharebus reset controlled from IO | artosyn | DFT |  |  | close
| ISP to SUB2 timing violation | artosyn |  |  |  | close
| ISP to top timing , try to improve ISP IO timing | artosyn |  |  |  | open
| add generated clock on divider reg output pin even though they are not intended to propagate for CTS design rule purpose | artosyn |  |  |  | open
| check balance requirement of multi-input clock mux | artosyn |  |  |  | close
| provide AHB interface module name of SD controller, it will be placed close to NOC | artosyn |  |  |  | close
| add retiming/pipeline for ISP/sub2, M7 timing | artosyn |  |  |  | close
| timing path from regs through IO to regs | artosyn |  |  |  | close
flatten | UPF is not available | artosyn |  |  |  | close
| switch-off power net name need to be aligned between UPF |  |  |  |  | open
| clock freqency consistency between block sdc and flatten sdc | artosyn |  |  |  | open
| interface constraint consistency between block sdc and flatten sdc | artosyn |  |  |  | open
| SDC is not available | artosyn |  |  |  | close
| many hold violations | artosyn |  |  |  | open
| uniquify module name between blocks | artosyn |  |  |  | close
| false path for async clocks groups | artosyn |  |  |  | close
| ca7 memory min period violation | artosyn |  |  |  | close
Issues: SDC general | Action Items | owner | comment | open date | close date | status
set_max_delay use variable (NOC) |  | artosyn |  |  |  | close
clock period 6/6.66/6.67 in some block |  | artosyn |  |  |  | VSI check ING
remove clock frequency over-constraint |  | artosyn |  |  |  | VSI check ING
wrong clock frequency |  | artosyn |  |  |  | VSI check ING
Issues: clock diagram | Action Items | owner | comment | open date | close date | status
update full chip clock diagram | Artosyn adjust cgu to imprve at-speed clock frequency | artosyn |  |  |  | close
update full chip clock diagram | provide instance name list for clock divider | artosyn |  |  |  | close
provide sub1/sub2/sub3/sub4 clock diagram |  | artosyn | DFT/Timing |  |  | close
privide clock sync group |  | artosyn |  |  |  | close
Issues: low power | Action Items | owner | comment | open date | close date | status
low power switch enable and isolation enable sequence configurable |  | artosyn |  |  |  | close
power switch control active 0 or 1 | artosyn to check | artosyn |  |  |  | close
UPF files from VSI need confirm |  | artosyn |  |  |  | open
Issues: ESD | Action Items | owner | comment | open date | close date | status
OTP CDM | Artosyn confirm OTP do not have CDM buffer requirement for both input/output | artosyn |  |  |  | close
PCIE CDM | Artosyn to confirm with SNPS about PCIE CDM requirement | artosyn |  |  |  | close
Issues: IP PG connection | Action Items | owner | comment | open date | close date | status
IP name: dwc_usb3_pads_sspx1_hspx1_ns VSS1/VSS2 connection | connected to SOC ground | artosyn |  |  |  | close
can dvdd/gnd of typeC connect to SOC VDD/VSS in SOC die ? |  | artosyn |  |  |  | close
can IP ground connect to SOC ground in package substrate and share same ball ? | lack of OTP/PLL_DDR/PLL_ARM/ABB/DDR | artosyn |  |  |  | close
pvt_osc_abs_top in ceva_harden/ca7_harden PG connect to OD power ? |  | artosyn |  |  |  | close
Issues: Package | Action Items | owner | comment | open date | close date | status
signal name mismatch between pin_assignemnt and netlist | 如：AVDD1V8_MIPI和AGND_MIPI在网表里是叫MIPI_AVDD1V8和MIPI_AGND VREFI[*](pkg name “DDR_VREF*”)在网表里是VREFI_*_ GPIO_B0_4(pkg name “EMMC_PWR”)在网表里叫EMMC_PWR_PAD | artosyn |  |  |  | close
SD/EMMC have two power domain, have seperated VDD18 IO , need seperatated pin name ; | Artosyn to check with TSMC | artosyn |  |  |  | close
SD/EMMC require to have dedicated VDD18 ball for decap | 1. For SD/EMMC, in same domain, same cells can share a bump if Current was enough. 2. For PVDD18SD in SD/EMMC, both PVDD18SD in same domain also share the same bump and ball. | artosyn |  |  |  | close
RGMII IO require to share same ball for different power pin | Artosyn to check with TSMC | artosyn |  |  |  | close
OTP | no instance name of OTP IO in pin assignment | artosyn |  |  |  | close
TYPEC ref clock tie which ground |  | artosyn |  |  |  | VSI check ING
define SSOG group |  | artosyn |  |  |  | VSI check ING
define slew rate and driving strength |  | artosyn |  |  |  | VSI check ING
swap USB and HDMI location in pin assignment due to bump rule |  | artosyn |  |  |  | close
ABB ball number > 1 for some bump | artosyn provide ball number requirement | artosyn |  |  |  | open
IP (DDR) bump review |  | artosyn |  |  |  | open
EMMC/SD/RGM IO-bump ratio |  | artosyn |  |  |  | close
MIPI different PHY bump name should be different because they are seperated in layout |  | artosyn |  |  |  | open
the different mipi PYH can share one ball |  | artosyn |  |  |  | close
Issues: physical guideline | Action Items | owner | comment | open date | close date | status
analog IP routing/placement keepout margin |  | artosyn |  |  |  | VSI check ING
don’t touch net list | Artosyn to provide don’t touch net list to VSI | artosyn |  |  |  | VSI check ING
Mask filed utilization |  | artosyn |  |  |  | close
use RVT for clock tree synthsis and use RVT ICG |  | VSI |  |  |  | close
abb wrapper hardening |  | artosyn |  |  |  | open
Issues: dft | Action Items | owner | comment | open date | close date | status
Prepare testbench to check functionality of clock gen logic and confirm the clock frequency in scan_mode/mbist_mode. |  | artosyn | DFT |  |  | open
clock diagram / block sdc/ flatten SDC frequency consistency |  | artosyn | DFT |  |  | open
at speed dft clock frequncy higher than function | check excel sheet | artosyn | DFT |  |  | VSI check ING
at speed dft clock frequncy lower than function |  | artosyn | DFT |  |  | VSI check ING
reset signal need double-sync before reach to CGU in scan¦mbist mode. |  | artosyn | DFT |  |  | VSI check ING
2. Don’t share OCC for clock groups which is async in function mode even they have same frequency , add fix buffer to split and mark in clock diagram . |  | artosyn | DFT |  |  | VSI check ING
typeC PHY macro | 1. The TypeC PMA macro netlist for simulation consists of standard cells of TSMC model which verilog cannot be found. Thus we cannot carry out simulation. Could you provide? |  |  |  |  | open
| 2. How can we carry out at-speed scan test for PMA macro? Is there any guide? |  |  |  |  | open
| 3. We find some pins like ‘cmn_scan_pll_ats’, about which the doc claims ‘can be used to generate the scan at-speed capture clocks’. Does it mean there are embedded PLLs? What if we do NOT want to use them? Is there any existing bypass logic? How to enter the bypass mode? |  |  |  |  | open
| 4. We find there are lots of clock ports of PMA macro used to carry out DC (low speed) scan test. But we are not aware of their internal clock tree latency, so that we cannot balance the clock trees at the full chip level. If some of them need balancing, the post-layout simulation will probably fail. So could you provide the netlist+sdc+spef with us, so that we can signoff the whole chip timing with PMA internal information? Or could you share your solution to solve this potential problem? |  |  |  |  | open
Issues: IR drop | Action Items | owner | comment | open date | close date | status
toggle rate | [5 empty] | open
library corner : tt85 | [5 empty] | open