## Sheet1
No | IP | pr person name | status | problem
1 | Sub_CA7 | Yongcheng | 4 setupt and 14 hold corner are almost timing clean. | DRC is not clean. Few short, need to fix.
2 | SUB_CEVA | Fangxiang
3 | DDR_TOP | Liangwei
4 | ISP_TOP | Guishuai | Waiting for new netlist. Post route based on old netlist. Checking netlist. | No problem. Timing and congestion is ok.
5 | BB_TOP | Wang Long
6 | HEVC | Wang Qing | fix timing in pt. DRC is under control, it appears at routing. Number is not big. | setup timing violation is a little big. Congestion is a problem. WNS is a little big.
7 | SUB_1 | Yi Xin
8 | SUB_2 | Xu Zhi Bin | fix timing in pt. DRC is under control, it appears at routing. Number is not big. | timing violation is under control. May use few LVT cells to fix timing. Not bigger than 1%.
9 | SUB_3 | Xu Zhi Bin | fix timing in pt.
10 | SUB_4 | Guishuai | fix timing in pt. | timing violation is under control, may use LVT to fix ctritical timing path. No LVT now.
11 | SUB_TOP | Yun Qing | CTS is on going based on new netlist. DRC appears at routing, not at lib cell. | No problem.
12 | DFT/MBIST | Chengyu, Huhao, Yiying | DFT/MBIST insert, simulation is on going, netlist and sdc are released | Share bus mbist debug. Simulation is on going.
13 | STA | Chen Xi
14 | Physical | Qiuhua
15 | Package | Daisy Lee