## IP checklist PCIE
| Sub-CLASS | Items | Description | Status | Comment
IP/Subsytem Checklist | Document | IP Release Note | Describes the content of IP package,and the updates to last version. | done | DWC_ddr_umctl2_relnotes.pdf
dwc_ddr4_multiphy_tsmc28hpc18_databook.pdf
|  | IP datasheet | Must include full register map and description, I/O structures, block description and sub IP partitioning. | done | DWC_ddr_umctl2_databook.pdf
dwc_ddr4_multiphy_tsmc28hpc18_databook.pdf
|  | IP DFT/ATE test spec (mostly for AMS IPs) | Must define what it contains (must include description of test protocol for special test modes) | pending
|  | IP integration Manual | Requiremnt for IO/Clock/Rest/DFT; IP block digarm; Port descriptions and connections in SOC | done
|  | IP verfication spec and report | Bench and test cases descriptions; code coverage; functional coverage | pending | code coverage and functional coverage ???
|  | IP programing guide | Description of IP bring up, Register settings for different modes | done | DWC_ddr_umctl2_user.pdf
|  | IP data flow /floorplan/TOP diagram | Description of connections among sub-blocks, memories, backend floorplan | done | dwc_ddr4_multiphy_tsmc28hpc18_databook.pdf
|  | IP package/PCB guide | Description of Ball assignment/PCB layout | done | dwc_ddr4_multiphy_ig.pdf
| Design | IP configure | Include IP feature configure | done
|  | RTL | RTL code, netlist, behavior models | done | 1
|  | Design File List | File list for Chip test bench build. | done
|  | Memory list | Memory configure list | done
|  | IP fake model | dummy IP subsystem top | done
|  | IP unit verification environment | Bench,test cases, scripts ,logs, coverage reports, failed case,issue | pending | coverage reports?????
|  | IP synthesis environment | Scripts,SDC,netlist,logs, report | done
|  | IP Formal check environment | Scripts, report | done
|  | IP ATPG environment | Scripts, report | pending
|  | IP verification Plan | Include SOC level/Veloce/FPGA verification test report. | pending
|  | IP NLS Maturity Check | release netlist, chiplevel backend SDC | pending
| Software | IP SW driver | Software driver for application | pending

## IP owner list
No | 3rd Party IP name | owner | support expired date | Status | Comment
1 | USB | Hao Sun | 1/25/2017
2 | PCIe20 | Jiajie Zhang | 1/25/2017
3 | MIPI | Zheng Xie | 1/25/2017
4 | HDMI/HDCP | Huibo Zhong | 1/25/2017
5 | TYPEC | Jingfeng Huang | 1/25/2017
6 | DDR4/MultiPHY/ECC | Ji Ma | 6/20/2017
7 | DMAC-AXI | LeiYang | 5/21/2017
8 | tRoot/TRNG/PKA/SPAcc | Hao Sun | 5/21/2017
9 | eMMC | LeiYang
10 | GMAC | LeiYang
11 | NOC | Weiwei Shen
12 | SMMU-500 | Peng Cheng | 11/7/2017
13 | CS ETM-A7 | Hao Zhang | 11/7/2017
14 | ADB-400 | Peng Cheng | 11/7/2017
15 | TZC-400 | Hao Zhang | 11/7/2017
16 | CCI-400 | Peng Cheng | expired
17 | Cortext-A7/FPU/NEON | Peng Cheng | expired
18 | M7 with FPU | Hao zhang | expired
19 | CS SoC-400 | Hao zhang | expired
20 | CEVA | Cong Liu
21 | OTP | Weiwei Shen
22 | TSMC IO | Yi Li
23 | SYNOPSYS LIB/MEM | Yi Li