## IP checklist PCIE
| Sub-CLASS | Items | Description | Status | Comment
IP/Subsytem Checklist | Document | IP Release Note | Describes the content of IP package,and the updates to last version. | done | core - 4.90a, phy - June 3 2016
|  | IP datasheet | Must include full register map and description, I/O structures, block description and sub IP partitioning. | done | DWC_pcie_dm_databook, DWC_pcie_dm_registers dwc_pcie2_phy_tsmc28hpc_09V18V_databook
|  | IP DFT/ATE test spec (mostly for AMS IPs) | Must define what it contains (must include description of test protocol for special test modes) | done
|  | IP integration Manual | Requiremnt for IO/Clock/Rest/DFT; IP block digarm; Port descriptions and connections in SOC | done
|  | IP verfication spec and report | Bench and test cases descriptions; code coverage; functional coverage | pending | no code coverage and functional coverage by synopsys, case 8000976465
|  | IP programing guide | Description of IP bring up, Register settings for different modes | pending | Simple guide in databook, case 8000976477
|  | IP data flow /floorplan/TOP diagram | Description of connections among sub-blocks, memories, backend floorplan | done
|  | IP package/PCB guide | Description of Ball assignment/PCB layout | pending | no PCB layout, double check in case 8000975965
| Design | IP configure | Include IP feature configure | done
|  | RTL | RTL code, netlist, behavior models | pending | top formality debugging
|  | Design File List | File list for Chip test bench build. | done
|  | Memory list | Memory configure list | done
|  | IP fake model | dummy IP subsystem top | done
|  | IP unit verification environment | Bench,test cases, scripts ,logs, coverage reports, failed case,issue | done
|  | IP synthesis environment | Scripts,SDC,netlist,logs, report | pending | formality failure
|  | IP Formal check environment | Scripts, report | pending | failure debugging
|  | IP ATPG environment | Scripts, report | pending | only phy
|  | IP verification Plan | Include SOC level/Veloce/FPGA verification test report. | pending | only have one soc level test passed
|  | IP NLS Maturity Check | release netlist, chiplevel backend SDC | pending
| Software | IP SW driver | Software driver for application | pending | only linux driver, case 8000936062

## IP owner list
No | 3rd Party IP name | owner | support expired date | Status | Comment
1 | USB | Hao Sun | 1/25/2017
2 | PCIe20 | Jiajie Zhang | 1/25/2017
3 | MIPI | Zheng Xie | 1/25/2017
4 | HDMI/HDCP | Huibo Zhong | 1/25/2017
5 | TYPEC | Jingfeng Huang | 1/25/2017
6 | DDR4/MultiPHY/ECC | Ji Ma | 6/20/2017
7 | DMAC-AXI | LeiYang | 5/21/2017
8 | tRoot/TRNG/PKA/SPAcc | Hao Sun | 5/21/2017
9 | eMMC | LeiYang
10 | GMAC | LeiYang
11 | NOC | Weiwei Shen
12 | SMMU-500 | Peng Cheng | 11/7/2017
13 | CS ETM-A7 | Hao Zhang | 11/7/2017
14 | ADB-400 | Peng Cheng | 11/7/2017
15 | TZC-400 | Hao Zhang | 11/7/2017
16 | CCI-400 | Peng Cheng | expired
17 | Cortext-A7/FPU/NEON | Peng Cheng | expired
18 | M7 with FPU | Hao zhang | expired
19 | CS SoC-400 | Hao zhang | expired
20 | CEVA | Cong Liu
21 | OTP | Weiwei Shen
22 | TSMC IO | Yi Li
23 | SYNOPSYS LIB/MEM | Yi Li

## PCIe checklist
1. For parameter config of pcie controller, mostly default value by synopsys is ok, like function_num, max_payload, vitural_channel, etc.
2. phy内部的状态也建议用apb读，而不仅仅依靠cr access; cr access 也挂在apb
3. pcie top registers, 尽可能足够的status以及input可控, 与controller/ phy异步
4. core和phy的reset分开, 方便phy的config和reset
5. hot-plug, prsnt#给cpu，软件做保护; perst#做mux，controller可选择reset; clkreq#在capability关掉; app_ltssm_enable在phy ready的时候才置起
6. 建议不配rombar或者改宏定义
7. RC可参考三星在Linux中的synopsys specific driver
8. verification中scrambler disable, 方便debug, 查看vip_trans.log / vip_symble.log
9. hot-plug在chip测试的时候注意插拔间隔时间过短可能引起问题
10. link_up（~link_down） and link_status作为interrupt
11. ref clk for phy的jitter要保证，alt和io的ref clk不能同时动，要tie住一个
12. 建议pcie做harden, 方便后仿，方便si pi仿真
13. 大数据量压phy仿真
14. sdc需要review （曾发现错误）, 尽量用clock_group, pcs和phy之间的timing特别注意，多做后仿
15. 利用pcie vip做仿真, 跑通所有test并check waveform, 特别是physical layer tests. pm tests low priority
16. gds review
17. dft 建议提前try
18. veloce mentor support
19. 所有interrupt寄存器可读，gic接收interrupt数量精简，cpu通过寄存器确定哪种中断
20. ate test先都跑起来，后面再确定chip测试选哪些
21. msi/ msix建议都配，msix在windows会配
22. iatu, dma 配置需要和同事check
23. backend / package/ board 有另外的同事share