## Sheet1
No | IP | module name | Pre Gloden RTL release | Pre Golden NLS/SDC release | fm status | sign off | date | release status (nls+sdc)
1 | dft_module/MBIST/Package | VSI
2 | CHIP_TOP | zhuoxu | by 4/14/2017 | n.a.
3 | IO SHARE | hzhang | OK | by 4/16/2017 |  |  | 2017-04-16 | done
4 | CGU/RGU/TOP_REG | jjzhang | by 4/13/2017 | by 4/16/2017 |  |  | 2017-04-16 | done
5 | ABB_TOP(analog/PLL) | yyuan | .v/.lib by 4/12/2017 .lef by 4/15/2017 | n.a. |  |  | 2017-04-12 | done
6 | A7_SUB_SYS | pchen | OK | by 4/15/2017 upf need delay |  |  | 2017-04-14 | done
7 | CCI/Boot_ROM/DVM_repeater | pchen | OK | OK(check) |  |  | 2017-04-14 | done
8 | CEVA_SUB_SYS | cliu | OK | by 4/15/2017 |  |  | 2017-04-14 | done
9 | M7_Peri | hzhang | OK | by 4/16/2017 |  |  | 2017-04-16 | done
10 | M7_core | hzhang | OK | by 4/16/2017 |  |  | 2017-04-16 | done
11 | CS | hzhang | OK | OK( check) |  |  | 2017-04-16 | done
12 | TZC400 | hzhang | OK | OK( check) |  |  | 2017-04-16 | done
13 | SMMU(VIDEO/DSP) | pchen | by 4/13/2017 | by 4/15/2017 |  |  | 2017-04-14 | done
14 | NOC | wwshen | by 4/13/2017 | by 4/15/2017 |  |  | 2017-04-14 | done
15 | DDR_TOP | jma | OK | by 4/15/2017 |  |  | 2017-04-16 | done
16 | USB30_TOP | hsun | by 4/12/2017 | by 4/15/2017 |  |  | 2017-04-16 | done
17 | TYPC_TOP | jfhuang | OK | by 4/14/2017 |  |  | 2017-04-14 | done
18 | PCIE_TOP | jjzhang | OK | by 4/15/2017 |  |  | 2017-04-16 | done
19 | HDMI_RX_TOP | hbzhong | by 4/12/2017 | by 4/15/2017 |  |  | 2017-04-14 | done
20 | MIPI_RX_TOP/TX | zxie | OK | by 4/15/2017 |  |  | 2017-04-15 | done
21 | GMAC_TOP | lyang | OK | by 4/15/2017 |  |  | 2017-04-14 | done
22 | eMMC_TOP | lyang | OK | by 4/15/2017 |  |  | 2017-04-14 | done
23 | ISP_TOP | huawang | OK | by 4/16/2017
24 | Video_IF(DVP) | zxie | OK | by 4/15/2017 |  |  | 2017-04-15 | done
25 | BB_TOP | zhengli | mem need confirm. | by 4/16/2017
26 | DMAC-TOP | lyang | OK | OK( check) |  |  | 2017-04-14 | done
27 | DMAC-CEVA | lyang | OK | OK( check) |  |  | 2017-04-14 | done
28 | SRAM_TOP | lyang | OK | by 4/15/2017 |  |  | 2017-04-14 | done
29 | Sec_sub_system | hsun | by 4/13/2017 | by 4/15/2017 |  |  | 2017-04-16 | done
30 | OTP_CTRL | wwshen | OK | by 4/15/2017 |  |  | 2017-04-16 | done
31 | HEVC_TOP | zqchen | by 4/12/2017 | by 4/17/2017
32 | H264_TOP | zqchen | by 4/12/2017 | by 4/15/2017
33 | JPEG_TOP | zqchen | OK | by 4/15/2017
34 | DISP_TOP | zqchen | by 4/12/2017 | by 4/15/2017