## History
no | date | history | owner
1 | 2016-10-19 | initial | pan song
2 | 2016-10-21 | v0.1 | pan song
3 | 2017-01-23 | v0.2 | pan song

## Veloce Test Case
Group | No | priority | veloce test item | test Description | Comments | Status
SOC infra | 1 | High | A7(MP x4) ,CoreSight-DS5 | code link
| 2 |  | DDR MC
| 3 |  | NOC
Multi-media interface | 4 |  | MIPI | source input max resolution 4k 30ps | 4lane 4k@30fps 2lane 1080p@60fps
| 5 |  | HDMI | source input max resolution 4k 30ps
| 6 |  | HDCP | HDCP1.4
| 7 |  | Display Port 1.3 | output max resolution 4k 30ps
High Speed interface | 8 |  | USB30 (dut as Host and Peripheral) | USB20/30 OTG function
| 9 |  | PCIe 2.0 (dual mode, dut as RC and EP) | RC/EP function | 1/13/2017
| 10 |  | Gmac+PCS | 10/100/1000M speed mode test | 1/13/2017
external storage | 11 |  | eMMC /SD interface | 1/4/8 bit mode | 1/13/2017
| 12 |  | SPI flash | 1/2/4 bit mode
Low speed interface | 13 |  | UART
| 14 |  | I2C
| 15 | Low | EJTAG
Other IP |  |  | CEVA
VIDEO CODEC

## Action items
No | veloce HW component list | Description | Comments | by date | Status
1 | Virtual UART | output CPU debug information |  | 12/25/2016 | done
2 | DDR4-64bit |  |  | 12/25/2016 | done
3 | DDR3-64bit |  | Virtual HDMI is ready in old top, and will be migrate to the new top
4 | LPDDR3-64bit
5 | DDR4-32bit
6 | DDR3-32bit
7 | LPDDR3-32bit
8 | Codelink for M7/A7 debug | A7/M7 and debug with Codelink |  | 12/25/2016 | done
9 | MIPI RX |  | Virtual HDMI is ready in old top, and will be migrate to the new top
10 | HDMI RX |  | Virtual HDMI is ready in old top, and will be migrate to the new top
11 | HDCP 1.4 |  | Virtual HDMI is ready in old top, and will be migrate to the new top
12 | CEVA |  | merger into veloce | 1/23/2017 | done
13 | TYPEC DP |  |  |  | waiting for Mentor expert field support
14 | eMMC |  |  |  | planing on Feb
15 | SD controller |  |  |  | planing on Feb
16 | GMAC(Ethernet) |  |  |  | planing on Feb
17 | PCIe |  |  |  | planing on Feb
18 | USB30 |  |  |  | planing on Feb
19 | USB20 |  |  |  | planing on Feb
20 | TYPEC USB30 |  |  |  | planing on Feb
21 | OTP controller
22 | DVP RX
23 | DVP TX
24 | HDMI I2S input
25 | MIPI TX

## SW test case
No | SW test case | Description | Comments | by date | Status
1 | Bootloader/ Linux kernel | A7 kernel running with DDR |  |  | Bootloader is OK, kernel is still doing
2 | OTP program | in secure mode, program OTP memory/read. In non-secure mode, read OTP
3 | HDCP Key operation | in secure mode, read HDCP key from OTP, then write to HDMI/DP
4 | boot from SPI only | A7 boot from SPI flash
5 | secure boot from SPI | A7 boot from ROM with SPI flash/tRoot/SPAcc
6 | secure boot from eMMC | A7 boot from ROM with eMMC flash/tRoot/SPAcc
7 | USB Host/Device mode | including TYPEC USB30/ SYNOPSYS USB20/30
8 | Gmac 10/100/1000 mode
9 | PCIe RC/EP mode
10 | A7+ CEVA | CEVA communicate with A7 to deal with the data from DDR and write back DDR, move data by DMAC and store into on-chip SRAM
11 | MIPI RX+ISP+Codec+BB+SD (Drone) | MIPI 4k60 input to ISP then to JEPG/HEVC Encoder stored into SD, and downscaling 1080p60 to H264 Encoder to BB transaction.
12 | HDMI RX+Codec+BB | HDMI RX 4k30 input to HEVC/H264, then to BB transaction
13 | BB+Codec+Display+DP | BB receive image then decode by HEVC/H264 ,then to Display enginee, to DP
14 | Audio processing | HDMI I2S input to DDR, DSP processing then output to I2S
15 | MIPI RX+ video interface | MIPI 1080x30 x2ch + 720x30x 4ch input data to DDR via video interface