## Sheet1
|  |  |  | 6/26 | 6/27 | 6/28 | 6/29 | 6/30 | 7/1 | 7/2 | 7/3 | 7/4 | 7/5 | 7/6 | 7/7 | 7/8 | 7/9 | 7/10 | 7/11 | 7/12 | 7/13 | 7/14 | 7/15 | 7/16 | 7/17 | 7/18 | 7/19 | 7/20 | 7/21 | 7/22 | 7/23 | 7/24 | 7/25 | 7/26 | 7/27 | 7/28 | 7/29 | 7/30 | 7/31 | 8/1 | 8/2 | 8/3 | 8/4 | 8/5 | 8/6 | 8/7 | 8/8 | 8/9 | 8/10 | 8/11 | 8/12 | 8/13 | 8/14 | 8/15 | 8/16 | 8/17 | 8/18 | 8/19 | 8/20 | 8/21 | 8/22 | 8/23 | 8/24 | 8/25 | 8/26 | 8/27 | 8/28 | 8/29 | 8/30 | 8/31 | 9/1 | 9/2 | 9/3 | 9/4 | 9/5 | 9/6 | 9/7 | 9/8 | 9/9 | 9/10 | 9/11 | 9/12 | 9/13 | 9/14 | 9/15 | 9/16 | 9/17 | 9/18 | 9/19 | 9/20 | 9/21 | 9/22 | 9/23 | 9/24 | 9/25 | 9/26 | 9/27 | 9/28 | 9/29 | 9/30 | 10/1 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6 | 10/7 | 10/8 | 10/9 | 10/10 | 10/11 | 10/12 | 10/13 | 10/14 | 10/15 | 10/16 | 10/17 | 10/18 | 10/19 | 10/20 | 10/21 | 10/22 | 10/23 | 10/24
CORE_CEVA | Release | NLS |  | 6/30: 0630(release date 20170512)
| Release | SCRIPT
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 8/18: pr.0818; 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF
| VSI | SPEF |  | 8/18: 0818.cworst_85
| Release | SDC |  | 6/30: 0630(release date 20170525)
| Release | UPF |  | 6/30: 0630(release date 20170622)
| Release | SYN LOG |  | 7/31: 0630
| Release | FM LOG |  | 7/31: 0630
HARD_CEVA | Release | NLS |  | 7/31: 0731(release date 20170728); 9/8: 0731.eco1
| Release | SCRIPT |  | 9/8: pr_eco.tcl.0731.eco1
| Release | NLS | SCAN | 9/8: scan.0731.eco1
| Release | NLS | PR | 9/8: pr.0731.eco1
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| Release | SDC |  | 7/31: 0731(release date 20170705)
| Release | UPF |  | 7/31: 0731(release date 20170622)
| Release | SYN LOG |  | 7/31: 0731
| Release | FM LOG |  | 7/31: 0731
SUB_CEVA | Release | NLS |  | 7/31: 0731(release date 20170728); 9/8: 0731.eco1
| Release | SCRIPT |  | 9/8: pr_eco.tcl.0731.eco1
| Release | NLS | SCAN | 9/8: scan.0731.eco1
| Release | NLS | PR | 9/8: pr.0731.eco1
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: 0906.cbest_m40c; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 7/31: 0731 & flat.0731(release date 20170727)
| Release | UPF |  | 7/31: 0731 & flat.0731(release date 20170622)
| Release | SYN LOG |  | 7/31: 0731 & cevaxm4_subsys.0731 & noc_ceva.0731 & mmu_dsp.0731 & dmac_ceva.0731
| Release | FM LOG |  | 7/31: 0731 & cevaxm4_subsys.0731 & noc_ceva.0731 & mmu_dsp.0731 & dmac_ceva.0731
CORE_CA7 | Release | NLS |  | 6/28: 0628(release date 20170620)
| Release | SCRIPT
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN | 8/28: scan.0828
| VSI | NLS | PR | 8/21: pr.0821; 8/24: pr.0824; 8/28: pr.0828; 9/29: pr.0929 pg.pr.0929
| VSI | SDF
| VSI | SPEF |  | 8/24: 0824.cworst_85
| VSI | SDC |  | 6/28: 0628(release date 20170608)
| VSI | UPF |  | 6/28: 0628(release date 20170620)
| Release | SYN LOG |  | 7/31: 0628
| Release | FM LOG |  | 7/31: 0628
HARD_CA7 | Release | NLS |  | 6/29: 0629; 9/7: 0629.eco1
| Release | SCRIPT |  | 9/7: tcl.0629.eco1
| Release | NLS | SCAN | 9/7: scan.0629.eco1
| Release | NLS | PR | 9/7: pr.0629.eco1
| VSI | NLS | SCAN | 8/28: scan.0828
| VSI | NLS | PR | 8/21: pr.0821; 8/24: pr.0824; 8/28: pr.0828; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 8/21: 0821.cbest_m40c 0821.cworst_m40c
| VSI | SPEF |  | 8/24: 0824.cworst_85
| Release | SDC |  | 6/30: 0629(release date 20170621)
| Release | UPF |  | 6/30: 0629(release date 20170623)
| Release | SYN LOG |  | 7/31: 0629
| Release | FM LOG |  | 7/31: 0629
SUB_CA7 | Release | NLS |  | 7/20: 0720; 7/21: 0721; 9/7: 0721.eco1
| Release | SCRIPT |  | 9/7: tcl.0721.eco1
| Release | NLS | SCAN | 9/7: scan.0721.eco1
| Release | NLS | PR | 9/7: pr.0721.eco1
| VSI | NLS | SCAN | 8/28: scan.0828
| VSI | NLS | PR | 8/24: pr.0824; 8/28: pr.0828; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 8/24: 0824.cbest_m40c 0824.cworst_m40c; 9/29: cworst.sdf.0929 cbest.sdf.0929
| VSI | SPEF |  | 8/24: 0824.cworst_85
| Release | SDC |  | 7/20: 0720 & flat.0720; 7/21: 0721 & flat.0721 same as 0720; 8/8: flat.0721.v1
| Release | UPF |  | 7/20: 0720 & flat.0720; 7/21: 0721 & flat.0721 same as 0720
| Release | SYN LOG |  | 7/31: 0721 & a7_subsystem.0721 & cci400_top.0721
| Release | FM LOG |  | 7/31: 0721 & a7_subsystem.0721 & cci400_top.0721
ISP | Release | NLS |  | 8/11: 0811; 9/11: 0811.eco1; 9/14: 0811.eco2
| Release | SCRIPT |  | 9/11: hwang/mqjiang/zyue/xyuan/isp_hdr.tcl.0811.eco1; 9/14: PR_ECO.tcl.0811.eco2; 9/18: PR0911_0918.tcl.0811.eco3
| Release | NLS | SCAN | 9/11: scan.0811.eco1; 9/14: scan.0811.eco2
| Release | NLS | PR | 9/11: pr.0811.eco1; 9/14: pr.0811.eco2; 9/18: pr.0811.eco3
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 8/25: pr.0825; 9/6: pr.0906; 9/11: pr.0911; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: 0906.cworst_m40; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 8/11: 0811; 9/21: 0811.v1
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
HEVC | Release | NLS |  | 6/27: 0627
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR | 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: 0906.wc_rcworst; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 6/30: 0627
| Release | UPF |  | 6/27: 0627
| Release | SYN LOG
| Release | FM LOG
DDR | Release | NLS |  | 6/28: 0628(release date 20170626); 7/25: 0628.eco1; 7/28: 0628.eco2; 9/7: 0628.eco3; 9/11: 0628.eco4
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR | 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: 0906.wc_rcworst; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 6/28: 0628(release date 20170622); 6/30: 0628.v1; 7/7: 0628.v2 & 0628.v3; 7/11: 0628.v4; 7/14: 0628.v5; 8/3: 0628.v6 & 0628.v7; 8/4: 0628.v8
| Release | UPF
| Release | DEF |  | 6/28: 0628(release date 20170622)
| Release | SYN LOG |  | 7/27: 0628
| Release | FM LOG |  | 7/27: 0628.eco1
BB | Release | NLS |  | 8/11: 0811; 9/12: 0811.eco1; 9/29: 0811.eco2
| Release | SCRIPT |  | 9/12: tcl.0811.eco1; 9/29: tcl.0811.eco2
| Release | NLS | SCAN | 9/12: scan.0811.eco1; 9/29: scan.0811.eco2
| Release | NLS | PR | 9/12: pr.0811.eco1; 9/29: pr.0811.eco2
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 8/25: pr.0825; 9/6: pr.0906; 9/11: pr.0911; 9/29: pr.0929 pg.pr.0929; 10/9: pr.1009 pg.pr.1009
| VSI | SDF |  | 9/6: 0906.cworst_m40c; 9/29: cworst.sdf.0929 cbest.sdf.0929; 10/9: cworst.sdf.1009 cbest.sdf.1009
| Release | SDC |  | 8/11: 0811(release date 0712)
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
SUB1 | Release | NLS |  | 8/1: 0801; 8/8: 0808; 8/10: 0810; 9/8: 0810.eco1; 10/11: 0810.eco2
| Release | SCRIPT |  | 9/8: pr_eco.tcl.0810.eco1; 10/11: pr_eco.tcl.0810.eco2
| Release | NLS | SCAN | 9/8: scan.0810.eco1; 10/11: scan.0810.eco2
| Release | NLS | PR | 9/8: pr.0810.eco1; 10/11: pr.0810.eco2
| VSI | NLS | SCAN | 9/6: scan.0906
| VSI | NLS | PR | 8/25: pr.0825; 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929; 10/10: pr.1010
| VSI | SDF |  | 9/6: 0906.cworst_m40; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 8/1: 0801; 8/3: 0801.v1; 8/4: 0801.v2; 8/8: 0808; 8/9: 0808.v1; 8/14: 0810; 8/16: 0810.v1; 9/26: 0810.v2
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
SUB2 | Release | NLS |  | 7/21: 0721; 8/11: 0721.eco1
| Release | NLS | SCAN | 8/11: scan.0721.eco1
| Release | NLS | PR | 8/11: pr.0721.eco1 & tcl.pr.0721.eco1
| VSI | NLS | SCAN | 8/10: scan.0721
| VSI | NLS | PR | 8/10: pr.0721; 8/16: pr.0816; 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: 0906.cworst_m40; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 7/21: 0721(release date 0713); 8/23: 0721.v1; 8/29: 0721.v2
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
SUB3 | Release | NLS |  | 7/27: 0727; 8/1: 0801; 8/5: 0801.eco1.notuse; 9/7: 0801.eco1; 10/13: 0801.eco2
| Release | SCRIPT |  | 8/5: 0801.eco1.notuse; 9/7: pr_eco.tcl.0801.eco1; 10/13: pr_eco.tcl.0801.eco2
| Release | NLS | SCAN | 9/7: scan.0801.eco1; 10/13: scan.0801.eco2
| Release | NLS | PR | 9/7: pr.0801.eco1; 10/13: pr.0801.eco2
| VSI | NLS | SCAN | 8/31: scan.0831; 9/6: scan.0906
| VSI | NLS | PR | 8/16: pr.0816; 8/31: pr.0831; 9/6: pr.0906; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: cworst_m40; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 7/27: 0727(release date 0726); 8/1: 0801; 8/23: 0801.v1
| Release | SYN LOG |  | 7/27: 0727 pcie.0727 typec.0727
| Release | FM LOG |  | 7/27: 0727 pcie.0727 typec.0727
SUB4 | Release | NLS |  | 7/21: 0721; 9/9: 0721.eco1
| Release | SCRIPT |  | 9/9: pr_eco.tcl.0721.eco1; 9/12: pr_eco.tcl.0721.eco1.v1 & pr_eco.tcl.0721.eco2
| Release | NLS | SCAN | 9/9: scan.0721.eco1; 9/12: scan.0721.eco2
| Release | NLS | PR | 9/9: pr.0721.eco1; 9/12: pr.0721.eco2
| VSI | NLS | SCAN | 8/31: scan.0831; 9/6: scan.0906
| VSI | NLS | PR | 8/18: pr.0818; 8/31: pr.0831; 9/6: pr.0906; 9/8: pr.0908; 9/29: pr.0929 pg.pr.0929
| VSI | SDF |  | 9/6: cworst_m40; 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 7/21: 0721(release date 0713)
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
SUB_TOP (both sub top and top are in top) | Release | NLS |  | 8/1: 0801; 8/4: 0801.eco1; 8/9: 0801.eco2; 9/10: 0801.eco3; 10/18: 0801.eco4
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN | 8/28: pr.0828(post cts); 8/31: bsd.0831; 9/6: bsd.0906
| VSI | NLS | PR | 8/31: pr.0831; 9/6: pr.0906; 9/8: pr.0908
| VSI | SDF
| Release | SDC
| Release | UPF
| Release | SYN LOG
| Release | FM LOG
TOP (both sub top and top are in top) | Release | NLS |  | 8/1: 0726; 8/2: 0802 & 0802.eco1; 9/10: 0802.eco2; 9/11: 0802.eco3
| Release | SCRIPT |  | 9/10: pr_eco.tcl.0802.eco2 & scan_eco.tcl.0802.eco2; 10/18: pin_share_pr.tcl.0802.eco4
| Release | NLS | SCAN | 9/10: scan.0802.eco2; 9/11: scan.0802.eco3; 10/18: scan.0802.eco4
| Release | NLS | PR | 9/10: pr.0802.eco2; 10/18: pr.0802.eco4
| VSI | NLS | SCAN
| VSI | NLS | PR | 9/29: pr.0929 pg.pr.0929; 10/17: pr.1017
| VSI | SDF |  | 9/29: cworst.sdf.0929 cbest.sdf.0929
| Release | SDC |  | 8/1: 0801 & flat.0801; 8/3: flat.0801.v1; 8/4: flat.0801.v2; 8/9: flat.0801.v3; 8/14: 0801.v1 & flat.0801.v4; 8/16: flat.0801.v5; 8/18: 0801.v2 & flat.0801.v6; 8/21: 0801.v3 & flat.0801.v7; 8/29: 0801.v4 & flat.0801.v8; 9/2: flat.0801.v9; 9/3: flat.0801.v10; 9/4: flat.0801.v11; 9/8: flat.0801.v12; 9/11: flat.0801.v13; 9/12: flat.0801.v14; 9/13: flat.0801.v15; 9/15: flat.0801.v16; 9/19: flat.0801.v17; 9/21: flat.0801.v18; 9/26: flat.0801.v19
| Release | UPF |  | 6/27: flat.0627; 6/30: flat.0630
| Release | SYN LOG
| Release | FM LOG

## Sheet2
|  |  |  | 6/26 | 6/27 | 6/28 | 6/29 | 6/30 | 7/1 | 7/2 | 7/3 | 7/4 | 7/5 | 7/6 | 7/7 | 7/8 | 7/9 | 7/10 | 7/11 | 7/12 | 7/13 | 7/14 | 7/15 | 7/16 | 7/17 | 7/18 | 7/19 | 7/20 | 7/21 | 7/22 | 7/23 | 7/24 | 7/25 | 7/26 | 7/27 | 7/28 | 7/29 | 7/30 | 7/31 | 8/1 | 8/2 | 8/3 | 8/4 | 8/5 | 8/6 | 8/7 | 8/8 | 8/9 | 8/10
CORE_CEVA | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
HARD_CEVA | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB_CEVA | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
CORE_CA7 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | SDC
| VSI | UPF
HARD_CA7 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB_CA7 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
ISP | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
HEVC | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
DDR | Release | NLS |  | 7/25: ECO,Change list: remove buffers on ddr_pll power pins; 7/28: ECO,Change list: remove buffers on ddr_pll power pins
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
| Release | DEF
BB | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB1 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB2 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB3 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB4 | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
SUB_TOP | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF
TOP | Release | NLS
| Release | NLS | SCAN
| Release | NLS | PR
| VSI | NLS | SCAN
| VSI | NLS | PR
| Release | SDC
| Release | UPF