## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
| IP Name | Display_Engine | RTL Simulation | Local Sim | 4 | 4 | 4 | 0 | 100%
|  |  |  | SoC-level Sim | 9 | 0 | 0 | 0 | 0%
| IP Owner | Jlliu | Gate-level Simulation
| Silicon Proven Status |  | Gate-level w/ sdf Sim
|  |  | FPGA |  | 1 | 0 | 0 | 0 | 0%
|  |  | Veloce |  | 2 | 0 | 0 | 0 | 0%
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[6 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
1 | IP | Display: two videos overlay: One video layer + One Overlayer |  |  | 1 |  | Pass
2 | SOC | CGU: clock select. Check wave |  |  | 1 |  | Pass |  | Not Done
3 | SOC | RGU: Check wave |  |  | 1 |  | Pass |  | Not Done
4 | IP | Input: 10bit YUV format |  |  | 1 |  | Pass
5 | IP | Cursor |  |  | 1 |  | Pass
6 | IP | Overlayer + Video + Cursor |  |  | 1 |  | Pass
8 | SOC | Monitor: Monitor connection |  |  | 1 |  | Pass
9 | SOC | Interrupt: |  |  | 1 |  | Pass
10 | IP | Mirror X for 8 bit/ 10bit |  |  | 1 |  | Pass
11 | IP | Mirror Y for 8 bit/ 10bit |  |  | 1 |  | Pass
12 | IP | Scalling for 8 bit/ 10bit |  |  | 1 |  | Pass
13 | IP | Rotation for 8bit |  |  | 1 |  | None
14 | IP | Gama Correction |  |  | 1 |  | Pass
15 | IP | Dithering |  |  | 1 |  | Pass
16 | SOC | Reset when there are uncompleted axi access |  |  | 1 |  | Pass
| SOC | scan mode frequency |  |  | 1 |  | Pass |  | Not Done
| SOC | Pixecl clock configure |  |  | 1 |  | Pass
| SOC | Display QoS function |  |  | 1 |  | Pass
| SOC | AHB access ( under work case ) |  |  | 1 |  | Pass
| SOC | AHB access ( under normal case ) |  |  | 1 |  | Pass
| IP | Adjust the blank time for adjusting the frame rate |  |  | 1 |  | Pass
| SOC | Display -> DVP/MIPI: YUV422, RGB |  |  | 1 |  | Pass
| SOC | Display -> DP |  |  | 1 |  | Pass
| IP | Video Scaling + overlayer |  |  | 1 |  | Pass |  | Not Done

## soc
Interface Verification
1.AHB: Full memory address space read/write (working mode)
2.AHB: Full memory address space read/write (standby mode)
3.AXI: Transitions (working mode)
3.AXI: Transitions (standby mode)
4.Reset: (normal reset, random reset)
5. Clock Generation (from different source, different frequency)
Memory Test
1. Scan mode
2. Mbist mode
3. Bsd mode
4. Normal mode
5 interrupt

## function
Frame Format
1. X4R4G4B4 (ARGB,不常用）
2. A4R4G4B4 (ARGB,不常用）
3. X1R5G5B5 (ARGB,不常用）
4. A1R5G5B5 (ARGB,不常用）
5. R5G5B5 (ARGB,不常用）
6. X8R8G8B8 (ARGB,不常用）
7. A8R8G8B8 (ARGB,不常用）
8. A2R10B10G10 (ARGB-10BIT,不常用）
9. INDEX8 (不常用）
10.INDEX4 (不常用）
11.INDEX2 (不常用）
12.INDEX1 (不常用）
13.YUY2 (Packed-YUV,不常用, 422）
14.UYVY (Packed-YUV,不常用, 422）
15.NV12 (2-Planar YUV)
16.NV16 (2-Planar YUV, 422)
17.YV12 (3-Planar YUV)
18.NV12_10BIT (2-Planar 10bit YUV)
19.NV16_10BIT (2-Planar 10bit YUV, 422)
20.P010 (2-Planar 10bit YUV)
21.NV12_10BIT_L1 (3pixel/4byte)
22.NV16_10BIT_L1 (3pixel/4byte)
Alpha-Blending
1
Cursor
Gamma/Dither
Scaling
Color-Key