## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
| Check Clock: Each IP can receive the corresponding clocks | HEVC | RTL Simulation | Local Sim | 4 | 4 | 4 | 0 | 100%
|  |  |  | SoC-level Sim | 9 | 0 | 0 | 0 | 0%
| IP Owner | Xyuan | Gate-level Simulation
| Silicon Proven Status |  | Gate-level w/ sdf Sim
|  |  | FPGA |  | 1 | 0 | 0 | 0 | 0%
|  |  | Veloce |  | 2 | 0 | 0 | 0 | 0%
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Check Point |  |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[9 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
1 | SoC | APB: Full memory address space read/write, with pclk enable | hevc_soc_apb_pclken |  | Check If reserved space cause system hang (Write 0x7100,debug_reg region),APB hang |  |  | 1 |  | Pass |  |  |  |  | Xyuan
2 | SoC | APB: Full memory address space read/write, with pclk disable | hevc_soc_apb_pclkdis |  | Check If cause system hang (it casued apb bus hang , apb_ready is always 0 ???) cnm confirm |  |  | 1 |  | Pass |  |  |  |  | Xyuan
3 | SoC | APB: Full memory address space read/write, with pclk enable, cclk disable | hevc_soc_apb_pclken_cclkdis |  | Check If cause system hang ( core_clk and apb_clk are all enabled) |  |  | 1 |  | Pass |  |  |  |  | Xyuan
4 | SoC | AXIM: Access Hang, Timeout reset | hevc_soc_axi_hang_timeout |  | Check if recover after hang |  |  | 1 |  | Pass |  |  |  |  | Xyuan
5 | SoC | CGU: Clock Connection, Clock Selection, Clock Gating PLL2, 600( 500 ), 500, 450 ( 375 ), 400, 333, 300, 200 | hevc_soc_clock_select |  | Check connection and right select |  |  | 1 |  | Pass |  | Not Done |  |  | Xyuan
6 | SoC | RGU: Reset connection, SW reset function | hevc_soc_reset_check |  | Check reset connection and sw function |  |  | 1 |  | Pass |  | Not Done |  |  | Xyuan
7 | SoC | Interrupt: A7 only | hevc_soc_interrupt(Run one interrupt handler) |  | Check if interrupt works |  |  | 1 |  | Pass |  | Not Done |  |  | Xyuan
8 | SoC | Security: Trustzone |  |  | Check function |  |  | 1 |  | Pass |  |  |  |  | Xyuan
9 | SoC | Monitor: Monitor connection |  |  | Check connection |  |  | 1 |  | Pass |  |  |  |  | Xyuan
10 | SoC | Simulation with ASIC SRAM, pass one 4K@30fps vectors |  |  | Check ASIC SRAM |  |  | 1 |  | Pass |  |  |  |  | Xyuan
11 | SoC | BIST/SCAN/BSD Mode: ASIC SRAM ls value |  |  | Check ASIC SRAM value |  |  | 1 |  | Pass |  | Not Done |  |  | Xyuan
12 | SoC | Scan Mode: MBIST/SCAN mode, clocks： BPU 300M, CCLK 333, ACLK:333 |  |  | Check scan mode clocks frequency |  |  | 1 |  | Pass |  | Not Done |  |  | Xyuan
13 | Post-Sim | Check APB ready signal tie 1, when power off | [5 empty] | 1 |  |  | Pass | Not Done |  |  | Jlliu
14 | SoC | use Netlist do the regression. |  |  | 把这个问题，转化成asic sram的check吧 |  |  | 1 | [5 empty] | Pass | Xyuan
15 | SoC | System: Decoder -> Display: YV12 | hevc_soc_sys_dec_display_yv12 |  | Check function |  |  | 1 |  | Pass |  |  |  | Pass | Xyuan
16 | SoC | System: Decoder -> Display: NV12 |  |  | Check function |  |  | 1 |  | Pass |  |  |  | Pass | Xyuan
17 | SoC | System: Decoder -> Display: NV21 |  |  | Check function |  |  | 1 |  | Pass |  |  |  | Pass | Xyuan
18 | SoC | System: Low delay encoding with ISP |  |  | Check low delay function |  |  | 1 |  | Pass |  |  |  |  | Xyuan
19 | SoC | System: Low delay decoding with ISP |  |  | check low delay decoding function |  |  | 1 |  | Pass |  |  |  |  | Xyuan
20 | SoC | System: Low delay encoding with VIF |  |  | Check low delay function |  |  |  |  | Pass
21 | SoC | System: Encoder work Buffer with ShareMem(BB and h264) |  |  | Check encoder and sharemem read/write function |  |  | 1 |  | Pass
22 | SoC | SMMU Codec Path |  |  | virtual address to physical address (one IP write , other IP read ?) |  |  | 1 |  | Pass |  |  |  |  | Lyu
23 | SoC | Check hevc_top signals about connection |  |  | Check if there are unconnection signals. |  |  | 1 |  | Pass
24 | Perf | Encoder: DDR4 16/32/64bit performance check |  |  | Check the least DDR4 requirement |  |  | 1 | [5 empty] | Pass | Xyuan
25 | Perf | Encoder: DDR3 16/32/64bit performance check |  |  | Check the least DDR3 requirement |  |  | 1 | [5 empty] | Pass | Xyuan
26 | Perf | Encoder: LPDDR3 16/32/64bit performance check |  |  | Check the least LPDDR3 requirement |  |  | 1 | [5 empty] | Pass | Xyuan |  |  | 理论上，LPDDR3的效率应该低于DDR3
27 | Perf | Encoder: CABAC performance check.( least QP ) |  |  | check CABAC performance |  |  | 1 | [5 empty] | Pass | Xyuan
28 | Perf | Encoder: Rate control performance.( 100Mbps) |  |  | check rate control performance |  |  | 1 | [5 empty] | Pass | Xyuan
29 | Perf | Encoder: 10 bit performance collection. |  |  | Check 10 bit interface / performance |  |  | 1 | [5 empty] | Pass | Xyuan
30 | Perf | Encoder: cf50 function and performance collection |  |  | Check cf50 interface / performance |  |  | 1 | [5 empty] | None | Xyuan | Don't support CF50.
31 | Perf | Decoder: Maxbitrate( CABAC performance) |  |  | Check CABAC decoding performance |  |  | 1 | [5 empty] | Pass | Xyuan | Up to 400Mbps under 410MHzCore & 333MHzBPU
32 | Perf | Decoder: 10bit performance |  |  | Cehck the performance |  |  | 1 | [5 empty] | Pass | Xyuan | Close to 410Mhz
33 | IP-Enc | Input Format: 4:2:0 |  |  | Check function |  |  | 1 |  |  |  | Not Done |  | Pass | Xyuan
34 | IP-Enc | Input Format: NV12 |  |  | Check function |  |  | 1 | [5 empty] | Pass | Xyuan
35 | IP-Enc | ROI: Intra in P slice |  |  | Check ROI |  |  | 1 | [5 empty] | Pass | Xyuan
36 | IP-Dec | BWB: Reference Picture is compressed, displayed picture is linear. |  |  | Check function |  |  | 1 | [5 empty] | Pass | Xyuan
| IP-Enc | 3Pixel/4Byte |  |  | Check function and interface | [8 empty] | Pass | Xyuan
| IP-Enc | UPF based RTL. 1. HEVC IDLE, power off, 2. HEVC Busy, power off. |  |  | Check when hevc idle, power off; check when hevc busy, power off |  |  | 1 | [5 empty] | Pass | Xyuan / Peng
| IP-Enc | UPB based netlist. 1. HEVC IDLE, power off. 2. HEVC Busy, power off. | [9 empty] | Not Done |  |  | Xyuan

## Sheet2
23 | SoC | Multi-Instance: 2 Channel Encoding |  | Check multiinstance | 1 |  | Not Done | Jlliu
24 | SoC | Multi-Instance: 2 Channel Decoding |  | Check multiinstance | 1 |  | Not Done | Jlliu
25 | SoC | Multi-Instance: 1 Encoding 1 Decoding |  | Check multiinstance | 1 |  | Not Done | Jlliu
13 | SoC | System: Encoder -> AES -> BB with low bitrate | hevc_soc_sys_enc2aes2bb_lbr | Check function | 1 |  | Not Done | Jlliu
14 | SoC | System: Encoder -> AES -> BB with high bitrate( 100Mbps ) | hevc_soc_sys_enc2aes2bb_hbr | Check function with multiple interrupts | 1 |  | Not Done | Jlliu
15 | SoC | System: Encoder -> AES -> BB use on-chip sram | hevc_soc_sys_enc2aes2bb_sram | check function | 1 |  | Not Done | Jlliu
16 | SoC | System: BB->AES->Decoder with hight bitrate( 100Mbps ) | hevc_soc_sys_bb2aes2enc_hbr | Check function with multiple interrupts | 1 |  | Not Done | Jlliu
17 | Soc | System: BB->AES->Decoder with low bitrate | hevc_soc_sys_bb2aes2enc_lbr | Check function | 1 |  | Not Done | Jlliu
29 | IP-Enc | IP Internal clock gating |  | Check function | 1 |  | Not Done | Jlliu
30 | IP-Enc | Input Format: 4:0:0 |  | Check mono encoding | 1 |  | Not Done | Jlliu
45 | IP-Enc | Bitstream Buffer: Ring |  | Check function | 1 |  | Not Done | Jlliu
46 | IP-Enc | Bitstream Buffer: Linear |  | Check function | 1 |  | Not Done | Jlliu
47 | IP-Enc | Frame Buffer Format: Tile |  | Check function and performance | 1 |  | Not Done | Jlliu
50 | IP-Enc | All Intra |  | Check function | 1 |  | Pass | Jlliu
52 | IP-Enc | Constrained Intra pref flag |  | Check function | 1 |  | Not Done | Jlliu
53 | IP-Enc | VUI Info |  | Check function | 1 |  | Not Done | Jlliu
54 | IP-Enc | Scaling List |  | Check function | 1 |  | Not Done | Jlliu
57 | IP-Dec | Post Rotation: |  | Check function and performance | 1 |  | Not Done | Jlliu
58 | IP-Dec | Post Mirror |  | Check function and performance | 1 |  | Not Done | Jlliu
59 | IP-Dec | Flush decoder cmd |  | Check function | 1 |  | Not Done | Jlliu
60 | IP-Dec | Error bitstream: resilience / concealment
61 | IP | Sleep VPU/Wake up VPU |  |  |  | Not Done
62 | IP | Debug ( VPU_PDBG ) |  |  |  | Not Done
63 | IP | Use Current Picture as long term picture
64 | IP-Enc | Use current picture as long term reference
65 | IP-Enc | Ctu QP enable |  | Check Ctu QP configuration
66 |  | PrefixSeiNal enable
67 |  | SuffixSeiNal enable
68 |  | HRD RBSP in VPS
69 |  | HRD RBSP in VUI
70 |  | VUI RBSP
71 |  | Lossless
48 | IP-Enc | Pre Mirror |  | Check function and performance | 1 |  | Not Done | Jlliu
49 | IP-Enc | Pre Rotation |  | Check function and performance | 1 |  | Not Done | Jlliu
33 | IP-Enc | Error resilience: Multiple Slice, in bits |  | Check function | 1 |  | Not Done | Xyuan
34 | IP-Enc | Error resilience: Multiple Slice, in MBs |  | Check function | 1 |  | Not Done | Xyuan
35 | IP-Enc | Error resilience: Cyclic Intra Refresh |  | Check function | 1 |  | Not Done | Xyuan