## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
|  | VIF | RTL Simulation | Local Sim | 13 | 2 | 2
|  |  |  | SoC-level Sim | 13 | 2 | 2
| IP Owner | Hbzhong/Zxie | Gate-level Simulation
| Silicon Proven Status |  | Gate-level w/ sdf Sim
FPGA
Veloce
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[6 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
ISPIF
1 | work mode | video2sync: frame fliter/single frame mode; |  |  |  | Pass | Pass |  |  |  | Pass
2 |  | video2sync: mipi interrupt;/config change |  |  |  | Pass | Pass |  |  |  | Pass
3 | one_view mode | 1 mipi view + RAW8 + ISP (640X480, 1280X720, 1920X1080, 4096X2160,3840X2160) |  |  |  | Pass | Pass |  |  |  | Pass
4 |  | 1 mipi view + RAW10 + ISP (640X480, 1280X720, 1920X1080, 4096X2160,3840X2160) |  |  |  | Pass | Pass |  |  |  | Pass
5 |  | 1 mipi view + RAW12 + ISP (640X480, 1280X720, 1920X1080, 4096X2160,3840X2160) |  |  |  | Pass | Pass |  |  |  | Pass
6 |  | 1 mipi view + RAW14 + ISP (640X480, 1280X720, 1920X1080, 4096X2160,4352X2160) |  |  |  | Pass | Pass |  |  |  | Pass
7 |  | 1 mipi view + YUV422_8 + ISP (320X100,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
8 |  | 1 mipi view + YUV422_10 + ISP (320X100,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
8 |  | 1 hdmi view + YUV422_8 + ISP (1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
9 |  | 1 dvp601 view + YUV422_8 ( 1920X1080 ) |  |  |  | Pass |  |  |  |  | Pass
10 |  | 1 dvp656 view + YUV422_8 ( 1920X1080 ) |  |  |  | Pass |  |  |  |  | Pass
11 | two_view mode | 2 mipi view + RAW8 (640X480,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
12 |  | 2 mipi view + RAW10 (640X480,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
13 |  | 2 mipi view + RAW12 (640X480,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
14 |  | 2 mipi view + RAW14 + ISP (640X480,1920X1080) |  |  |  | Pass | Pass |  | Pass |  | Pass
15 |  | 2 mipi view + YUV422_8 (640X480,1920X1080) |  |  |  | Pass | Pass |  |  |  | Pass
16 |  | 2 mipi view + YUV422_10 (640X480,1920X1080) |  |  |  | Pass | Pass |  | Pass |  | Pass
17 |  | 2 dvp601 view + YUV422_8 ( 1920X1080 ) |  |  |  | Pass
18 |  | 2 dvp656 view + YUV422_8 ( 1920X1080 ) |  |  |  | Pass
19 | fpga_test | 1 dvp view + raw8 (2112X1536) + ISP |  |  |  | Pass |  |  |  | Pass
20 |  | pattgen_mode + 1view + raw8 (2112X1536) + ISP |  |  |  | Pass
21 |  | 2 dvp view + raw8 (2112X1536) |  |  |  | Pass |  |  |  | Pass
22 |  | pattgen_mode + 2view + raw8 (2112X1536) |  |  |  | Pass |  |  |  | Pass
VIF_BPIF |  | 1view |  |  |  | pass | pass
|  | 2view |  |  |  | pass | pass
|  | 3view |  |  |  | pass
|  | 4view |  |  |  | pass
|  | 5view |  |  |  | pass
|  | 6view |  |  |  | pass
|  | 7view |  |  |  | pass
|  | 8view | [7 empty] | None
random view num
pass
[6 empty] | pass | pass
|  | 1view + audio |  |  |  | pass | pass
|  | 2view + audio |  |  |  | pass
|  | 3view + audio |  |  |  | pass
|  | 4view + audio |  |  |  | pass
|  | 5view + audio |  |  |  | pass
|  | 6view + audio |  |  |  | pass
7view + audio
8view + audio
| DVPIN |  |  |  |  | pass
[6 empty] | pass | pass
|  | 1view sdr 8bit |  |  |  | pass | pass |  |  | Pass | Pass
|  | 1view sdr 16bit |  |  |  | pass
|  | 2view sdr 8bit |  |  |  | pass | pass
|  | 1view ddr 8bit |  |  |  | pass | pass |  | Pass
|  | 1view ddr 16bit |  |  |  | pass | pass
|  | 2view ddr 8bit |  |  |  | pass | pass |  | Pass
| DVPO |  |  |  |  | pass
|  | fixed YUV422 output |  |  |  | pass | Pass |  |  |  | Pass
|  | 1view sdr 8bit |  |  |  | pass
|  | 1view sdr 16bit |  |  |  | pass | Pass |  | Pass |  | Pass
|  | 1view ddr 8bit |  |  |  | pass | Pass |  |  |  | Pass
|  | 1view LCD output |  |  |  | pass | Pass |  | Pass |  | Pass
|  | dvp delay control for DVPIN/DVPOUT |  |  |  |  | Pass |  | Pass