## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
| IP Name | CEVA_DMAC | RTL Simulation | Local Sim | 0 | 0 | 0 | 0 | 0%
|  |  |  | SoC-level Sim | 0 | 0 | 0 | 0 | 0%
| IP Owner | Lei Yang | Gate-level Simulation
| Silicon Proven Status |  | Gate-level w/ sdf Sim
|  |  | FPGA |  | 0 | 0 | 0 | 0 | 0%
|  |  | Veloce |  | 0 | 0 | 0 | 0 | 0%
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[6 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
1 | CEVA_DMAC | A single block transfer(mem to mem) |  |  |  | Pass | Pass |  | Not Done |  | Pass
2 |  | A single block transfer(mem to peripheral) |  |  |  | Pass
3 |  | A single block transfer(peripheral to mem) |  |  |  | Pass
4 |  | A single block transfer(peripheral to peripheral) |  |  |  | Pass
5 |  | A reloading transfer(mem to mem) |  |  |  | Pass
6 |  | A reloading transfer(mem to peripheral) |  |  |  | Pass
7 |  | A reloading transfer(peripheral to mem) |  |  |  | Pass
8 |  | A reloading transfer(peripheral to peripheral) |  |  |  | Pass
9 |  | A shadow transfer(mem to mem) |  |  |  | Pass
10 |  | A shadow transfer(mem to peripheral) |  |  |  | Pass
11 |  | A shadow transfer(peripheral to mem) |  |  |  | Pass
12 |  | A shadow transfer(peripheral to peripheral) |  |  |  | Pass
13 |  | An LLP block chaining transfer(mem to mem) |  |  |  | Pass |  |  |  | Not Done | Pass
14 |  | An LLP block chaining transfer(mem to peripheral) |  |  |  | Pass |  |  |  | Not Done
15 |  | An LLP block chaining transfer(peripheral to mem) |  |  |  | Pass |  |  |  | Not Done
16 |  | An LLP block chaining transfer(peripheral to peripheral) |  |  |  | Pass |  |  |  | Not Done
17 | CEVA_DSP | An LLP block chaining transfer(ceva to sram) |  |  |  |  | Pass |  |  | Not Done
18 |  | An LLP block chaining transfer(sram to ceva) |  |  |  |  | Pass |  |  | Not Done
19 | SOC | interrupt test |  |  |  |  | Pass
20 | SOC | CLK frequency/RSTN/Interrupt connection check |  |  |  |  | Pass