## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
| IP Name | GMAC | RTL Simulation | Local Sim | 0 | 0 | 0 | 0 | 0%
|  |  |  | SoC-level Sim | 0 | 0 | 0 | 0 | 0%
| IP Owner | Lei Yang | Gate-level Simulation | [5 empty] | .
| Silicon Proven Status |  | Gate-level w/ sdf Sim
|  |  | FPGA |  | 0 | 0 | 0 | 0 | 0%
|  |  | Veloce |  | 0 | 0 | 0 | 0 | 0%
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[6 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
1 | GMAC receiver | check_address |  |  |  | Pass
2 |  | check_ifg |  |  |  | Pass
3 |  | check_all_128BD_and_wrap_from_BD_127_to_0 |  |  |  | Pass
4 |  | check_wrap_from_BD127_to_BD_TX_NUM |  |  |  | Pass
5 |  | check_overrun check_overrun |  |  |  | Pass
6 |  | check_short_frames |  |  |  | Pass
7 |  | check_length_from_0_to_100 check_length_from_0_to_100 |  |  |  | Pass
8 |  | check_huge_packets_enable |  |  |  | Pass
9 |  | check_64k_packets check_64k_packets |  |  |  | Pass
10 |  | preamble |  |  |  | Pass
11 |  | check_rx_err |  |  |  | Pass
12 |  | buserror |  |  |  | Pass
|  | transmitter packets to phy |  |  |  |  | Pass |  | Not Done |  | Pass
13 | GMAC transmitter | fifo_fill_level |  |  |  | Pass
14 |  | transmit_packets_from_MIN_FRAME_SIZE_to_MAX_FRAM |  |  |  | Pass
15 |  | check_crc_and_pad |  |  |  | Pass
16 |  | check_tx_enable check_ |  |  |  | Pass
17 |  | check_all_128BD_and_wrap_from_BD_127_to_0 |  |  |  | Pass
18 |  | check_tx_bd_num |  |  |  | Pass
19 |  | check_huge_packets_enable |  |  |  | Pass
20 |  | check_no_preamble |  |  |  | Pass
21 |  | transmit_64K_packet |  |  |  | Pass
22 |  | underrun |  |  |  | Pass
23 |  | bus_error |  |  |  | Pass
|  | receive packets from phy |  |  |  |  | Pass |  | Not Done | Not Done | Pass
24 | GMAC half_duplex | transmitter_late_collision |  |  |  | Pass
25 |  | transmitter_late_collision_extension_field |  |  |  | Pass
26 |  | transmitter_retransmission_limit |  |  |  | Pass
27 |  | transmitter_retry_counter |  |  |  | Pass
28 |  | transmitter_carrier_sense_lost |  |  |  | Pass
29 |  | transmitter_carrier_sense_lost_extension_field |  |  |  | Pass
30 |  | transmitter_backoff |  |  |  | Pass
31 |  | transmitter_cs_true_last_third |  |  |  | Pass
32 |  | transmitter_defer_timeout and transmitter_defer_timeout_start_frame |  |  |  | Pass
33 |  | transmitter_defer and defer_indication and transmitter_defer and transmitter_defer_indication |  |  |  | Pass
34 |  | transmitter_full_duplex_collision |  |  |  | Pass |  |  |  | Not Done | Not Done
35 |  | transmitter_full_duplex_carrier_sense |  |  |  | Pass
36 |  | receiver_collision |  |  |  | Pass
37 |  | receiver_full_duplex_collision |  |  |  | Pass
38 | GMAC rgmii receiver | check_all_128BD_and_wrap_from_BD_127_to_0 |  |  |  | Pass | Pass |  |  | Not Done | Not Done
39 | GMAC rgmii transmitter | transmit_packets_from_MIN_FRAME_SIZE_to_MAX_FRAM |  |  |  | Pass | Pass |  |  | Not Done | Not Done
40 | GMAC loop_back | loop_back_one_packet |  |  |  | Pass | Pass
41 |  | serial_send_rec |  |  |  | Pass
42 | GBE_CLK test(PAD) | 25M/50M PHY clk |  |  |  |  | Pass
43 | GMAC WISHBONE tests |  |  |  |  | Pass
44 | SOC | interrupt test |  |  |  |  | Pass
45 | SOC | CLK frequency/RSTN/Interrupt connection check |  |  |  |  | Pass
47 | SOC | memory LS/DS/SD control |  |  |  |  | Pass
48 | SOC | subsystem register |  |  |  |  | Pass