## Sheet1
| Title | Sirius IP Verification Summary | Verification Status |  | Pattern Number
[5 empty] | Planned | Executed | Passed | Failed | Complete Rate
| IP Name | HDMI | RTL Simulation | Local Sim | 49 | 49 | 49 | 0 | 100%
|  |  |  | SoC-level Sim | 9 | 1 | 1 | 0 | 0%
| IP Owner | Huibo Zhong | Gate-level Simulation
| Silicon Proven Status |  | Gate-level w/ sdf Sim
|  |  | FPGA |  | 0 | 0 | 0 | 0 | 0%
|  |  | Veloce |  | 6 | 1 | 1 | 0 | 0%
Pattern No. | ROLE | Function Verified by Pattern | Pattern path/Pattern Name |  | Pattern Number | Verification Status | [5 empty] | Reporter | Cross-checker | Reporting Date
[6 empty] | RTL local sim | RTL SoC-level sim | Gate-level Sim | Gate-level w/ sdf Sim | FPGA | Velcoe
local
1 | PHY | PHY local simualtion, quick start | testbench/simple_datapath |  | 1 | Pass
2 |  | run_scan | scan |  | 1 | Pass
3 | phy+controller | test_audio_dst_1 | video mod 57: 729x480p @240p, 44.1k |  | 1 | Pass
4 |  | test_audio_hbr_1 | video mode cea12, 720x240p @60fps, 768k sapmle per second |  | 1 | Pass
5 |  | test_audio_hbr_2 | 3-d top and video mode 31 : 1920x1080p @50khz, 768k fs |  | 1 | Pass
6 |  | test_audio_hbr_3 | hdmi video format: 4kx2k@24fps, 768k fs |  | 1 | Pass
7 |  | test_audio_oba_1 | video mode 57: 720x480@240fps, 48k fs, layout0 |  | 1 | Pass
8 |  | test_audio_oba_2 | video mode 57, 48k, layout1 |  | 1 | Pass
9 |  | test_audio_oba_3 | video mode 57, 32k, layout0 |  | 1 | Pass
10 |  | test_audio_oba_4 | video mode 57, 32k, layout1 |  | 1 | Pass
11 |  | test_audio_oba_5 | video mode 57, 48k, layout0, auto_rate feature enabled |  | 1 | Pass
12 |  | test_audio_oba_6 | video mode 57, 48k, layout0, auto_rate feature disabled |  | 1 | Pass
13 |  | test_cec_1 | simple communication between two cec device |  | 1 | Pass
14 |  | test_cec_2 | test detection of wrong pulse widths |  | 1 | Pass
15 |  | test_cec_3 | test communication with phase shifts in cec clocks |  | 1 | Pass
16 |  | tet_hdcp_1 | video mode 1: 640x480p @60hz, hdcp enable |  | 1 | Pass
17 |  | tet_hdcp_2 | 3d top and bottom videomode 16: 1920x1080p @60fps |  | 1 | Pass
18 |  | test_video_wr | register default-value check and register write -and-read -back tests. |  | 1 | Pass
19 |  | test_video_hdmi_1 | hdmi_vic 4: 4kx2k@24hz |  | 1 | Pass
20 |  | test_video_dcm_1 | 10 -bit ycc 444 |  | 1 | Pass
21 |  | test_video_dcm_2 | 10 bit ycc 422 |  | 1 | Pass
22 |  | test_video_dcm_3 | 12 bit rgb |  | 1 | Pass
23 |  | test_video_dcm_4 | 16bit ycc 444 |  | 1 | Pass
24 |  | test_video_dcm_5 | 10 bit rgb |  | 1 | Pass
25 |  | test_video_dcm_6 | 16 bit rgb |  | 1 | Pass
26 |  | test_video_cea_1 | video mode 1: 640x480p @60hz |  | 1 | Pass
27 |  | test_video_cea_2 | video mode 2: 720x480p @60hz |  | 1 | Pass
28 |  | test_video_cea_3 | video mode 4: 1280x720p @60hz |  | 1 | Pass
29 |  | test_video_cea_4 | video mode 5: 1920x1080i @60hz |  | 1 | Pass
30 |  | test_video_cea_5 | video mode 6: 720(1440)x480i @60hz |  | 1 | Pass
31 |  | test_video_cea_6 | video mode 17: 720x576p @50hz |  | 1 | Pass
32 |  | test_video_cea_7 | video mode 19: 1280x720p @50hz |  | 1 | Pass
33 |  | test_video_cea_8 | video mode 20: 1920x1080i @50hz |  | 1 | Pass
34 |  | test_video_cea_9 | video mode 21: 720(1440)x576i @60hz |  | 1 | Pass
35 |  | test_video_cea_10 | video mode 39: 1920x1080i @50hz |  | 1 | Pass
36 |  | test_video_3d_1 | video mode 4, 1280x720@60hz (frame packing) |  | 1 | Pass
37 |  | test_video_3d_2 | video mode 4, 1280x720@60hz (side-by-side(half)) |  | 1 | Pass
38 |  | test_video_3d_3 | video mode5, 1920x1080i @60hz frame-packing |  | 1 | Pass
39 |  | test_video_3d_4 | video mode16, 1920x1080p @60hz (top and bottom) |  | 1 | Pass
40 |  | test_video_3d_5 | video mode 19, 1280x720@50hz (frame packing) |  | 1 | Pass
41 |  | test_video_3d_6 | video mode 19, 1280x720@50hz (top and bottom) |  | 1 | Pass
42 |  | test_video_3d_7 | video mod20, 1920x1080i @50hz (side-by-side(half)) |  | 1 | Pass
43 |  | test_video_3d_8 | video mode32, 1920x1080 @50hz (top and botton) |  | 1 | Pass
44 |  | test_video_3d_9 | video mode32, 1920x1080p @50hz (side-by-side(half)) |  | 1 | Pass
45 |  | test_video_3d_10 | video mode34, 1920x1080 @30hz (top and botton) |  | 1 | Pass
46 |  | test_video_3d_11 | video mode34, 1920x1080 @30hz (side-by-side(half) |  | 1 | Pass
47 |  | test_video_3d_12 | video mode57, 720x480p @240hz (frame packing) |  | 1 | Pass
48 |  | test_video_pr_1 | pixel repetition 1 |  | 1 | Pass
49 |  | test_video_pr_2 | pixel repetition 3 |  | 1 | Pass
TOP
1 |  | IO connet check/clock check |  |  |  |  | pass |  | pass
2 |  | hdmi + audio pll whole chip simulation |  |  |  |  | pass |  | pass
3 |  | video datapath, video data to video_if then to ddr. |  |  |  |  | pass |  |  |  | pass
4 |  | audio datapath, audio data to video_if then to to ddr. |  |  |  |  | pass |  |  |  | pass
5 |  | audio datapath, audio data to i2s. |  |  |  |  | pass |  |  |  | pass
6 |  | register write/read |  |  |  |  | pass |  |  |  | pass
7 |  | hdcp key datapath |  |  |  |  | pass
8 |  | hdcp datapath with/without data encryption | [8 empty] | pass
9 |  | cec datapath |  |  |  |  | pass |  |  |  | pass
10 |  | ATE IO check |  |  |  |  | pass
11 |  | io_cont_test |  |  |  |  | pass
12 |  | short bist |  |  |  |  | pass
13 |  | long bist |  |  |  |  | pass |  | pass