## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | flush S2C FPGA: synplifer
| 2016-11-29 | flush S2C FPGA: DDR4 demo
| 2016-11-30 | flush S2C FPGA: DDR4 AXI slave interface
| 2016-12-01 | flush S2C FPGA: enviroment optimizing
| 2016-12-02 | flush S2C FPGA: enviroment optimizing
49 | 2016-12-05 | Sirius sub block synthesis
| 2016-12-06 | Sirius sub block synthesis
| 2016-12-07 | Sirius sub block synthesis & DDR/AXI sub block FPGA flusing
| 2016-12-08 | Sirius sub block synthesis & DDR/AXI sub block FPGA flusing
| 2016-12-09 | Sirius sub block synthesis & DDR/AXI sub block FPGA flusing | 1)Completed. Sub block such as noc, coresight, m7, a7 and cci completed by synplify. 2)In progress. DDR/AXI sub block debugging based on vivado simulation envrioment for FPGA.
59 | 2016-12-12 | Sirius top block synthesis & DDR/AXI sub block FPGA flusing
| 2016-12-13 | Sirius top block synthesis & DDR/AXI sub block FPGA flusing
| 2016-12-14 | Sirius top block synthesis & DDR/AXI sub block FPGA flusing | Completed. DDR/AXI sub block FPGA.
| 2016-12-15 | Sirius top block synthesis & DDR/AXI sub block FPGA optimization
| 2016-12-16 | Sirius top block synthesis & DDR/AXI sub block FPGA optimization | First sirius_top synthesis without DDR4 run completed.
59 | 2016-12-19 | new DDR/AXI sub block FPGA & Sirius_top S2C FPGA board flushing
| 2016-12-20 | new DDR/AXI sub block FPGA & Sirius_top S2C FPGA board flushing
| 2016-12-21 | Sirius_top S2C FPGA board flushing
| 2016-12-22 | CoreSight of Sirius_top without DDR4 flushing on FPGA board
| 2016-12-23 | CoreSight of Sirius_top without DDR4 flushing on FPGA board | Completed. New DDR/AXI sub block FPGA.
59 | 2016-12-26 | CoreSight of Sirius_top
| 2016-12-27 | CoreSight of Sirius_top
| 2016-12-28 | CoreSight of Sirius_top accessing DDR4.
| 2016-12-29 | CoreSight of Sirius_top accessing DDR4.
| 2016-12-30 | CoreSight of Sirius_top accessing DDR4. | Completed. CoreSight can check soc devices (except for A7)
60 | 2017-01-02 | CoreSight of Sirius_top accessing DDR4.
| 2017-01-03 | CoreSight of Sirius_top accessing DDR4.
| 2017-01-04 | CoreSight of Sirius_top accessing DDR4 & Fomality Enviroment
| 2017-01-05 | CoreSight of Sirius_top accessing DDR4.& memroy ip
| 2017-01-06 | CoreSight of Sirius_top accessing DDR4.& memroy ip