## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | Leaving day | any commnets
| 2016-11-29 | Confirming the CevaXM4 subsystem architecture
| 2016-11-30 | Classfying the use of input ports and output ports of CevaXM4 core (need to be confirmed)
| 2016-12-01 | Implementing cevaxm4 control register
| 2016-12-02 | Spliting ADB400 AXI4 master and slave. Integrating APB async bridge
49 | 2016-12-05 | Integrating 4 CevaXM4 cores, ADB400 AXI4 | Finished
| 2016-12-06 | CevaXM4 subsystem CGU RGU | Finished
| 2016-12-07 | CevaXM4 subsystem CGU RGU | Finished
| 2016-12-08 | APB Bus or Decoder Design (need to be dicussed more) | A round-robin arbiter mechanism for 5 APB masters has been designed. Some cases has been tested already and it seems can work correctly. But I think it need more test later.
| 2016-12-09 | APB Bus or Decoder Design
50 | 2016-12-12 | CevaXM4 subsystem ReadOnly Register | Finished
| 2016-12-13 | CevaXM4 subsystem IGU | Finished
| 2016-12-14 | Check the error of CevaXM4 subsystem | Finished
| 2016-12-15 | Preparing the synthesis environment for CevaXM4 subsystem and do the synthesis | Ongoing
| 2016-12-16 | Preparing the synthesis environment for CevaXM4 subsystem and do the synthesis | Ongoing
51 | 2016-12-19 | Synthesis CevaXM4 Core
| 2016-12-20 | Synthesis CevaXM4 Core
| 2016-12-21 | Synthesis CevaXM4 Subsystem
| 2016-12-22 | Synthesis CevaXM4 Subsystem
| 2016-12-23 | Preparing the simulation environment for CevaXM4 subsystem
52 | 2016-12-26 | Preparing the simulation environment for CevaXM4 subsystem
| 2016-12-27 | do simulation for CevaXM4 subsystem and fix bugs
| 2016-12-28 | change memory ,only using GEN2. Handle the special pins of memory
| 2016-12-29 | Synthesis CevaXM4 Core.(new memory with the handling of the special pins)
| 2016-12-30 | do simulation for CevaXM4 subsystem and fix bugs
54 | 2017-01-16 | simulation(cevaxm4 access DDR). Synthesis cevaxm4 using register to control LS | 1.CevaXM4_subsystem simulation in SOC is OK.Some small program using the AXI port to read/write code/data from/to DDR has passed. 2.Synthesis : To meet the timing request, PTCM LS port must be only controlled by global register 3.Formailty Fail.
| 2017-01-17 | Synthesis and Formality CevaXM4 core. CevaXM4 tool to initialize DDR.
| 2017-01-18 | Synthesis and Formality CevaXM4 core. CevaXM4 tool to generate the code and data memory.
| 2017-01-19 | Synthesis and Formality CevaXM4 core. CevaXM4_subsystem simulation in SOC
| 2017-01-20 | Synthesis and Formality CevaXM4 core.