## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | cadence USB in typeC subsystem evaluate.
| 2016-11-29 | confirm audio data path, Apply cadence's usb vip
| 2016-11-30 | compile USB uvm env. | hanged by tools problem, to be solved
| 2016-12-01 | Modifid Veloce DP data base, study cadence USB controller SPEC
| 2016-12-02 | debug Veloce DP data base, study cadence USB PHY SPEC | hanged in training problem,
49 | 2016-12-05 | 1. Veloce DP emulation debug, try to pass some case. | doing, firmware issue, (mentor transactor may also have some support issue)
| 2016-12-06 | 1. cadence usb simulation env, try to pass some case this week | doing, firmware problem and env problem
| 2016-12-07 | 1. fix the ISP bypss module spec | doing, use case,
| 2016-12-08 | 1. arrange HDMI part for review | controller done,
2016-12-09
50 | 2016-12-12 | 1. Veloce DP emulation debug, try to pass some case. | veloce's main_link_ctrl signal problem,
| 2016-12-13 | 1. cadence usb simulation env, try to pass some case this week | regression simulation can run now, will check the case one by one
| 2016-12-14 | 1. fix the ISP bypss module spec | finish 70% rtl code, start build sim env
| 2016-12-15 | 1. arrange HDMI part for review, add add phy part
2016-12-16
50 | 2016-12-19 | 1. Veloce DP emulation debug,. | veloce's main_link_ctrl signal problem seems have solution, will try this week
| 2016-12-20 | 1. check some usb case, extract configuration for further simulation/emuation
| 2016-12-21 | 1. finish isp_bypass rtl design, evaluate the area
2016-12-22
2016-12-23