## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 2016-11-28 | check cadance usb3 IP config
reconfig synopsys usb3 IP with high latency option on
run all local simulation with femtophy
check femtophy integration problem
| 2016-11-29 | run all local simulation with femtophy | 4 local case fail
debug femtophy integration problem
| 2016-11-30 | debug femtophy integration problem | left 3 local case fail, one pass
unpack tRoot, read doc and run basic sim
| 2016-12-01 | debug femphy integration problem | the uploaded waveform can't be read
read femtophy ATE note
local sim femtophy ATE and function testcase
| 2016-12-02 | debug femphy integration problem | left 2 local case fail, 1 case pass, uploaded waveform can't be read
|  | local sim femtophy ATE and function testcase | all pass but case not match with femtophy databook
connect a top wrapper with femtophy for Emulation
|  | synthesis tRoot | 400MHz 20%margin
49 | 2016-12-05 | confirm usb3 ATE test
confirm usb3 subsystem register controlled pins
|  | synthesis tRoot | 500MHz 5% margin
| 2016-12-06 | confirm usb3 ATE test | not resolved
usb3 subsystem register define
| 2016-12-07 | usb3 subsystem register design and local test
| 2016-12-08 | VBUSVLDEXT, VBUSVLDEXTSEL, OTGDISABLE,VBUSVALID, VBUS signal connection | not resolved
| 2016-12-09 | PKA and SPAcc training, usb3.0 review
50 | 2016-12-12 | finish simulation with AHB config, VBUSVLDEXT=0, VBUSVLDEXTSEL=0, OTGDISABLE=1
|  | The VBUSVLDEXT=0, VBUSVLDEXTSEL=0, OTGDISABLE=1 and charge pump connection is OK | resolved
| 2016-12-13 | AXI master interface is based on AXI3, and extend awlen/arlen to support 256 INCR burst, can connect to AXI4 IF
merge apb to ahb address, and test in NOC VIP environment
| 2016-12-14 | debug ahb to apb logic
generate usb30 and tRoot memory
usb30 subsystem
|  | confirm usb3 ATE test | resolved
| 2016-12-15 | connect usb30 subsystem
test ahb to apb logic conner case
| 2016-12-16 | connect usb30 subsystem | ver 1.0
51 | 2016-12-19 | add debug mux and ate test mux to usb30 subsystem | not resolved
prepare usb30 subsystem top stub file for SOC connection
run ate test sim with given config in the pin list in femtophy's environment
| 2016-12-20 | add ate test mux to usb30 subsystem | debug mux resovled, ate not
| 2016-12-21 | usb30 controller add rx detect in phy's P3 mode and do local simulation
generate spacc and pka memory
try synthesis spacc and pka to confirm their configuration
| 2016-12-22 | add security subsystem's apb registers and combine them with a timer and uart to one apb port
finish usb30 local simulation with rx detect in phy's P3 mode
do trng's local sim
| 2016-12-23 | connect security top
51 | 2016-12-26 | connect security top
|  | check usb30 all flow | not resolved
| 2016-12-27 | sim spacc and pka with memory model
| 2016-12-28 | modify usb30 top sdc | not resolved
|  | synthesis usb30 top-down | not resolved
| 2016-12-29 | modify usb30 top sdc | modified phy's sdc
| 2016-12-30 | run test usb30 controller synth constrain
|  | connect security top | without OTP
disable spacc SKP interface
53 | 2017-01-03 | synthesis usb30 top-down
|  | modify security top | not resolved
| 2017-01-04 | synthesis usb30 top-down
| 2017-01-05 | synthesis usb30 top-down | not resolved
|  | synthesis security top top-down | not resolved
| 2017-01-06 | use new software environment to run firmware
54 | 2017-01-12 | modify environment to run firmware
synthesis usb30 top-down with liyi release memory
| 2017-01-13 | modify amba vip to run firmware | not resolved
| 2017-01-14 | firmware not work correctly, debug
55 | 2017-01-16 | vip works in sirius, but not response correctly
synthesis usb3 subsys
| 2017-01-17 | formality fail
synthesis and try fomality
| 2017-01-18 | synthesis and try fomality
controller formality pass in coreConsultant
| 2017-01-19 | phy formality pass in both local syn env and Sirius syn env
try to use compile command
| 2017-01-20 | send some question for solvenet review
prepare for IP review meeting
56 | 2017-01-22 | change the dc environment and usb3_top formality pass
| 2017-01-23 | security subsystem formality pass
modify security subsys for apb to trust zone
release USB and SEC handoff_silver data