## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | 1. generate the source code for TZC400 2. integrate the TZC_2F and TZC_4F to a 6-filter TZC
| 2016-11-29 | 1. do simulation about reading at falling edge of SCK
| 2016-11-30 | 1. do simulation about reading at falling edge of SCK 2. IP reviews meeting 3. re-add the SD card controller to M7 subsystem
| 2016-12-01 | 1. add a sample flag for QSPI flash controller reading - read data can be at rising or falling edge of SCK 2. do simulation for QSPI reading at different sample flags 3. help zxu to build platform about M7 subsystem
| 2016-12-02 | 1. num of trace ports - 8 bits 2. split the async bridges in CoreSight SoC, and update the top of CXSOC
49 | 2016-12-05 | 1. do simulation about doing operation to flash during booting 2. find solutions to deal with the Debug and ETM ports on A7
| 2016-12-06 | 1. arrange the global register in M7 subsystem 2. renew the SPI in M7 subsystem if its source code is back 3. do simple simulation about new SPI
| 2016-12-07 | 1. deal with the ports of Debug and ETM on A7 2. addr decode for TSZ 3. deal with the LS pins in M7 subsystem and CXSOC
| 2016-12-08 | 1. add CXSOC to the top (zxu) 2. do simulation for CXSOC at top (zxu)
| 2016-12-09 | do simulation for CXSOC at top (zxu)
50 | 2016-12-12 | fix the reading switch between quad and standard mode. Do simulation for it
| 2016-12-13 | 1. re-generate memory and then do synthesis for M7 subsystem and CXSOC again 2. do synthesis for TZC400
| 2016-12-14 | deal with the ports on M7 subsystem and cxsoc, perfect it in Sirius top (zxu)
| 2016-12-15 | 1. verify the new SPI if sirius top is ready 2. sync the reset from RGU top, add the soft control from global register
| 2016-12-16 | sync the reset from RGU top, add the soft control from global register. deal with the relative ports on memory
51 | 2016-12-19 | do a simple simulation for CXSOC at new top (after adding cgu/rgu/rstn async)
| 2016-12-20 | perfact the sdc for M7/CS/TZC, re-new the synthesis
| 2016-12-21 | perfact the sdc for M7/CS/TZC, re-new the synthesis
| 2016-12-22 | verify the CoreSight on FPGA if it is ready with Li Yi
| 2016-12-23 | verify the CoreSight on FPGA if it is ready with Li Yi
52 | 2016-12-26 | verify the CoreSight on FPGA
| 2016-12-27 | verify the CoreSight on FPGA
| 2016-12-28 | sliver the rtl, re-view the sdc for M7 subsystem, CXSOC and TZC, and then generate the netlist
| 2016-12-29 | sliver the rtl, re-view the sdc for M8 subsystem, CXSOC and TZC, and then generate the netlist
| 2016-12-30 | sliver the rtl, re-view the sdc for M9 subsystem, CXSOC and TZC, and then generate the netlist
1 | 2017-01-02
| 2017-01-03 | fix the QSPI /WP init problem, do sim
| 2017-01-04 | fix the QSPI /WP init problem, do sim
| 2017-01-05 | verify the CoreSight on FPGA
| 2017-01-06 | verify the CoreSight on FPGA
2 | 2017-01-09
2017-01-10
2017-01-11
| 2017-01-12 | update the m7 top and try dc and fm for M7, CS and TZC
| 2017-01-13 | update the m7 top and try dc and fm for M7, CS and TZC
| 2017-01-14 | pin-share
3 | 2017-01-06 | silver the dc and fm for M7, CS and TZC
| 2017-01-17 | silver the dc and fm for M7, CS and TZC
| 2017-01-18 | pin-share
| 2017-01-19 | pin-share
| 2017-01-20 | pin-share
| 2017-01-21 | try formatlity flow
4 | 2017-01-22 | try formatlity flow
| 2017-01-23 | try formatlity flow and silver the design (including the M7 subsystem, CS and TZC)
| 2017-01-24 | pin-share global registers and signal connection prepare
| 2017-01-25 | pin-share global registers and signal connection prepare
2017-01-26
6 | 2017-02-06 | modify the pin-share occording to the new-assignment
| 2017-02-07 | modify the pin-share occording to the new-assignment
| 2017-02-08 | generate the test function pin-share
| 2017-02-09 | generate the test function pin-share
| 2017-02-10 | debug the CSSOC on fpga, co-work with LiYI
2017-02-11
7 | 2017-02-13 | re-new the pin-share for new-need
| 2017-02-14 | view tzc400 doc for top integration and use
| 2017-02-15 | do simulation for M7 subsystem if TOP is okay
| 2017-02-16 | do simulation for M7 subsystem if TOP is okay
| 2017-02-17 | do simulation for M7 subsystem if TOP is okay
8 | 2017-02-20 | Performance compare. Do simulation for the 2 M7 sub diagrams
| 2017-02-21 | replace the memory using the new
| 2017-02-23 | modify the m7 subsystem according the new diagram.
| 2017-02-24 | do synthesis and formality for new m7 and cssoc
| 2017-02-25 | do synthesis and formality for new m7 and cssoc