## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | list config parameter and update config for dma, slave wrap burst, msi, msix
| 2016-11-29 | list top input /output and write initial pcie_elbi module for external registers access
| 2016-11-30 | pull latest release of phy database and verify top
| 2016-12-01 | run simulation and analyze data transfer performance
| 2016-12-02 | check std cell datasheet and write initial top cgu module
49 | 2016-12-05 | update config parameter TARGET_ABOVE_CONFIG_LIMIT update pcie_elbi module
| 2016-12-06 | update pcie_elbi module
| 2016-12-07 | smulate pcie_elbi, need share noc port with axi dbi update sirius cgu
| 2016-12-08 | check hot-plug solution, open solvnet case write sirius rgu
| 2016-12-09 | update cgu, rgu and registers define
50 | 2016-12-12 | summary config parameter
| 2016-12-13 | summary input output port finish pcie subsystem review
| 2016-12-14 | check review action item with synopsys support update pcie_elbi module to only include msi / msg pin
| 2016-12-15 | update pcie_registers and pcie_registers_grant module to include local registers
| 2016-12-16 | run simulation for the three handmade module update cgu, rgu for latest checkin
51 | 2016-12-19 | continue run simulation and fix errors
| 2016-12-20 | continue run simulation and fix errors
| 2016-12-21 | add debug / interrupt module to include related pcie ports
| 2016-12-22 | add debug / interrupt module to include related pcie ports
| 2016-12-23 | Study and discuss TS IP
52 | 2016-12-26 | merge pcie core and phy sdc to top
| 2016-12-27 | update std cell for DWC_pcie_clkrst and update sdc
| 2016-12-28 | run top synthesis and fix timing
| 2016-12-29 | run top synthesis and fix timing
| 2016-12-30 | update non_secure_top accordingly and update registers' default value

## Weekly Status 2017
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
1 | 2017-01-03 | work on sar10_3
| 2017-01-04 | discuss rgu design with delay time run fm flow
| 2017-01-05 | work on sar10_3
| 2017-01-06 | prepare for support questions check pcie latest version update
2 | 2017-01-12 | run local sim & syn for pcie latest version
| 2017-01-13 | run simple pcie firmware in soc add phy_reset, add clock_gate for core and axi clock
| 2017-01-14 | integrate pcie vip in soc add scan mode for non_secure
3 | 2017-01-16 | integrate pcie vip in soc
| 2017-01-17 | run pcie firmware in soc update no_secure with abb change
| 2017-01-18 | run pcie firmware in soc try different dc and fm command / flow to pass fm check
| 2017-01-19 | try different dc and fm command / flow to pass fm check
| 2017-01-20 | work on pcie review and checklist
4 | 2017-01-22 | review pcie integration with starblaze integrate sirius_pin_share to non_secure
| 2017-01-23 | update pcie top with latest core release
| 2017-01-24 | run dc and fm with latest pcie subsystem update non_secure with latest sirius_pin_share and abb, run dc and fm | PCIE - done: subsystem with latest controller and phy release version ready. Local simulation passed. Synthesis netlist ready with formality passed. PCIE - plan: work on checklist to enhance the design Run local testlist with new subsystem top and check waveform Run more test in soc level (cover a7 / ddr path, cover iatu / dma) Run in veloce review sdc and netlist (phy filelist, scripts) non_secure - done: integrated cgu/rgu/abb/pin_share synthesis netlist non_secure - plan: finish ts control continue update with latest checkin (cgu/rgu) run simulation
5 | 2017-02-03 | update rgu registers reset value check pin_share synthesis report update pcie hand-placed logic and constraints
| 2017-02-04 | update cgu/ rgu update solvnet cases update perst_n logic
6 | 2017-02-06 | run sar10_3 simulation
| 2017-02-07 | update ts control rtl and run simulation
| 2017-02-08 | update pin_share wrapper, cgu, rgu, global registers
| 2017-02-09 | run firmware in soc level with iatu / edma feature, cover ddr / dmac path
| 2017-02-10 | run firmware in soc level with iatu / edma feature, cover ddr / dmac path