## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | Confirming GMAC architecture and reading databook. | any commnets
| 2016-11-29 | GMAC simulation try and fix some bug.
| 2016-11-30 | 1.Debug error in GMAC simulation. 2.Confirming the Microphone I2S slave interface 3.Studying the Rgmii IO PAD.
| 2016-12-01 | 1.Confirming the new GMAC IP release 2.Confirming the synthsis script in new GMAC IP release and write the new DC synthesis script 3.Studying the Rgmii IO PAD
| 2016-12-02 | 1.Discussion with BB team and Confirming the Sram_top architeture 2.Config the new IP parameter, including I2S, X2X, GS 3.Debug the error in dmac ip release
49 | 2016-12-05 | 1.Modify the sram_top and then join the BB simulation to debug
| 2016-12-06 | 1.Reading the DMAC databook and config the parameter 2. Join the BB simulation to debug SRAM_TOP
| 2016-12-07 | 1.Reading the DMAC databook and config the parameter 2.Join the BB simulation to debug SRAM_TOP
| 2016-12-08 | 1.Join the BB simulation to debug SRAM_TOP 2.Synthesize GMAC and DMAC
| 2016-12-09 | 1.Join the BB simulation to debug SRAM_TOP 2.Fix the connection in I2S master and slave IP
50 | 2016-12-12 | leaving day
| 2016-12-13 | studing the sos architecute and make the dmac configuration
| 2016-12-14 | synthesize the dmac and modify configuration
| 2016-12-15 | Implementing GMAC
| 2016-12-16 | 1.Implementing GMAC 2.the Sram_top perfomance evaluation
52 | 2016-12-26 | 1.GMAC synthesize 2.the Sram_top modification for performance
| 2016-12-27 | 1.GMAC synthesize 2.the Sram_top perfomance modification
| 2016-12-28 | 1.Implementing GMAC 2.Implemeting DMAC
| 2016-12-29 | 1.Implementing GMAC 3.Implemeting DMAC
| 2016-12-30 | 1.Implementing GMAC 4.Implemeting DMAC
53 | 2017-01-02 | double check the SRAM_TOP and modify the perfomace about AXI_X2X
| 2017-01-03 | double check the SRAM_TOP for assistance
| 2017-01-04 | double check the SRAM_TOP for assistance
| 2017-01-05 | 1.double check the SRAM_TOP for assistance 2.work on the dmac memory substituion
| 2017-01-06 | 1.double check the SRAM_TOP for assistance 2.prepare review report
54 | 2017-01-12 | view emmc ip databook
| 2017-01-13 | view emmc ip databook and synthsize try
| 2017-01-14 | view emmc ip databook and synthsize try
55 | 2017-01-16 | implementing emmc ip
| 2017-01-17 | implementing emmc ip
| 2017-01-18 | modify the sram_top and formality try
| 2017-01-19 | modify the sram_top and formality try
| 2017-01-20 | modify the sram_top and formality try
| 2017-01-22 | dmac formality try
56 | 2017-01-23