## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 2016-11-28 | ar8020 eco verification: usb host test on fpga
| 2016-11-29 | ar8020 eco verification: dma access dtcm itcm on veloce ar8020 usb to sdram path debug: test software programming | veloce usb environment not ready
| 2016-11-30 | ar8020 eco verification: usb host test on veloce ar8020 usb to sdram path debug: board test environment building and veloce environment building
| 2016-12-01 | ar8020 usb to sdram path debug: read U disk file and write to sdram/video bypass test on ar8020 board, software test running on veloce
| 2016-12-02 | ar8020 usb to sdram path debug: read U disk file and write to sdram/video bypass test on ar8020 board, software test running on veloce veloce Sirius DDR access error debug: find bug on veloce ddr phy module
49 | 2016-12-05 | ask for leave
| 2016-12-06 | ask for leave
| 2016-12-07 | ask for leave
| 2016-12-08 | ask for leave
| 2016-12-09 | ask for leave
50 | 2016-12-12 | Sirius whole chip simulation environment debug: DDR access right DDR Inline ECC license debug: check license feature on 27000@eda-11 right, send ticket on solvenet DDR multiphy preparation | DDR Inline ECC license error
| 2016-12-13 | DDR multiphy perparation DDR lnline ECC license debug: license get for EV version, configure new version DDR
| 2016-12-14 | DDR multiphy perpatation DDR burst length check: BL8 fix, required by DDR spec DDR local test environment building: built for old version DDRC, change to new version DDRC
| 2016-12-15 | DDR multiphy preparation: open case on solvenet to require kick-off training new version DDR synthesis DDR local test environment building: error on axi bus, need to debug
| 2016-12-16 | DDR multiphy preparation: need pulldown DDR local test environment building: environement ready, running testcase required Zheng Jinshan, 2 masters send 32*8 burst and analyzing ddr waveform
51 | 2016-12-19 | DDR local test environment simulation: run testcase for 2 masters and 3 masters to analyze DDRC effciency DDR multiphy preparation: waiting for license ar8020 arm ahbs port eco: timing violation reported, try to find solution
| 2016-12-20 | DDR local test environment simulation: find bug, send waveform to synopsys, said that it is caused by inline ecc, need to change to 3.00a version DDR multiphy preparation: waiting for license ar8020 arm ahbs port eco: find solution, do ECO, run formality
| 2016-12-21 | DDR local test environment simulation: download 3.00a version, reconfig DDRC, run simulation, former bug eliminated DDR multiphy perparation: license ready, pulldown ip ar8020 arm ahbs port eco: formality pass, run testcase for ECO
| 2016-12-22 | DDR local test environment simulation: try different transfer sequence, find DDRC effciency issue, send waveform to synopsys to help analyze reason DDR multiphy perparation: require synopsys to arrange kick-off training ar8020 arm ahbs port eco: building veloce environment for ECO code
| 2016-12-23 | DDR local test environment simulation: get synopsys reply for DDRC effciency issue causeb by CAM depth setting, change ddr driver, effciency improved DDR multiphy perparation: kick-off training at 3pm 12/28 ar8020 arm ahbs port eco: veloce environment ready, run usb and dma testcase on veloce
52 | 2016-12-26 | DDR local test environment simulation: run test for 3 masters and 6 masters accessing ar8020 arm ahbs port eco: big timing vio reported by backend, try to find solution
| 2016-12-27 | DDR local test environment simulation: analyze waveform, modified DDR driver setting ar8020 arm ahbs port eco: run formality, run simulation reconfigure DDRC for Inline ECC related setting, run synthesis
| 2016-12-28 | DDR4 multiphy Kick-off training ar8020 arm ahbs port eco: building testcase and environment for sdf simulation
| 2016-12-29 | try PHY compiler to generate configure and report file ar8020 arm ahbs port eco: run sdf simulation meeting with synopsys to discuss Inline ECC issue
| 2016-12-30 | ar8020 arm ahbs prot eco: debug sdf simulation issue modified DDRC configuration and re-synthesis, as big timing violation caused by Inline ECC related setting