## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | split ADB-400 bridge | any commnets
split ATB bridge
split APB async bridge
split NTS async bridge
| 2016-11-29 | connect a7_harden_subsystem top
| 2016-11-30 | connect a7_subsystem top
| 2016-12-01 | verify bus widht and syntax rules are ok.
| 2016-12-02 | connect some unused signals of cortexa7_integration to a7_harden_subsystem(not finished)
make sure basic configuration of SMMU, and programming slave interface
49 | 2016-12-05 | connect some unused signals of cortexa7_integration to a7_harden_subsystem and make sure these signals in right status
| 2016-12-06 | connect a7_subsystem to sirius top
| 2016-12-07 | verify and debug a7_subsystem, and make sure a7 can load code and access memory
| 2016-12-08 | verify cgu and rgu functions.
| 2016-12-09 | verify coresight function with Hao Zhang
50 | 2016-12-12 | cortexa7 harden subsystem verify
| 2016-12-13 | fix cortexa7 harden subsystem dc flow
| 2016-12-14 | fix cortexa7 harden subsystem unconstraints
| 2016-12-15 | fix cortexa7 harden subsystem unconstraints
| 2016-12-16 | generate SMMU rtl code
51 | 2016-12-19 | generate SMMU ram
| 2016-12-20 | add pll, pvt sensor lib into a7_harden_subsystem
| 2016-12-21 | check pll, pvt and sensor lib and debug
| 2016-12-22 | connect ls, rm, rme to global register and verify
| 2016-12-23 | adjust dc flow for new design, find power pin error of pll, pvt and sensor lib
52 | 2016-12-26 | debug power pin error of pll, pvt and sensor lib
| 2016-12-27 | adjust cortexa7_harden timing and fix power pin of pll, pvt and sensor
| 2016-12-28 | netlist and sdc of cortexa7_harden is ready
| 2016-12-29 | verify smmu ram integration
| 2016-12-30 | setup smmu dc flow
53 | 2017-01-03 | fix timing and smmu_dsp and smmu_video dc data is ready
| 2017-01-04 | extact lib file of a7_harden_subsystem and setup down top flow for a7_subsystem
| 2017-01-05 | fix timing and prepare the dc data of a7_subsystem
| 2017-01-05 | design and verify boot rom, its dc data is ready and booting from ROM is ready