## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | design 4 NOC subsystem
| 2016-11-29 | design 4 NOC subsystem
| 2016-11-30 | collect new interfaces and clock groups information for one combined NOC
| 2016-12-01 | debug NOC system
| 2016-12-02 | collect new interfaces and clock groups information for one combined NOC, and design part of the new NOC
49 | 2016-12-05 | fix the interface and clock inforamtion, and fix new address map, design the newNOC
| 2016-12-06 | redesign the address map, and add several new interfaces into NOC
| 2016-12-07 | add PCI-e apb interface into the NOC， and update the corresponding address map
| 2016-12-08 | synthesize the new NOC, read the documents about OTP
| 2016-12-09 | design the otp
50 | 2016-12-12 | collect the information about the outstanding number of IPs， and discuss the otp design
| 2016-12-13 | discuss the outstanding section，and dicuss the otp design
| 2016-12-14 | redesign the NOC network， and synthesize the newdesign
| 2016-12-15 | draw the otp controller diagram, and confirm the newquestion about OTP vendor
| 2016-12-16 | draw the otp controller diagram, and redesign the NOC, and synthesize the design
51 | 2016-12-19 | redesign the NOC owing to timing violations，and synthesize the new design， and write the otp read module，discuss the otp BISR funtion
| 2016-12-20 | collect the information about timing violations of NOC, and send it to Sonics surpports. And join the TSMC lecture. Write otp_read_ctrl module.
| 2016-12-21 | finish otp_read_ctrl module, and finish otp_program_ctrl module
| 2016-12-22 | write the otp_register and otp_top_ctrl module
| 2016-12-23 | redeisgn the NOC owing to timing violations about routers and tas, and synthesize the newly one.
| 2016-12-25 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one.
52 | 2016-12-19 | discuss the timing violations about NOC, and discuss ID types of NOC transfer. Write OTP_ctrl module.
| 2016-12-20 | join the training and bypass and HDMI review,write otp module
| 2016-12-21 | write otp module
| 2016-12-22 | run sdf of efuse and tcm ，and debug
| 2016-12-23 | run sdf of efuse and tcm ，and debug
| 2016-12-26 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one, and try different options, and debug sdf
| 2016-12-27 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one, and try different options, and debug sdf
| 2016-12-28 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one, and try different options, and debug sdf
| 2016-12-29 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one, and try different options, and debug sdf
| 2016-12-30 | redeisgn the NOC again owing to the timing violations, and synthesize the newly one, and try different options, and debug sdf
| 2016-01-03 | run new sdf, and change NOC options, and synthesize NOC
| 2016-01-04 | run new sdf, and change NOC options, and synthesize NOC
| 2016-01-05 | run new sdf, and change NOC options, and synthesize NOC
| 2016-01-06 | run new sdf, and change NOC options, and synthesize NOC
| 2016-01-12 | depart the combined NOC into 3 sub NOCs,and regroup them
| 2016-01-13 | depart the combined NOC into 3 sub NOCs, design NOC_ceva, and synthesize it
| 2016-01-14 | design NOC_vision, and synthesize it
| 2016-01-16 | design NOC_main
| 2016-01-17 | design NOC_main
| 2016-01-18 | review the final NOC details,and readdress the address map, and synthesize it
| 2016-01-19 | redesign NOC_main, added DMA to coherent bridge, BB to SRAM main
| 2016-01-20 | redesign NOC_main, and move ceva slaves from NOC_main to NOC_ceva
| 2016-01-22 | synthesize the three NOCs, and fm them, and synthesizie the otp, and fm it
| 2016-01-23 | synthesize the three NOCs, and fm them, and synthesizie the otp, and fm it
| 2016-01-24 | synthesize the three NOCs, and fm them, and synthesizie the otp, and fm it
| 2016-01-25 | synthesize the three NOCs, and fm them, and synthesizie the otp, and fm it
| 2016-01-26 | synthesize the three NOCs, and fm them, and synthesizie the otp, and fm it
| 2016-02-06 | create otp local simulation enviroment
| 2016-02-07 | create otp local simulation enviroment
| 2016-02-08 | run otp load main option for rst mode read
| 2016-02-09 | run otp load main option for rst mode read
| 2016-02-10 | run ate program
| 2016-02-13 | run ate program
| 2016-02-14 | help video bypass debug NOC
| 2016-02-15 | help video bypass debug NOC
| 2016-02-16 | try to tranport loacl otp simulation enviroment to soc
| 2016-02-17 | try to tranport loacl otp simulation enviroment to soc
| 2016-02-20 | rediesign the NOC, owing to add coresponding QOS singal, and ID width and types change
| 2016-02-21 | rediesign the NOC, owing to add coresponding QOS singal, and ID width and types change
| 2016-02-22 | synthesize the three NOCs, and fm them,try different NOC configuration for better timing
| 2016-02-23 | synthesize the three NOCs, and fm them,try different NOC configuration for better timing
| 2016-02-24 | synthesize the three NOCs, and fm them,try different NOC configuration for better timing
| 2016-02-28 | tranport loacl otp simulation enviroment to soc, and finish it
| 2016-03-01 | verify ate program in the new soc enviroment
| 2016-03-02 | verify ate program in the new soc enviroment, and finish it
2016-03-03
2016-03-04