## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 11/28/2016 | line_buffer module coding
| 11/29/2016 | line_buffer module coding
| 11/30/2016 | line_buffer module coding
| 12/01/2016 | line_buffer module coding
| 12/02/2016 | line_buffer module coding | sub module coding finished
49 | 12/05/2016 | line_buffer module top integreated | finished
| 12/06/2016 | compile && TB coding | ongoing&&line_buffer spec may changed
| 12/07/2016 | TB coding&&Debug | discuss about line_buffer&&bypass module merge
| 12/08/2016 | Debug&&DC <unfinished> | TB coding&Debug
| 12/09/2016 | Debug&&DC&Release <unfinished> | Leave
50 | 12/12/2016 | confirm the arch of line_buffer&&bypass module merge module | DONE && change can be added later
| 12/13/2016 | coding&&debug | Coding submodule
| 12/14/2016 | coding&&debug | Coding submodule
| 12/15/2016 | coding&&debug | top integrator,done
| 12/16/2016 | coding&&debug | tb_coding&&debug DONE
51 | 12/19/2016 | DC && DEBUG | Done
| 12/20/2016 | DEBUG | Done
| 12/21/2016 | Add new feathers&&DEBUG | Done
| 12/22/2016 | Add new feathers&&DEBUG | Done
| 12/23/2016 | Add new feathers&&DEBUG | Done, basic case pass
52 | 12/26/2016 | Add new feathers&&DEBUG | Add new feathers
| 12/27/2016 | MIPI_TOP integrate | MIPI_TOP integrate
| 12/28/2016 | DPHY Learning&Debug | MIPI_TOP integrate, DONE
| 12/29/2016 | DPHY Learning&Debug, DC for MIPI_TOP | DPHY Learning, DC for MIPI_TOP
| 12/30/2016 | DPHY Learning&Debug, DC for MIPI_TOP | DPHY Learning, DC for MIPI_TOP
1 | 1/03/2017 | DPHY Learning, DC for MIPI_TOP | DC for MIPI_TOP DONE
| 1/04/2017 | DPHY Learning& DSI learning | DPHY Learning
| 1/05/2017 | Video_if Debug | DPHY Learning & FM
| 1/06/2017 | Video_if Debug | coding dvp interface consideration about ddr clk and two dvp merge
| 1/12/2018 |  | MIPI IP UPDATA&& Try the flow again&DPHY Learning
| 1/13/2019 |  | MIPI IP UPDATA&& Try the flow again&DPHY Learning
| 1/14/2020 |  | Review&Modify the DC script of video_if&MIPI IP UPDATA