## Weekly Status
Week No. | Date | Working status | Blocking issue & Comment | Delivery version
48 | 2016-11-28 | bring up sim2 env: filelist, runsim script preparation; some updates to sirius top generation script
| 2016-11-29 | bring up sim2 env: fix noc compilation issue - same module name exists in 4 noc separately. Able to run simulation without compilation error in sim2.
| 2016-11-30 | debug m7, a7 simulation issues in sim2. replace gating logic with actual gating cells. M7 print to uart can work.
| 2016-12-01 | cleanup sim2 env and other supporting files, check into SVN. debug a7 firmware issue with Peng.
| 2016-12-02 | integrate a7-subsystem to top level. simulation issues are now handling by Peng. | simulation issues are now handling by Peng.
49 | 2016-12-05 | integrate ddrc (Maji is on maternity leave).
| 2016-12-06 | integrate ddrc: compilation passed. integrate a7 subsystem (need a7 to initialize ddrc)
| 2016-12-07 | integrate ddrc: FW not work as expected, Maji would come to debug tomorrow. integrate a7 subsystem: ok to execute ddrc FW for now. | ddrc fw not working as expected. Need Maji to debug.
| 2016-12-08 | new noc, a7 subsystem, coresight integration
| 2016-12-09 | refine sirius top gen script. new noc integration. ddrc issue resolved by Maji | a7 not working properly after new noc integrated. debug in progress.
50 | 2016-12-12 | cleanup recent update on DDRC, merge veloce's modification for DDRC. commit all changes. new top with most recent NOC and other modules are ready. start to review top-level clock connections.
| 2016-12-13 | connect rgu/cgu to sirius_top.
| 2016-12-14 | connect rgu/cgu to sirius_top. passed simulation.
| 2016-12-15 | top env: pass the env to Mentor emu team for Veloce bring up. ddrc env: bring up uvm env for ddr controller.
| 2016-12-16 | top env: new module integration - SRAM, BB(dummy), ISP(dummy), Display(dummy); still in progress. ddrc env: working now. adjust testcases to make scenarios required by Maji.
51 | 2016-12-19 | top env: new module integration - SRAM, BB(dummy), ISP(dummy), Display(dummy); done. ddrc env: some maintanence.
| 2016-12-20 | veloce env: start to integrate vendor's makefile to sim2's runsim flow. ddrc env: some maintanence.
| 2016-12-21 | veloce env: vendor's flow is integrated to runsim. met some issues in emulation and found need to sync some changes in A7 harden system. first case passed now. still need to cleanup/fine-tune env changes made in sim2. ddrc env: some maintanence.
| 2016-12-22 | top env: Integrate new sram, debugging FW issue.
| 2016-12-23 | for veloce flow and simulation flow, sim script is updated to fully separate compile phase and run phase, so that changing firmware does not require recompilation of the design.
52 | 2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30